## Form Responses 1
Timestamp | You are part of which of the following directors org | Select reporting manager per Sage? | What's your primary role for the release? | Enter the Team/Scrum team that you are mostly associated with during the release. (Select Only One) Note: If associated with multiple teams, please select individual capacity | Sprint Retrospective Effectiveness | Were the action item from the Sprint retrospectives addressed during this release? | What was the action item and how was it resolved during the release? | Are you directly involved in the Release Deliverables for current release items or items planned and in progress for future releases? | How would you rate Release Overall (Individual Perspective) ? | How would you rate the release planning in comparison to previous release plannings? (1-Poor, 5- Improved) | How well were you as an individual aware of your teams commitments and scope of work prior to release implementation start ? (1-Not Aware, 5- Aware) | What was your involvement in Release planning and the selection of commitments? (1-Not Involved, 5- Fully Involved) | Were you as an individual aware of the Release timelines and your tasks in hand for the Release ? (1-Somewhat Aware, 5- Fully Aware) | Detailed Epic Breakdown with estimates and scrum team ownership were done for your trackers parent epic prior to Release Implementation Initiation. | How confident were you in terms of your teams commitments and deliverables? (1-Not Confident, 5- Full Confidence) | How would you rate effectiveness the Sprint Planning Meetings ? (1-Not Effective, 5- Effective) | Individual items efforts estimate for completion of the task is done by whom ? (Desired state is by scrum team) | How would you rate effectiveness of the Daily Standup connect to understand and analyse your tasks in hand ? (1-Not Effective, 5- Effective) | How would you rate effectiveness of the Sprint Closure / review meetings ? (1-Not Effective, 5- Effective) | Was Sprint retrospective Conducted for your Team at the end of each Sprint | Do you as an individual get sufficient opportunity to raise risk or concerns during agile ceremonies? | Do you get opportunity to learn new things in accordance to your role release over release? | What percentage of your capacity in the sprint was reserved for Items such as CS Support Bugs/Requests which cannot be estimated but as a team you reserve some bandwidth, as per history you are aware of such requests and your team reserves capacity for it ?(individual capacity reserved) | Is your reserved capacity for the Historical support activities such as CS Bugs/Support tickets and others, sufficient during the release. | How much Adhoc requests (Request for which no bandwidth was reserved during Release/Sprint Planning) were received post sprint planning. | How was your available capacity utilised during the Release i.e. your workload. (1-Under Utilisation, 5- Over Utilisation) | Do you have sufficient details available on Jira to successfully and independently complete your assigned tasks(details like description, acceptance criteria and timeline) | Was the Release Coordination Group initiated with representatives from each directors org, helpful and more efficient in managing the Release checkpoints and ensuring the key asks were routed better to the respective team/people? | How well were dependencies managed in the Release. | Check the Release Ceremony where there is need to spend more efforts to make the release more effective. | Check the Sprint Ceremony where there is need to spend more efforts to make the release more effective. | What is the top improvement area in the below list you would suggest to improve for a smoother release? | What do we need to improve in Release Implementation | Anything that you would like to call out which improved in this release as compared to the previous releases. | What is the most probable reason that deviates the planned timelines? | Applicable only for pure DEV or QA Resources - What percent of your available capacity is impacted by process changes and new processes enablement on regular tasks not the other cleanup activities from previous releases (Not Applicable to EM's, SM's & Other Folks responsible for process streamlining) | Any other thought you would like to share related to the releases. | In Your individual opinion are we considering the release Delivery Timelines and milestones while we are planning and delivering our assigned tasks | Do you have any suggestion for improving and streamlining the release further? | Any Suggestions for Jira enhancements? | What was your engagement area during this release while not associated with the release deliverables? | Are you using AI for efficiency improvement in your day to day Dev/QA activity? | Which Tool are you using for your AI tasks | With the usage of AI what has been increase in your productivity as compared to previous release? | Are you getting the required support and guidance within Engineering to explore and increase efficiency using AI? | Column 47 | Column 48 | Column 49 | Column 50 | Column 51 | Column 52
2025-04-10 14:55 | Jegadeesh Santhana Krishnan | Rajesh Subramani | Dev | Hercules | 5 | No |  | Yes | Balanced | 4 | 4 | 4 | 4 | Yes | 5 | 5 | Scrum Team | 5 | 5 | Yes | YES | None | 10% to 20% | Yes | Moderate | Over Utilised (90% and Above) | Some Information but still need further details | Yes | Well Managed | Code Freeze Milestones and hardening phase | Sprint Closure/review | Ad-hoc requests prioritisation and acceptance | Change in Due date and QA Sign off Date restrictions | Reduced over commit | Reviews | More Than 5% but less than 10% |  | YES | nil |  |  | Yes | CoPilot | 10% to 20% | Yes
2025-04-09 15:17 | Mujtaba Ahmad | Ranjith Kumar M | Dev | Zeta | 3 | Yes | Reducing the communication gap btw qa and dev | Yes | Balanced | 4 | 3 | 4 | 5 | Yes | 4 | 4 | Scrum Team | 4 | 3 | Yes | YES | Moderate | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Code Freeze Milestones and hardening phase | Sprint Closure/review | Ad-hoc requests prioritisation and acceptance | Risk call out during Weekly SoS | Better Estimations & Epic Breakdown | Ad-hoc Tasks & improper prioritisation | More Than 5% but less than 10% |  | YES |  |  |  | Yes | ChatGPT, CoPilot | 10% to 20% | Yes
2025-04-11 10:15 | Mujtaba Ahmad | Priya Vanteru | Dev | Phi | 4 | Yes | NA | Yes | Balanced | 4 | 3 | 4 | 4 | Yes | 4 | 4 | Scrum Team | 5 | 4 | Yes | YES | Moderate | 10% to 20% | Yes | Multiple | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Committed Epic Prioritisation | Sprint Closure/review | Ad-hoc requests prioritisation and acceptance | Blocking Scope change | Better & transparent commitments | Ad-hoc Tasks & improper prioritisation | Less than 5% |  | YES | NA |  |  | Yes | ChatGPT, Langchain, Scrapper | 10% to 20% | Yes
2025-04-14 13:33 | Jegadeesh Santhana Krishnan | Chandra Sekhar Kusupati | Dev | Eirene | 5 | No |  | Yes | Well Managed | 5 | 5 | 5 | 5 | Yes | 5 | 5 | Individual | 5 | 5 | Yes | YES | Moderate | Less than 10% | Yes | None | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Continuous Epic Grooming | Sprint Closure/review | Ad-hoc requests prioritisation and acceptance | Change in Due date and QA Sign off Date restrictions | Better Estimations & Epic Breakdown | Improper Epic Breakdown & Estimations - Missing Sprint Backlog | Less than 5% |  | YES | NA |  |  | Yes | ChatGPT, CoPilot, Gemini, GitHub AI review | 20% to 30% | Yes
2025-04-08 15:41 | Mohammed Fayaz | Tharuni Sai Idupulapati | QA | Gryffindor | 5 | Yes | To have a call for PR reviews and mostly able to review the PR soon | Yes | Balanced | 4 | 4 | 4 | 5 | Yes | 4 | 4 | Individual | 5 | 3 | Yes | YES | Multiple | Less than 10% | Yes | Moderate | Balanced (80% - 90%) | Some Information but still need further details | Yes | Average | Continuous Epic Grooming | Sprint Closure/review | Ad-hoc requests prioritisation and acceptance | Change in Due date and QA Sign off Date restrictions | Reduced over commit | Ad-hoc Tasks & improper prioritisation | More than 10% but Less than 20% | NA | YES | Right now I feel it's Good | No |  | Yes | ChatGPT, AutoTest case Generation tool | 30% and Above | Yes
2025-04-11 10:28 | Mohammed Fayaz | Komal Varma | QA | Pheonix | 5 | Yes | having sprint assigned to trackers on jira before on the day of sprint planning, before the sprint starts | Yes | Balanced | 4 | 5 | 5 | 5 | Yes | 5 | 4 | Scrum Team | 5 | 5 | Yes | YES | Moderate | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Average | Continuous Epic Grooming | Sprint Closure/review | Ad-hoc requests prioritisation and acceptance | Blocking Scope change | Efficient Jira Usage (New Fields such as - Due date, QA Lead, QA Involvement, QA Signoff date) | Communication gap b/w dependent teams | Less than 5% |  | YES | Nthg |  |  | Yes | ChatGPT, Gemini | 10% to 20% | Yes
2025-04-08 14:14 | Mujtaba Ahmad | Priya Vanteru | Dev | Phi | 4 | Yes | We have created the FDR validation utility and also the mapping for the FDR | Yes | Balanced | 3 | 4 | 3 | 5 | Yes | 4 | 4 | Individual | 4 | 4 | Yes | Moderately | Moderate | More than 30% | Yes | Moderate | Balanced (80% - 90%) | Some Information but still need further details | Not aware of any such initiative. Though the release coordination among teams was better than previous releases among teams | Well Managed | Continuous Epic Grooming | Sprint Closure/review | Ad-hoc requests prioritisation and acceptance | Blocking Scope change | None | Delayed Response on open Queries, need multiple followups | More than 20% | NA | YES | NA | NA |  | Yes | ChatGPT, CoPilot, GitHub AI review, Claude | 10% or below | Yes
2025-04-08 17:59 | Mohammed Fayaz | Varun Batra | QA | Skywalker | 5 | No |  | Yes | Balanced | 5 | 5 | 5 | 5 | Yes | 5 | 5 | Individual | 5 | 5 | Yes | YES | Moderate | Less than 10% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Monitoring and Controlling Progress | Sprint Closure/review | Ad-hoc requests prioritisation and acceptance | Change in Due date and QA Sign off Date restrictions | Release Planning, Strategy & Schedule (Proper Checkpoint and dates on jira tickets) | Ad-hoc Tasks & improper prioritisation | Less than 5% |  | YES | NA |  |  | Yes | ChatGPT | 10% to 20% | Yes
2025-04-11 13:43 | Mohammed Fayaz | Prasad Deverakonda | QA | E2E | 5 | No |  | Yes | Chaotic | 5 | 5 | 1 | 3 | Yes | 4 | 5 | Individual | 4 | 4 | Yes | YES | Moderate | Less than 10% | Yes | Moderate | Over Utilised (90% and Above) | Optimal information available | Yes | Average | Monitoring and Controlling Progress | Sprint Closure/review | Ad-hoc requests prioritisation and acceptance | Risk call out during Weekly SoS | Sprint Planning Structure | Delay in commitments from dependant team | Less than 5% |  | YES | - Adhering to strict timelines and deployments during hardening phase & PST and ensure Test environments are stable enough before hand by taking required measure for it. | Making few Jira fields mandatory, from Regression/RCA pov making to ensure all details are upfated. And some template to be followed while closing any task with comments on it, #how many tcs added, existing, and cause/conclusion of the Issue. |  | Yes | ChatGPT | Just started using AI, need time to quantify | No
2025-04-09 12:55 | Jegadeesh Santhana Krishnan | Ashok Kumar Dantham | Dev | Iris | 5 | No |  | Yes | Balanced | 5 | 5 | 5 | 5 | Yes | 5 | 5 | Individual | 5 | 5 | Yes | YES | Moderate | 10% to 20% | Yes | Moderate | Over Utilised (90% and Above) | Optimal information available | Yes | Well Managed | Monitoring and Controlling Progress | Sprint Closure/review | Ad-hoc requests prioritisation and acceptance | Change in Due date and QA Sign off Date restrictions | Better Estimations & Epic Breakdown | Delay in commitments from dependant team | More Than 5% but less than 10% |  | YES |  |  |  | Yes | ChatGPT, CoPilot | 10% to 20% | Yes
2025-04-11 18:10 | Jegadeesh Santhana Krishnan | Jegadeesh Santhana Krishnan | EM |  |  |  |  | Yes | Well Managed | 5 | 5 | 5 | 5 | Yes | 5 | 5 | Scrum Team | 5 | 5 | Yes | YES | Moderate | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Release Kick Off | Sprint Closure/review | Ad-hoc requests prioritisation and acceptance | Blocking Scope change | None | PR Merges | My role involves process improvement and enablement (EM's, SM's & Other folks responsible for process streamlining) |  | YES | NA |  |  | Yes | ChatGPT, CoPilot | 10% to 20% | Yes
2025-04-10 15:37 | Mujtaba Ahmad | Diksha Khatri | Dev | Enigma | 4 | Yes | - | Yes | Balanced | 4 | 4 | 4 | 4 | Yes | 4 | 4 | Individual | 4 | 4 | Yes | YES | Moderate | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Code Freeze Milestones and hardening phase | Sprint Planning | Ad-hoc requests prioritisation and acceptance | Risk call out during Weekly SoS | Risk call out (Release Confluence Page) | PR Merges | More Than 5% but less than 10% |  | YES | - |  |  | Yes | ChatGPT, CoPilot | 10% to 20% | Yes
2025-04-08 15:51 | Jegadeesh Santhana Krishnan | Ankur Sachdeva | Dev | Chipmuks | 4 | Yes | N/A | Yes | Balanced | 4 | 4 | 3 | 4 | Yes | 4 | 4 | Scrum Team | 4 | 4 | Yes | YES | Moderate | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Some Information but still need further details | Not aware of any such initiative. Though the release coordination among teams was better than previous releases among teams | Well Managed | Committed Epic Prioritisation | Sprint Planning | Ad-hoc requests prioritisation and acceptance | Risk call out during Weekly SoS | Reduced over commit | Modifications on Approved Tech designs | More Than 5% but less than 10% |  | YES | no |  |  | Yes | ChatGPT, CoPilot | 20% to 30% | Yes
2025-04-10 15:17 | Mohammed Fayaz | Komal Varma | QA | Hercules | 5 | Yes | Provided retro update on having sprint planning grooming session or atleast having backlog scrubbing. Which started taking place and which was helpful in planning in actual sprint plan meet. | Yes | Balanced | 4 | 4 | 4 | 5 | Yes | 4 | 5 | Scrum Team | 5 | 5 | Yes | YES | Moderate | 10% to 20% | Yes | None | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Committed Epic Prioritisation | Sprint Planning | Ad-hoc requests prioritisation and acceptance | Risk call out during Weekly SoS | Release Planning, Strategy & Schedule (Proper Checkpoint and dates on jira tickets) | Ad-hoc Tasks & improper prioritisation | More than 10% but Less than 20% | NA | YES | NA | NA |  | Yes | ChatGPT, CoPilot | 10% to 20% | Yes
2025-04-14 12:33 | Jegadeesh Santhana Krishnan | Anusha Badveeti | Dev & Scrum Master | Tranformers | 4 | Yes | The issues were handled within the team they were about details to be provided in tickets | Yes | Balanced | 4 | 4 | 4 | 4 | Yes | 4 | 4 | Individual | 4 | 4 | Yes | YES | Moderate | 20% to 30% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Continuous Epic Grooming | Sprint Planning | Ad-hoc requests prioritisation and acceptance | Blocking Scope change | Better Estimations & Epic Breakdown | Reviews | More than 10% but Less than 20% | None | YES | None | None |  | Yes | ChatGPT, CoPilot, Gemini | 10% to 20% | Yes
2025-04-09 12:54 | Mujtaba Ahmad | Ranjith Kumar M | Dev | Zeta | 5 | Yes | Better sprint planning and timely update of JIRA fields | Yes | Balanced | 5 | 4 | 4 | 4 | Partially/Incomplete | 3 | 4 | Individual | 4 | 4 | Yes | YES | None | 10% to 20% | Yes | Multiple | Over Utilised (90% and Above) | Optimal information available | Not aware of any such initiative. Though the release coordination among teams was better than previous releases among teams | Average | Continuous Epic Grooming | Sprint Planning | Ad-hoc requests prioritisation and acceptance | Blocking Scope change | Sprint Planning Structure | PR Merges | More Than 5% but less than 10% |  | YES | No |  |  | Yes | ChatGPT, CoPilot | 10% or below | Yes
2025-04-09 18:14 | Mujtaba Ahmad | Diksha Khatri | Dev | Titans | 5 | Yes | Quick pr reviews | Yes | Well Managed | 5 | 5 | 5 | 5 | Yes | 5 | 5 | Individual | 5 | 5 | Yes | YES | Moderate | 20% to 30% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Epic Breakdown | Sprint Planning | Ad-hoc requests prioritisation and acceptance | Blocking Scope change | Better & transparent commitments | Ad-hoc Tasks & improper prioritisation | More Than 5% but less than 10% |  | YES | n/a |  |  | Yes | ChatGPT, CoPilot | 10% to 20% | Yes
2025-04-08 12:54 | Mujtaba Ahmad | Ranjith Kumar M | Dev | Zeta | 4 | No |  | Yes | Balanced | 4 | 5 | 5 | 5 | Yes | 4 | 4 | Scrum Team | 5 | 4 | Yes | YES | Moderate | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Monitoring and Controlling Progress | Sprint Planning | Ad-hoc requests prioritisation and acceptance | Risk call out during Weekly SoS | Work allocation with sufficient capacity reserve | Ad-hoc Tasks & improper prioritisation | Less than 5% | N/A | YES | N/A | N/A |  | Yes | ChatGPT, CoPilot | 10% to 20% | Yes
2025-04-11 19:09 | Mohammed Fayaz | Varun Batra | QA | Individual Capacity, Not Associated with any particular team | 3 | Yes | Improvisation of agents certification process for release | Yes | Chaotic | 3 | 5 | 4 | 3 | No | 5 | 4 | Individual | 5 | 3 | No | YES | Moderate | 20% to 30% | Yes | Multiple | Over Utilised (90% and Above) | Optimal information available | Yes | Average | Monitoring and Controlling Progress | Sprint Planning | Ad-hoc requests prioritisation and acceptance | Strict Bug SLA's | Release Planning, Strategy & Schedule (Proper Checkpoint and dates on jira tickets) | Ad-hoc Tasks & improper prioritisation | More than 20% | There is a larger need for process optimisation especially in mission critical things like agent and workers which leads to more burnout of people involved due to many ad hoc and unplanned things that come up. | Not Efficiently | Yes better process for branching and git handling is needed as team is still not aware where to cut patch / hotfix branches from. Even what should be naming convention of branches is stillone grey area for team. Secondly, better management of unplanned tasks is needed as a lot of ad hoc requests come up from SME perspective along with other release items. |  |  | Yes | ChatGPT, CoPilot | 20% to 30% | Yes
2025-04-11 12:48 | Mohammed Fayaz | Anusha Jharupula | QA | Indus | 5 | Yes | To gain better control over the burndown chart by effectively managing the JIRA tasks. | Yes | Well Managed | 5 | 5 | 5 | 5 | Yes | 5 | 5 | Scrum Team | 5 | 5 | Yes | YES | Multiple | 10% to 20% | Yes | Moderate | Over Utilised (90% and Above) | Optimal information available | Yes | Well Managed | Monitoring and Controlling Progress | Sprint Planning | Ad-hoc requests prioritisation and acceptance | Risk call out during Weekly SoS | Release Planning, Strategy & Schedule (Proper Checkpoint and dates on jira tickets) | Non Release Activities | Less than 5% | NA | YES | NA | NA |  | Yes | ChatGPT | 10% or below | Yes
2025-04-10 14:46 | Mujtaba Ahmad | Priya Vanteru | Dev | Falcon | 5 | No |  | Yes | Balanced | 4 | 5 | 4 | 5 | Yes | 5 | 5 | Scrum Team | 5 | 4 | Yes | YES | Moderate | 10% to 20% | Yes | Multiple | Balanced (80% - 90%) | Optimal information available | Not aware of any such initiative. Though the release coordination among teams was better than previous releases among teams | Well Managed | Monitoring and Controlling Progress | Sprint Planning | Ad-hoc requests prioritisation and acceptance | Change in Due date and QA Sign off Date restrictions | Better Estimations & Epic Breakdown | Reviews | More Than 5% but less than 10% |  | YES | NA |  |  | Yes | ChatGPT, CoPilot | 20% to 30% | Yes
2025-04-11 12:13 | Mujtaba Ahmad | Raman Soni | Dev | Ganges | 5 | Yes | Had call with Ram and Architect council regarding the branching strategy of patch releases and mongoose-util issue. Listed out the action items in the doc. | Yes | Well Managed | 5 | 5 | 5 | 5 | Yes | 5 | 5 | Scrum Team | 5 | 5 | Yes | YES | None | Less than 10% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Monitoring and Controlling Progress | Sprint Planning | Ad-hoc requests prioritisation and acceptance | Risk call out during Weekly SoS | Better & transparent commitments | Ad-hoc Tasks & improper prioritisation | Less than 5% |  | YES | fix issues in integrator-common-util |  |  | Yes | CoPilot | 10% to 20% | Yes
2025-04-11 13:54 | Mujtaba Ahmad | SWATANTRA ROUT | Dev & Scrum Master | Iota | 5 | Yes | - We started having a clear sprint backlog defined from this sprint - We had an action item to refine our KTs. We preserved dedicated bandwidth for that and created a JIRA to refine the trainings. | Yes | Balanced | 4 | 4 | 3 | 5 | Yes | 5 | 4 | Scrum Team | 5 | 4 | Yes | YES | Moderate | Less than 10% | Yes | Moderate | Balanced (80% - 90%) | Some Information but still need further details | Yes | Average | Monitoring and Controlling Progress | Sprint Planning | Ad-hoc requests prioritisation and acceptance | Blocking Scope change | Release Planning, Strategy & Schedule (Proper Checkpoint and dates on jira tickets) | Improper Epic Breakdown & Estimations - Missing Sprint Backlog | More Than 5% but less than 10% |  | YES | NA |  |  | Yes | ChatGPT, CoPilot, GitHub AI review | 10% or below | Yes
2025-04-09 15:34 | Mujtaba Ahmad | Priya Vanteru | Dev & Scrum Master | Phi | 4 | No |  | Yes | Balanced | 4 | 5 | 5 | 5 | Yes | 4 | 3 | Individual | 4 | 4 | Yes | Moderately | None | 10% to 20% | Yes | Moderate | Over Utilised (90% and Above) | Some Information but still need further details | Yes | Average | Monitoring and Controlling Progress | Sprint Planning | Ad-hoc requests prioritisation and acceptance | Blocking Scope change | Reduced over commit | Communication gap b/w dependent teams | Less than 5% |  | Not Efficiently | NA | NA |  | No | ChatGPT, CoPilot | 10% or below | Yes
2025-04-08 14:57 | Jegadeesh Santhana Krishnan | Ankur Sachdeva | Dev & Scrum Master | Echo | 5 | Yes | Proper prioritisation of adhoc and P1 tasks | Yes | Well Managed | 5 | 5 | 5 | 5 | Yes | 5 | 5 | Individual | 5 | 5 | Yes | YES | Multiple | 10% to 20% | Yes | Moderate | Over Utilised (90% and Above) | Some Information but still need further details | Yes | Well Managed | Code Freeze Milestones and hardening phase | Sprint Retrospective | Ad-hoc requests prioritisation and acceptance | Risk call out during Weekly SoS | Better & transparent commitments | CS Bugs higher than the reserved Capacity | More Than 5% but less than 10% |  | YES | no |  |  | Yes | ChatGPT, CoPilot, GitHub AI review | 20% to 30% | Yes
2025-04-10 15:34 | Mohammed Fayaz | Komal Varma | QA | Eirene | 3 | No |  | Yes | Balanced | 3 | 4 | 4 | 4 | Yes | 5 | 4 | Individual | 4 | 4 | Yes | YES | Moderate | Less than 10% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Committed Epic Prioritisation | Sprint Retrospective | Ad-hoc requests prioritisation and acceptance | Change in Due date and QA Sign off Date restrictions | Sprint Planning Structure | Communication gap b/w dependent teams | Less than 5% |  | YES | NO |  |  | Yes | ChatGPT, CoPilot | 10% or below | Yes
2025-04-11 13:21 | Mujtaba Ahmad | Ranjith Kumar M | Dev | Gryffindor | 5 | Yes | Do next sprint planning after and according to the closure of current sprint. | Yes | Balanced | 4 | 4 | 4 | 4 | Partially/Incomplete | 4 | 4 | Scrum Team | 4 | 4 | Yes | Moderately | Multiple | 10% to 20% | No | Multiple | Balanced (80% - 90%) | Optimal information available | Yes | Average | Committed Epic Prioritisation | Sprint Retrospective | Ad-hoc requests prioritisation and acceptance | Risk call out during Weekly SoS | None | Ad-hoc Tasks & improper prioritisation | Less than 5% |  | YES | NA |  |  | Yes | ChatGPT, CoPilot | 10% to 20% | Yes
2025-04-09 12:01 | Mujtaba Ahmad | Ranjith Kumar M | Dev & Scrum Master | Zeta | 3 | Yes | Grooming, Better story pointing | Yes | Balanced | 3 | 3 | 3 | 3 | Yes | 3 | 3 | Scrum Team | 3 | 3 | Yes | YES | None | 10% to 20% | No | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Continuous Epic Grooming | Sprint Retrospective | Ad-hoc requests prioritisation and acceptance | Blocking Scope change | Better Estimations & Epic Breakdown | Communication gap b/w dependent teams | My role involves process improvement and enablement (EM's, SM's & Other folks responsible for process streamlining) | Too many JIRA fields (adding dates on epic,story,subtask) are spamming the mails and date misses | YES | NA | Try to reduce the number of JIRA field changes, not every tracker's subtask required qa-signoff, qa ready date. Mails on missing start date is not necessary |  | Yes | ChatGPT, CoPilot, Perplexity, Claude | 30% and Above | Yes
2025-04-09 02:46 | Mujtaba Ahmad | Mujtaba Ahmad | EM |  |  |  |  | Yes | Balanced | 5 | 5 | 5 | 5 | Partially/Incomplete | 5 | 4 | Scrum Team | 4 | 4 | Yes | YES | Multiple | 10% to 20% | Yes | None | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Continuous Epic Grooming | Sprint Retrospective | Ad-hoc requests prioritisation and acceptance | Strict Bug SLA's | Work allocation with sufficient capacity reserve | Improper Epic Breakdown & Estimations - Missing Sprint Backlog | My role involves process improvement and enablement (EM's, SM's & Other folks responsible for process streamlining) |  | YES | NA |  |  | Yes | ChatGPT | 10% to 20% | Yes
2025-04-10 14:55 | Mujtaba Ahmad | Priya Vanteru | Dev & Scrum Master | Indus | 3 | Yes | In previous sprint , the action item was , if sprint tasks got delayed due to some adhoc tasks , we should callout those risks during DSU's.Because it was impacting our planning and also the sprint burndown chart was going up only. We resolved this by calling out those risks in the DSU only so in case any priority adhoc item came, we move a planned tracker of similar size to next sprints so that planning remains on point and also sprint burndown chart is not much affected. | Yes | Balanced | 5 | 5 | 5 | 5 | Yes | 4 | 4 | Scrum Team | 3 | 3 | Yes | YES | Moderate | 10% to 20% | Yes | Moderate | Over Utilised (90% and Above) | Some Information but still need further details | Yes | Well Managed | Continuous Epic Grooming | Sprint Closure/review | Backlog & CS bugs prioritisation | Blocking Scope change | Efficient Jira Usage (New Fields such as - Due date, QA Lead, QA Involvement, QA Signoff date) | Ad-hoc Tasks & improper prioritisation | More Than 5% but less than 10% |  | YES | none |  |  | Yes | ChatGPT, CoPilot | 10% to 20% | Yes
2025-04-11 17:13 | Mujtaba Ahmad | SWATANTRA ROUT | Dev & Scrum Master | Iota | 5 | No |  | Yes | Well Managed | 4 | 5 | 5 | 5 | Yes | 5 | 5 | Scrum Team | 5 | 4 | Yes | YES | None | 10% to 20% | Yes | Moderate | Over Utilised (90% and Above) | Optimal information available | Yes | Well Managed | Continuous Epic Grooming | Sprint Closure/review | Backlog & CS bugs prioritisation | Blocking Scope change | Release Planning, Strategy & Schedule (Proper Checkpoint and dates on jira tickets) | Ad-hoc Tasks & improper prioritisation | My role involves process improvement and enablement (EM's, SM's & Other folks responsible for process streamlining) |  | YES | NA |  |  | Yes | CoPilot, GitHub AI review | 10% or below | Yes
2025-04-08 13:11 | Mujtaba Ahmad | Raman Soni | Dev & Scrum Master | Apollo | 3 | Yes | We were facing issues with extended discussions beyond the stipulated time for DSUs and other meetings. We decided to keep DSU and other scrum meetings to quick updates and sticking to the agenda. Any other important callouts were to be made in a different call & by blocking that time seperately. | Yes | Balanced | 4 | 4 | 4 | 4 | Yes | 4 | 4 | Scrum Team | 4 | 4 | Yes | YES | Moderate | Less than 10% | Yes | None | Balanced (80% - 90%) | Some Information but still need further details | Yes | Average | Continuous Epic Grooming | Sprint Closure/review | Backlog & CS bugs prioritisation | Blocking Scope change | Better & transparent commitments | Improper Epic Breakdown & Estimations - Missing Sprint Backlog | Less than 5% |  | YES | no | no |  | Yes | ChatGPT, CoPilot | 10% or below | Yes
2025-04-09 13:11 | Mujtaba Ahmad | Priya Vanteru | Dev | Indus | 5 | Yes | Jira trackers assignment and close upto the status completed for the sprint was actively taken up the team and closed | Yes | Well Managed | 5 | 5 | 5 | 5 | Yes | 5 | 5 | Scrum Team | 5 | 5 | Yes | YES | Multiple | More than 30% | Yes | Moderate |  | Optimal information available | Yes | Well Managed | Continuous Epic Grooming | Sprint Closure/review | Backlog & CS bugs prioritisation | Change in Due date and QA Sign off Date restrictions | Efficient Jira Usage (New Fields such as - Due date, QA Lead, QA Involvement, QA Signoff date) | CS Bugs higher than the reserved Capacity | Less than 5% | NA | YES | NA | NA |  | Yes | ChatGPT, CoPilot, Langchain | 20% to 30% | Yes
2025-04-10 14:44 | Mujtaba Ahmad | Priya Vanteru | Dev | Falcon | 3 | Yes | NA | Yes | Balanced | 4 | 4 | 4 | 4 | Partially/Incomplete | 4 | 3 | Scrum Team | 4 | 2 | Yes | YES | Moderate | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Some Information but still need further details | Not aware and did not find any significant change in the release coordination among teams | Well Managed | Continuous Epic Grooming | Sprint Closure/review | Backlog & CS bugs prioritisation | Strict Bug SLA's | Work allocation with sufficient capacity reserve | Improper Epic Breakdown & Estimations - Missing Sprint Backlog | Less than 5% |  | YES | no |  |  | Yes | ChatGPT | 30% and Above | Yes
2025-04-08 16:32 | Jegadeesh Santhana Krishnan | Ankur Sachdeva | Dev | Echo | 4 | No |  | Yes | Balanced | 3 | 4 | 4 | 3 | Yes | 4 | 3 | Individual | 4 | 3 | Yes | Moderately | Multiple | 10% to 20% | No | Moderate | Balanced (80% - 90%) | Optimal information available | Not aware and did not find any significant change in the release coordination among teams | Average | Monitoring and Controlling Progress | Sprint Closure/review | Backlog & CS bugs prioritisation | Blocking Scope change | Effective communication | Ad-hoc Tasks & improper prioritisation | Less than 5% |  | Not Efficiently | NA |  |  | Yes | ChatGPT, CoPilot | 10% to 20% | Yes
2025-04-10 16:47 | Mohammed Fayaz | Prasad Deverakonda | QA | Iota | 5 | Yes | Should have the dedicated document related to IA Automation framework. Team is working on it. | Yes | Well Managed | 5 | 5 | 5 | 5 | Yes | 4 | 5 | Individual | 5 | 5 | Yes | YES | Moderate | 10% to 20% | Yes | Moderate | Over Utilised (90% and Above) | Optimal information available | Yes | Well Managed | Monitoring and Controlling Progress | Sprint Closure/review | Backlog & CS bugs prioritisation | Risk call out during Weekly SoS | Reduced over commit | Ad-hoc Tasks & improper prioritisation | Less than 5% |  | YES | No |  |  | Yes | ChatGPT | Just started using AI, need time to quantify | Yes
2025-04-09 15:48 | Jegadeesh Santhana Krishnan | Rajesh Subramani | Dev & Scrum Master | Hercules | 4 | Yes | We have initiated separate grooming sessions for the sprint, as we previously conducted these during the planning phase. | Yes | Balanced | 4 | 4 | 5 | 5 | Yes | 4 | 4 | Individual | 4 | 4 | Yes | YES | Moderate | Less than 10% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Average | Continuous Epic Grooming | Sprint DSU's | Backlog & CS bugs prioritisation | Change in Due date and QA Sign off Date restrictions | Release Planning, Strategy & Schedule (Proper Checkpoint and dates on jira tickets) | Reviews | My role involves process improvement and enablement (EM's, SM's & Other folks responsible for process streamlining) |  | YES | N/A |  |  | Yes | CoPilot | 10% or below | Yes
2025-04-10 15:04 | Mujtaba Ahmad | Priya Vanteru | Dev & Scrum Master | Falcon | 5 | Yes | Qa and Dev were in sync for the release deliverables. | Yes | Balanced | 4 | 4 | 4 | 4 | Partially/Incomplete | 4 | 4 | Scrum Team | 4 | 4 | Yes | Moderately | Moderate | 10% to 20% | Yes | Moderate |  | Some Information but still need further details | Not aware and did not find any significant change in the release coordination among teams | Average | Continuous Epic Grooming | Sprint DSU's | Backlog & CS bugs prioritisation | Blocking Scope change | Better & transparent commitments | Improper Epic Breakdown & Estimations - Missing Sprint Backlog | More than 10% but Less than 20% |  | YES | No |  |  | Yes | ChatGPT | Just started using AI, need time to quantify | Yes
2025-04-10 17:19 | Jegadeesh Santhana Krishnan | Subhan Ansari | Dev | Aliens | 5 | Yes | Bandwith for ad-hock task | Yes | Chaotic |  |  |  |  | Yes |  |  | Scrum Team |  |  | Yes | YES | Multiple | 10% to 20% | Yes |  |  | Optimal information available | Yes |  | Committed Epic Prioritisation | Sprint Planning | Backlog & CS bugs prioritisation | Strict Bug SLA's | Effective communication | Ad-hoc Tasks & improper prioritisation | More Than 5% but less than 10% |  | YES | NA |  |  | Yes | ChatGPT, CoPilot, Gemini | 10% to 20% | Yes
2025-04-09 11:24 | Jegadeesh Santhana Krishnan | Jegadeesh Santhana Krishnan | Dev | Dynamos | 5 | Yes | Peers doing the proper review | Yes | Balanced | 5 | 5 | 5 | 5 | Yes | 5 | 5 | Scrum Team | 5 | 5 | Yes | YES | Multiple | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Continuous Epic Grooming | Sprint Planning | Backlog & CS bugs prioritisation | Blocking Scope change | Reduced over commit | Improper Epic Breakdown & Estimations - Missing Sprint Backlog | Less than 5% |  | YES | NA |  |  | Yes | ChatGPT, CoPilot | 10% or below | Yes
2025-04-14 12:13 | Jegadeesh Santhana Krishnan | Ramakrishna Grandhi | Dev & Scrum Master | Tintin | 4 | Yes | no action point | Yes | Balanced | 4 | 4 | 4 | 4 | Yes | 4 | 4 | Scrum Team | 4 | 4 | No | YES | Moderate | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Not aware and did not find any significant change in the release coordination among teams | Well Managed | Continuous Epic Grooming | Sprint Planning | Backlog & CS bugs prioritisation | Blocking Scope change | Sprint Planning Structure | Improper Epic Breakdown & Estimations - Missing Sprint Backlog | More than 10% but Less than 20% | nothing specific | YES | na | na |  | Yes | ChatGPT | 10% to 20% | Yes
2025-04-08 13:44 | Mujtaba Ahmad | Priya Vanteru | QA | Phi | 4 | Yes | Developer will provide the scrrenshot to document team before implementing entore connector | Yes | Balanced | 4 | 3 | 3 | 3 | Yes | 3 | 3 | Scrum Team | 3 | 3 | Yes | Moderately | None | 10% to 20% | No | Multiple | Over Utilised (90% and Above) | Optimal information available | Not aware and did not find any significant change in the release coordination among teams | Average | Monitoring and Controlling Progress | Sprint Planning | Backlog & CS bugs prioritisation | Strict Bug SLA's | Dependency management | Ad-hoc Tasks & improper prioritisation | More Than 5% but less than 10% |  | YES | Better soprint planning |  |  | Yes | ChatGPT | 10% or below | Yes
2025-04-09 17:31 | Mohammed Fayaz | Tharuni Sai Idupulapati | EM |  |  |  |  | Yes | Chaotic | 5 | 5 | 5 | 5 | Yes | 5 | 5 | Scrum Team | 5 | 4 | Yes | YES | Multiple | Less than 10% | Yes | Moderate |  | Optimal information available | Yes | Average | Code Freeze Milestones and hardening phase | Sprint Closure/review | Bugs Management & Deferring | Strict Bug SLA's | Release Planning, Strategy & Schedule (Proper Checkpoint and dates on jira tickets) | Delayed Response on open Queries, need multiple followups | My role involves process improvement and enablement (EM's, SM's & Other folks responsible for process streamlining) |  | YES | Last minute changes are really painful, we need to avoid last minute inclusions and multiple follow ups required on the deployment cloudOPs trackers, we need to focus in streamlining this process. |  |  | Yes | ChatGPT | 20% to 30% | Yes
2025-04-11 19:25 | Mujtaba Ahmad | SWATANTRA ROUT | Dev | Iota | 5 | Yes | have clear sprint backlog, IA Automation doc | Yes | Balanced | 4 | 4 | 4 | 4 | Partially/Incomplete | 4 | 4 | Scrum Team | 4 | 4 | Yes | YES | Moderate | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Some Information but still need further details | No | Average | Continuous Epic Grooming | Sprint Closure/review | Bugs Management & Deferring | Blocking Scope change | Better & transparent commitments | Modifications on Approved Tech designs | More Than 5% but less than 10% |  | YES | NA |  |  | Yes | CoPilot, GitHub AI review | 10% or below | No
2025-04-09 11:21 | Jegadeesh Santhana Krishnan | Anusha Badveeti | Dev | Dynamos | 4 | Yes | Discussed how branch merges are causing issue at the end of release and now following normal release branch process | Yes | Balanced | 4 | 5 | 5 | 5 | Yes | 4 | 5 | Scrum Team | 5 | 4 | Yes | YES | Multiple | Less than 10% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Epic Breakdown | Sprint Closure/review | Bugs Management & Deferring | Strict Bug SLA's | Release Planning, Strategy & Schedule (Proper Checkpoint and dates on jira tickets) | Improper Epic Breakdown & Estimations - Missing Sprint Backlog | Less than 5% |  | YES | NA |  |  | Yes | ChatGPT, CoPilot, GitHub AI review | 10% to 20% | Yes
2025-04-11 15:42 | Mujtaba Ahmad | Raman Soni | Dev | Apollo | 4 | Yes | Meetings should have the hard stops, this we are trying to follow but not adhering to it from the long time | Yes | Balanced | 4 | 4 | 4 | 4 | Yes | 4 | 4 | Scrum Team | 3 | 4 | Yes | Moderately | Moderate | 10% to 20% | Yes | Moderate | Over Utilised (90% and Above) | Some Information but still need further details | Yes | Average | Code Freeze Milestones and hardening phase | Sprint Planning | Bugs Management & Deferring | Blocking Scope change | Effective communication | Modifications on Approved Tech designs | Less than 5% |  | YES | no | no |  | Yes | ChatGPT, CoPilot | 10% to 20% | Yes
2025-04-11 12:17 | Mujtaba Ahmad | Raman Soni | Dev | Stark | 5 | Yes | Proper testing before sending any fix and verify all the test suites (Including backend + UI) | Yes | Well Managed | 5 | 5 | 5 | 5 | Yes | 5 | 5 | Scrum Team | 5 | 5 | Yes | YES | Multiple | 20% to 30% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Committed Epic Prioritisation | Sprint Planning | Bugs Management & Deferring | Risk call out during Weekly SoS | Work allocation with sufficient capacity reserve | Ad-hoc Tasks & improper prioritisation | Less than 5% |  | YES | NA |  |  | Yes | ChatGPT, CoPilot | 10% to 20% | Yes
2025-04-09 17:04 | Jegadeesh Santhana Krishnan | Ramakrishna Grandhi | Dev & Scrum Master | Avengers | 3 | No |  | Yes | Balanced | 4 | 4 | 4 | 4 | Partially/Incomplete | 4 | 3 | Scrum Team | 3 | 3 | Yes | YES | Moderate | Less than 10% | No | Moderate | Over Utilised (90% and Above) | Some Information but still need further details | Not aware of any such initiative. Though the release coordination among teams was better than previous releases among teams | Well Managed | Continuous Epic Grooming | Sprint Planning | Bugs Management & Deferring | Blocking Scope change | Better & transparent commitments | Modifications on Approved Tech designs | My role involves process improvement and enablement (EM's, SM's & Other folks responsible for process streamlining) |  | YES | No |  |  | Yes | ChatGPT, CoPilot | 10% to 20% | Yes
2025-04-09 11:30 | Mujtaba Ahmad | Priya Vanteru | Dev | Falcon | 4 | Yes | BG all the trackers before loading into the sprint. This was addressed during the release. | Yes | Well Managed | 5 | 5 | 5 | 5 | Yes | 5 | 5 | Scrum Team | 5 | 5 | Yes | YES | Moderate | 10% to 20% | Yes | Moderate | Over Utilised (90% and Above) | Some Information but still need further details | Yes | Average | Continuous Epic Grooming | Sprint Planning | Bugs Management & Deferring | Risk call out during Weekly SoS | Release Planning, Strategy & Schedule (Proper Checkpoint and dates on jira tickets) | Communication gap b/w dependent teams | Less than 5% |  | YES | N/A |  |  | Yes | ChatGPT, CoPilot | 10% or below | Yes
2025-04-08 15:46 | Mohammed Fayaz | Prasad Deverakonda | QA | Tetris | 5 | No |  | Yes | Well Managed | 5 | 5 | 5 | 5 | Yes | 5 | 5 | Individual | 5 | 4 | Yes | YES | Moderate | 20% to 30% | Yes | Moderate | Balanced (80% - 90%) | Some Information but still need further details | Yes | Well Managed | Monitoring and Controlling Progress | Sprint Planning | Bugs Management & Deferring | Strict Bug SLA's | Release Planning, Strategy & Schedule (Proper Checkpoint and dates on jira tickets) | Partial or missing details on Jira Trackers Description | Less than 5% |  | YES | no |  |  | Yes | ChatGPT | 10% to 20% | Yes
2025-04-08 13:17 | Mujtaba Ahmad | Raman Soni | Dev & Scrum Master | Stark | 5 | Yes | Dependency Management | Yes | Balanced | 4 | 5 | 4 | 5 | Yes | 4 | 4 | Individual | 4 | 4 | Yes | YES | Moderate | Less than 10% | No | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Monitoring and Controlling Progress | Sprint Planning | Bugs Management & Deferring | Strict Bug SLA's | Release Planning, Strategy & Schedule (Proper Checkpoint and dates on jira tickets) | Ad-hoc Tasks & improper prioritisation | More Than 5% but less than 10% |  | YES | Processes around branch creation and management could be improved for planned patches and releases. |  |  | Yes | ChatGPT, CoPilot | 10% or below | Yes
2025-04-09 19:28 | Krishna Kishore Mothukuri | Ajitkumar kaller | Dev | Velocity | 5 | Yes | Keeping trackers updated to correct status, adding description, and regular comments for proper communication | Yes | Well Managed | 5 | 5 | 5 | 5 | Yes | 5 | 4 | Scrum Team | 5 | 5 | Yes | YES | Moderate | 10% to 20% | Yes | None | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Monitoring and Controlling Progress | Sprint Retrospective | Bugs Management & Deferring | Change in Due date and QA Sign off Date restrictions | Efficient Jira Usage (New Fields such as - Due date, QA Lead, QA Involvement, QA Signoff date) | Missing SLA's for Bugs, Trackers on Jira | Less than 5% | N/A | YES | N/A |  |  | Yes | ChatGPT, CoPilot, GitHub AI review | 10% to 20% | Yes
2025-04-11 12:27 | Mujtaba Ahmad | Ranjith Kumar M | Dev | Gryffindor | 2 | Yes | Action Item - Better Planning and Respecting due dates Resolution - Timely reminder in the DSUs, faster reviews | Yes | Balanced | 3 | 3 | 4 | 3 | Yes | 5 | 5 | Scrum Team | 4 | 4 | Yes | Moderately | Moderate | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Not at All | Not aware of any such initiative. Though the release coordination among teams was better than previous releases among teams | Average | Monitoring and Controlling Progress | Sprint Retrospective | Bugs Management & Deferring | Risk call out during Weekly SoS | Reduced over commit | Reviews | Less than 5% | NA | YES | There should be a way to track the time spent on reviews and a solution for this | NA |  | Yes | ChatGPT | 10% to 20% | Yes
2025-04-08 16:39 | Jegadeesh Santhana Krishnan | Subhan Ansari | Dev | Skywalker | 4 | Yes | spillover and better planning | Yes | Balanced |  |  |  |  | Yes |  |  | Individual |  |  | Yes | YES | Moderate | 10% to 20% | Yes |  |  | Some Information but still need further details | Yes | Average | Code Freeze Milestones and hardening phase | Sprint Closure/review | CI/CD, Testing & Continuous planning | Risk call out during Weekly SoS | Effective communication | Delayed Test Designs | Less than 5% |  | YES | stricter code freeze and package deliveries |  |  | Yes | ChatGPT, CoPilot | 10% or below | Yes
2025-04-10 17:04 | Jegadeesh Santhana Krishnan | Jegadeesh Santhana Krishnan | EM |  |  |  |  | Yes | Balanced | 4 | 5 | 5 | 5 | Yes | 4 | 5 | Scrum Team | 5 | 5 | Yes | YES | Multiple | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Code Freeze Milestones and hardening phase | Sprint Closure/review | CI/CD, Testing & Continuous planning | Blocking Scope change | None | Non Release Activities | My role involves process improvement and enablement (EM's, SM's & Other folks responsible for process streamlining) |  | YES | NA |  |  | Yes | ChatGPT | 20% to 30% | Yes
2025-04-14 11:04 | Jegadeesh Santhana Krishnan | Selvakumar Thiyagarajan | Dev | Pheonix | 5 | Yes | No action item | Yes | Balanced | 4 | 5 | 1 | 5 | Yes | 5 | 5 | Individual | 5 | 5 | Yes | YES | Moderate | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Not aware of any such initiative. Though the release coordination among teams was better than previous releases among teams | Well Managed | Continuous Epic Grooming | Sprint Closure/review | CI/CD, Testing & Continuous planning | Risk call out during Weekly SoS | Efficient Jira Usage (New Fields such as - Due date, QA Lead, QA Involvement, QA Signoff date) | Delay in commitments from dependant team | Less than 5% |  | YES | NA |  |  | Yes | ChatGPT, CoPilot | 10% to 20% | Yes
2025-04-08 14:45 | Jegadeesh Santhana Krishnan | Jegadeesh Santhana Krishnan | EM |  |  |  |  | Yes | Well Managed | 5 | 5 | 5 | 5 | Yes | 5 | 4 | Scrum Team | 5 | 5 | Yes | YES | Moderate | 20% to 30% | Yes | Moderate | Over Utilised (90% and Above) | Optimal information available | Yes | Well Managed | Continuous Epic Grooming | Sprint Closure/review | CI/CD, Testing & Continuous planning | Risk call out during Weekly SoS | Release Planning, Strategy & Schedule (Proper Checkpoint and dates on jira tickets) | Ad-hoc Tasks & improper prioritisation | My role involves process improvement and enablement (EM's, SM's & Other folks responsible for process streamlining) |  | YES | NA | Please do more automations. |  | Yes | ChatGPT, Gemini | 10% to 20% | Yes
2025-04-11 15:20 | Mujtaba Ahmad | Raman Soni | Dev & Scrum Master | Ganges | 4 | Yes | There were action items on optimising the mongoose-util issue and on the RMS pre commit build issue. Resolved by having POC and RCA respectively | Yes | Well Managed | 4 | 5 | 5 | 5 | Yes | 5 | 5 | Scrum Team | 5 | 5 | Yes | YES | Moderate | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Code Freeze Milestones and hardening phase | Sprint Planning | CI/CD, Testing & Continuous planning | Change in Due date and QA Sign off Date restrictions | Reduced over commit | Modifications on Approved Tech designs | More than 10% but Less than 20% |  | Not Efficiently | No | Sometimes the story points on the story doesn’t add up to the sub task’s story point’s summation by the automation, because of which there is a deviation in the burndown |  | Yes | CoPilot | 10% to 20% | Yes
2025-04-09 13:10 | Mujtaba Ahmad | Diksha Khatri | Dev | Titans | 5 | Yes | smooth prod deployment and dates info | Yes | Balanced | 3 | 5 | 5 | 5 | Yes | 5 | 5 | Scrum Team | 5 | 5 | Yes | YES | Moderate | 10% to 20% | Yes | Moderate | Over Utilised (90% and Above) | Optimal information available | Yes | Well Managed | Committed Epic Prioritisation | Sprint Planning | CI/CD, Testing & Continuous planning | Risk call out during Weekly SoS | Effective communication | Reviews | Less than 5% |  | YES | N/A |  |  | Yes | ChatGPT, CoPilot | 10% to 20% | Yes
2025-04-11 11:26 | Mujtaba Ahmad | Diksha Khatri | Dev | Titans | 4 | Yes | Plan things before sprint starts to improve burn down chart | Yes | Balanced | 4 | 4 | 4 | 4 | Yes | 4 | 4 | Scrum Team | 4 | 4 | Yes | YES | Multiple | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Some Information but still need further details | Yes | Well Managed | Continuous Epic Grooming | Sprint Planning | CI/CD, Testing & Continuous planning | Blocking Scope change | Efficient Jira Usage (New Fields such as - Due date, QA Lead, QA Involvement, QA Signoff date) | CS Bugs higher than the reserved Capacity | Less than 5% |  | YES | NA |  |  | Yes | ChatGPT, CoPilot | 10% to 20% | Yes
2025-04-09 20:23 | Jegadeesh Santhana Krishnan | Selvakumar Thiyagarajan | Dev & Scrum Master | Pheonix | 3 | Yes | NA | Yes | Well Managed | 4 | 5 | 5 | 5 | Yes | 5 | 5 | Individual | 5 | 5 | Yes | YES | Moderate | Less than 10% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Continuous Epic Grooming | Sprint Closure/review | Intra Team Collaboration - Dependency linking on Jira by Individual owners | Risk call out during Weekly SoS | Better Estimations & Epic Breakdown | Communication gap b/w dependent teams | My role involves process improvement and enablement (EM's, SM's & Other folks responsible for process streamlining) |  | YES | NA |  |  | Yes | ChatGPT, CoPilot | 10% to 20% | Yes
2025-04-11 11:16 | Mujtaba Ahmad | Priya Vanteru | Dev & Scrum Master | Phi | 4 | No |  | Yes | Balanced | 4 | 4 | 5 | 5 | Yes | 4 | 4 | Scrum Team | 4 | 4 | Yes | YES | Moderate | 10% to 20% | Yes | None | Balanced (80% - 90%) | Optimal information available | Not aware of any such initiative. Though the release coordination among teams was better than previous releases among teams | Average | Continuous Epic Grooming | Sprint Closure/review | Intra Team Collaboration - Dependency linking on Jira by Individual owners | Blocking Scope change | Better & transparent commitments | Communication gap b/w dependent teams | My role involves process improvement and enablement (EM's, SM's & Other folks responsible for process streamlining) | NA | YES | NA | Resolutions fields to be editable via bulk edit operation for CON and TPC projects |  | Yes | ChatGPT, CoPilot, Scrapper | 20% to 30% | Yes
2025-04-11 13:44 | Mujtaba Ahmad | Ranjith Kumar M | Dev & Scrum Master | Gryffindor | 5 | Yes | Majority of action items were regarding sprint closure. we performed the sprint closure throughly this release | Yes | Balanced | 4 | 5 | 4 | 5 | Yes | 4 | 5 | Scrum Team | 3 | 4 | Yes | YES | Moderate | 10% to 20% | Yes | Multiple | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Continuous Epic Grooming | Sprint Closure/review | Intra Team Collaboration - Dependency linking on Jira by Individual owners | Change in Due date and QA Sign off Date restrictions | Release Planning, Strategy & Schedule (Proper Checkpoint and dates on jira tickets) | Ad-hoc Tasks & improper prioritisation | My role involves process improvement and enablement (EM's, SM's & Other folks responsible for process streamlining) |  | YES | NA |  |  | Yes | ChatGPT, CoPilot, GitHub AI review | 10% to 20% | Yes
2025-04-09 21:53 | Jegadeesh Santhana Krishnan | Selvakumar Thiyagarajan | EM |  |  |  |  | Yes | Well Managed | 5 | 5 | 5 | 5 | Yes | 5 | 5 | Scrum Team | 5 | 5 | Yes | YES | Multiple | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Committed Epic Prioritisation | Sprint Planning | Intra Team Collaboration - Dependency linking on Jira by Individual owners | Change in Due date and QA Sign off Date restrictions | Effective communication | Communication gap b/w dependent teams | My role involves process improvement and enablement (EM's, SM's & Other folks responsible for process streamlining) |  | YES | NO |  |  | No | NA | Just started using AI, need time to quantify | Yes
2025-04-09 16:33 | Jegadeesh Santhana Krishnan | Ashok Kumar Dantham | Dev | Aurora | 3 | Yes | Better task planning | Yes | Balanced | 4 | 5 | 5 | 5 | Yes | 5 | 4 | Scrum Team | 4 | 3 | Yes | YES | Moderate | Less than 10% | Yes | Moderate | Balanced (80% - 90%) | Some Information but still need further details | Yes | Average | Committed Epic Prioritisation | Sprint Planning | Intra Team Collaboration - Dependency linking on Jira by Individual owners | Blocking Scope change | Effective communication | Communication gap b/w dependent teams | Less than 5% |  | YES | Better intra team dependency management and transparency |  |  | Yes | ChatGPT, CoPilot | 10% to 20% | Yes
2025-04-09 17:40 | Mujtaba Ahmad | Ranjith Kumar M | Dev | Gryffindor | 5 | Yes | Work on PR review time - Discussions are done in one call daily avoiding to and fro on the PR. | Yes | Chaotic | 2 | 3 | 3 | 2 | Yes | 4 | 4 | Scrum Team | 4 | 5 | Yes | YES | None | Less than 10% | Yes | Moderate | Over Utilised (90% and Above) | Optimal information available | Yes | Not Well | Committed Epic Prioritisation | Sprint Planning | Intra Team Collaboration - Dependency linking on Jira by Individual owners | Change in Due date and QA Sign off Date restrictions | None | Communication gap b/w dependent teams | More Than 5% but less than 10% |  | YES | NA |  |  | Yes | ChatGPT, CoPilot | 10% to 20% | Yes
2025-04-10 13:32 | Jegadeesh Santhana Krishnan | Selvakumar Thiyagarajan | Dev | Chloris | 4 | Yes | There weren't any major action items as we were occupied with automation tasks. The minor ones like timely updates of Due dates of dependent trackers etc are addressed as it's being done on a timely basis now | Yes | Balanced | 4 | 4 | 4 | 4 | Yes | 4 | 4 | Individual | 4 | 4 | Yes | YES | Moderate | Less than 10% | Yes |  |  | Optimal information available | Yes | Average | Committed Epic Prioritisation | Sprint Planning | Intra Team Collaboration - Dependency linking on Jira by Individual owners | Risk call out during Weekly SoS | Dependency management | Ad-hoc Tasks & improper prioritisation | More Than 5% but less than 10% |  | YES | - |  |  | Yes | ChatGPT, CoPilot | 10% to 20% | Yes
2025-04-10 13:35 | Jegadeesh Santhana Krishnan | Chandra Sekhar Kusupati | Dev & Scrum Master | Eirene | 4 | Yes | na | Yes | Balanced | 4 | 4 | 4 | 4 | Yes | 4 | 4 | Individual | 4 | 4 | Yes | YES | Moderate | Less than 10% | Yes | None | Balanced (80% - 90%) | Some Information but still need further details | Yes | Average | Committed Epic Prioritisation | Sprint Planning | Intra Team Collaboration - Dependency linking on Jira by Individual owners | Blocking Scope change | Efficient Jira Usage (New Fields such as - Due date, QA Lead, QA Involvement, QA Signoff date) | Communication gap b/w dependent teams | My role involves process improvement and enablement (EM's, SM's & Other folks responsible for process streamlining) |  | YES | na |  |  | Yes | ChatGPT, CoPilot | 10% to 20% | Yes
2025-04-11 19:55 | Jegadeesh Santhana Krishnan | Chandra Sekhar Kusupati | EM |  |  |  |  | Yes | Well Managed | 5 | 5 | 5 | 5 | Yes | 5 | 5 | Scrum Team | 5 | 5 | Yes | YES | Multiple | Less than 10% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Continuous Epic Grooming | Sprint Planning | Intra Team Collaboration - Dependency linking on Jira by Individual owners | Blocking Scope change | Sprint Planning Structure | Delay in commitments from dependant team | My role involves process improvement and enablement (EM's, SM's & Other folks responsible for process streamlining) |  | YES | . |  |  | Yes | ChatGPT | 30% and Above | Yes
2025-04-09 15:43 | Jegadeesh Santhana Krishnan | Selvakumar Thiyagarajan | Dev & Scrum Master | Chloris | 5 | Yes | Team was getting less of PM epics | Yes | Well Managed | 5 | 5 | 5 | 5 | Yes | 5 | 5 | Individual | 5 | 5 | Yes | YES | Multiple | Less than 10% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Continuous Epic Grooming | Sprint Planning | Intra Team Collaboration - Dependency linking on Jira by Individual owners | Blocking Scope change | Better & transparent commitments | Delay in commitments from dependant team | My role involves process improvement and enablement (EM's, SM's & Other folks responsible for process streamlining) |  | YES | NO |  |  | Yes | CoPilot | 10% to 20% | Yes
2025-04-10 17:19 | Mohammed Fayaz | Komal Varma | QA & Scrum Master | Iris | 4 | Yes | Action item-due dates are getting missed from BE team Resolved by below action-Please tag BE Dev in jira if we are not getting response through Slack threads | Yes | Balanced | 4 | 5 | 5 | 5 | Partially/Incomplete | 5 | 4 | Individual | 5 | 4 | Yes | YES | Moderate | 10% to 20% | No | Multiple | Over Utilised (90% and Above) | Some Information but still need further details | Yes | Well Managed | Continuous Epic Grooming | Sprint Planning | Intra Team Collaboration - Dependency linking on Jira by Individual owners | Blocking Scope change | Dependency management | Modifications on Approved Tech designs | More than 10% but Less than 20% |  | YES | PM should not change scope or FRD in middle of sprint. If scope change is needed then new story should be created for the same |  |  | Yes | ChatGPT, CoPilot | 10% to 20% | Yes
2025-04-08 21:49 | Mohammed Fayaz | Tharuni Sai Idupulapati | QA | Apollo | 4 | Yes | Updating of acceptance criteria and dates for the dashboards are updated accordingly | Yes | Balanced | 4 | 5 | 5 | 5 | Yes | 4 | 4 | Scrum Team | 4 | 4 | Yes | Moderately | Moderate | Less than 10% | Yes | Multiple | Over Utilised (90% and Above) | Optimal information available | Yes | Well Managed | Epic Breakdown | Sprint Planning | Intra Team Collaboration - Dependency linking on Jira by Individual owners | Change in Due date and QA Sign off Date restrictions | Effective communication | Ad-hoc Tasks & improper prioritisation | More Than 5% but less than 10% |  | YES | NA |  |  | Yes | ChatGPT, CoPilot | 10% or below | Yes
2025-04-10 13:39 | Jegadeesh Santhana Krishnan | Selvakumar Thiyagarajan | Dev | Chloris | 5 | No |  | Yes | Chaotic | 4 | 5 | 2 | 2 | Partially/Incomplete | 2 | 5 | Individual | 5 | 5 | Yes | YES | Moderate | Less than 10% | No | Moderate | Over Utilised (90% and Above) | Some Information but still need further details | Not aware and did not find any significant change in the release coordination among teams | Average | Epic Breakdown | Sprint Planning | Intra Team Collaboration - Dependency linking on Jira by Individual owners | Blocking Scope change | Efficient Jira Usage (New Fields such as - Due date, QA Lead, QA Involvement, QA Signoff date) | Delayed Response on open Queries, need multiple followups | Less than 5% |  | YES | None |  |  | Yes | CoPilot | 10% to 20% | Yes
2025-04-09 15:57 | Jegadeesh Santhana Krishnan | Selvakumar Thiyagarajan | Dev | Pheonix | 4 | Yes | how can we fix scope and not change once everything is finalized | Yes | Balanced | 3 | 3 | 3 | 3 | Yes | 3 | 3 | Individual | 3 | 3 | Yes | YES | Moderate | Less than 10% | Yes | Moderate | Balanced (80% - 90%) | Some Information but still need further details | Not aware of any such initiative. Though the release coordination among teams was better than previous releases among teams | Average | Monitoring and Controlling Progress | Sprint Planning | Intra Team Collaboration - Dependency linking on Jira by Individual owners | Blocking Scope change | Better Estimations & Epic Breakdown | Ad-hoc Tasks & improper prioritisation | More Than 5% but less than 10% |  | YES | N/A |  |  | Yes | ChatGPT, CoPilot, GitHub AI review | 20% to 30% | Yes
2025-04-10 11:23 | Jegadeesh Santhana Krishnan | Anusha Badveeti | Dev | Dynamos | 4 | No |  | Yes | Balanced | 4 | 4 | 4 | 5 | Yes | 4 | 5 | Individual | 4 | 4 | Yes | YES | Moderate | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Monitoring and Controlling Progress | Sprint Planning | Intra Team Collaboration - Dependency linking on Jira by Individual owners | Risk call out during Weekly SoS | Release Planning, Strategy & Schedule (Proper Checkpoint and dates on jira tickets) | Improper Epic Breakdown & Estimations - Missing Sprint Backlog | More than 10% but Less than 20% |  | YES | NA |  |  | Yes | CoPilot | 10% to 20% | Yes
2025-04-10 15:33 | Jegadeesh Santhana Krishnan | Ramakrishna Grandhi | Dev | Avengers | 5 | Yes | Detailed design docs and thorough review of cloudops tickets | Yes | Well Managed | 5 | 5 | 5 | 5 | Yes | 5 | 5 | Scrum Team | 5 | 5 | Yes | YES | Multiple | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Monitoring and Controlling Progress | Sprint Planning | Intra Team Collaboration - Dependency linking on Jira by Individual owners | Blocking Scope change | Better Estimations & Epic Breakdown | Communication gap b/w dependent teams | More than 10% but Less than 20% |  | YES | N/A | N/A |  | Yes | ChatGPT, CoPilot | 30% and Above | Yes
2025-04-08 12:54 | Jegadeesh Santhana Krishnan | Selvakumar Thiyagarajan | EM |  |  |  |  | Yes | Well Managed | 5 | 5 | 5 | 5 | Yes | 5 | 5 | Individual | 5 | 5 | Yes | YES | Multiple | Less than 10% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Monitoring and Controlling Progress | Sprint Retrospective | Intra Team Collaboration - Dependency linking on Jira by Individual owners | Risk call out during Weekly SoS | Work allocation with sufficient capacity reserve | Intra team collaboration | My role involves process improvement and enablement (EM's, SM's & Other folks responsible for process streamlining) |  | YES | No |  |  | Yes | ChatGPT, CoPilot, GitHub AI review | 20% to 30% | Yes
2025-04-09 15:56 | Jegadeesh Santhana Krishnan | Rajesh Subramani | Dev | Helios | 5 | Yes | Tracking/capturing of story points. | Yes | Well Managed | 3 | 4 | 5 | 5 | Yes | 5 | 5 | Individual | 5 | 4 | Yes | Moderately | Moderate | Less than 10% | Yes | None | Balanced (80% - 90%) | Some Information but still need further details | Yes | Well Managed | Monitoring and Controlling Progress | Sprint Retrospective | Intra Team Collaboration - Dependency linking on Jira by Individual owners | Risk call out during Weekly SoS | None | PR Merges | Less than 5% |  | YES | N.A |  |  | Yes | ChatGPT, CoPilot, Claude | 10% to 20% | Yes
2025-04-09 17:06 | Jegadeesh Santhana Krishnan | Ramakrishna Grandhi | Dev & Scrum Master | Sharks | 5 | Yes | na | Yes | Balanced | 3 | 5 | 5 | 5 | Yes | 5 | 5 | SME/Epic Owner/EM/QM (Pre Defined Efforts Estimates) | 5 | 5 | Yes | YES | Multiple | Less than 10% | No | Moderate | Over Utilised (90% and Above) | Optimal information available | Yes | Average | Code Freeze Milestones and hardening phase | Sprint Closure/review | Jira Automation | Risk call out during Weekly SoS | None | Improper Epic Breakdown & Estimations - Missing Sprint Backlog | My role involves process improvement and enablement (EM's, SM's & Other folks responsible for process streamlining) |  | YES | na |  |  | Yes | CoPilot | 10% or below | Yes
2025-04-09 16:35 | Jegadeesh Santhana Krishnan | Selvakumar Thiyagarajan | Dev | Pheonix | 5 | Yes | Automation tasks | Yes | Well Managed | 5 | 5 | 5 | 5 | Yes | 5 | 5 | Scrum Team | 5 | 5 | Yes | YES | Moderate | 10% to 20% | Yes | None | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Code Freeze Milestones and hardening phase | Sprint Closure/review | Jira Automation | Blocking Scope change | Better Estimations & Epic Breakdown | Delayed Response on open Queries, need multiple followups | Less than 5% |  | YES | NA | Minimize the non essential fields |  | Yes | CoPilot | 30% and Above | Yes
2025-04-11 10:55 | Mohammed Fayaz | Komal Varma | QA | Helios | 5 | Yes | All the tasks are done within the sprint | Yes | Balanced | 3 | 4 | 5 | 5 | Yes | 4 | 4 | Individual | 4 | 4 | Yes | YES | Multiple | More than 30% | Yes | Moderate | Balanced (80% - 90%) | Some Information but still need further details | Yes | Average | Committed Epic Prioritisation | Sprint Closure/review | Jira Automation | Blocking Scope change | None | Delay in commitments from dependant team | More than 20% | No | YES | No | No |  | Yes | ChatGPT | 20% to 30% | Yes
2025-04-11 13:26 | Mujtaba Ahmad | Raman Soni | Dev | Ganges | 5 | Yes | RMS Jenkins Build Issue RCA | Yes | Well Managed | 5 | 5 | 5 | 5 | Yes | 5 | 5 | Scrum Team | 4 | 4 | No | YES | Moderate | Less than 10% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Release Kick Off | Sprint Closure/review | Jira Automation | Blocking Scope change | Release Planning, Strategy & Schedule (Proper Checkpoint and dates on jira tickets) | Communication gap b/w dependent teams | More Than 5% but less than 10% |  | YES | KT and doc on monolith branching strategy |  |  | Yes | ChatGPT, CoPilot | 10% to 20% | Yes
2025-04-15 01:43 | Jegadeesh Santhana Krishnan | Jegadeesh Santhana Krishnan | EM |  |  |  |  | Yes | Well Managed | 4 | 5 | 5 | 5 | Yes | 5 | 4 | Scrum Team | 4 | 4 | Yes | YES | Multiple | Less than 10% | Yes | None | Balanced (80% - 90%) | Optimal information available | Yes | Average | Continuous Epic Grooming | Sprint Planning | Jira Automation | Change in Due date and QA Sign off Date restrictions | Better Estimations & Epic Breakdown | Delay in commitments from dependant team | My role involves process improvement and enablement (EM's, SM's & Other folks responsible for process streamlining) | nothing specific | YES | we need to reduce staging/production deployment duration |  |  | Yes | ChatGPT | 10% or below | Yes
2025-04-11 13:34 | Mohammed Fayaz | Komal Varma | QA | Helios | 5 | Yes | log tracker before the sprint starts | Yes | Well Managed | 5 | 5 | 5 | 5 | Yes | 5 | 5 | SME/Epic Owner/EM/QM (Pre Defined Efforts Estimates) | 5 | 5 | Yes | YES | Multiple | 20% to 30% | No | Moderate | Over Utilised (90% and Above) | Optimal information available | Yes | Well Managed | Epic Breakdown | Sprint Planning | Jira Automation | Change in Due date and QA Sign off Date restrictions | Effective communication | Non Release Activities | Less than 5% |  | YES | no |  |  | Yes | ChatGPT | 10% or below | No
2025-04-14 11:53 | Mohammed Fayaz | Anusha Badveeti | Dev | Dynamos | 4 | No |  | Yes | Well Managed | 4 | 4 | 4 |  | Partially/Incomplete | 4 | 4 | SME/Epic Owner/EM/QM (Pre Defined Efforts Estimates) | 4 |  | Yes | Moderately | Moderate | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Epic Breakdown | Sprint Planning | Jira Automation | Change in Due date and QA Sign off Date restrictions | Sprint Planning Structure | PR Merges | More Than 5% but less than 10% |  | YES | NA |  |  | No | CoPilot | Just started using AI, need time to quantify | No
2025-04-08 13:32 | Mujtaba Ahmad | Priya Vanteru | Dev | Phi | 4 | No |  | Yes | Balanced | 4 | 4 | 4 | 5 | Yes | 3 | 4 | Individual | 4 | 5 | Yes | Moderately | None | 20% to 30% | No | Multiple | Over Utilised (90% and Above) | Some Information but still need further details | Yes | Average | Epic Breakdown | Sprint Planning | Jira Automation | Blocking Scope change | Sprint Planning Structure | Ad-hoc Tasks & improper prioritisation | Less than 5% |  | YES | NA | Jira Automation |  | Yes | ChatGPT, Gemini, Scrapper | Just started using AI, need time to quantify | No
2025-04-08 16:41 | Jegadeesh Santhana Krishnan | Anusha Badveeti | Dev | Dynamos | 4 | No |  | Yes | Balanced | 4 | 4 | 4 | 4 | Yes | 4 | 4 | Individual | 4 | 4 | Yes | Moderately | Moderate | 10% to 20% | Yes | None | Balanced (80% - 90%) | Some Information but still need further details | Not aware of any such initiative. Though the release coordination among teams was better than previous releases among teams | Average | Monitoring and Controlling Progress | Sprint Planning | Jira Automation | Blocking Scope change | Work allocation with sufficient capacity reserve | Reviews | More Than 5% but less than 10% |  | YES | -NA- |  |  | Yes | ChatGPT, Gemini | 10% to 20% | Yes
2025-04-08 15:02 | Jegadeesh Santhana Krishnan | Ankur Sachdeva | Dev & Scrum Master | Chipmuks | 5 | Yes | Prioritising tasks | Yes | Well Managed | 5 | 5 | 5 | 5 | Yes | 4 | 5 | Scrum Team | 5 | 5 | Yes | YES | Multiple | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Some Information but still need further details | Yes | Well Managed | Committed Epic Prioritisation | Sprint Closure/review | Jira Details - Epic breakdown, DoD, Exit criteria, CS Bugs | Change in Due date and QA Sign off Date restrictions | Effective communication | Reviews | More Than 5% but less than 10% |  | YES | Nope |  |  | Yes | ChatGPT, CoPilot | 10% to 20% | Yes
2025-04-08 13:10 | Krishna Kishore Mothukuri | Krishna Kishore Mothukuri | EM |  |  |  |  | Yes | Balanced | 4 | 5 | 5 | 5 | Partially/Incomplete | 5 | 5 | Scrum Team | 5 | 5 | Yes | YES | Multiple | Less than 10% | Yes | None | Balanced (80% - 90%) | Some Information but still need further details | Yes | Well Managed | Continuous Epic Grooming | Sprint Closure/review | Jira Details - Epic breakdown, DoD, Exit criteria, CS Bugs | Change in Due date and QA Sign off Date restrictions | Release Planning, Strategy & Schedule (Proper Checkpoint and dates on jira tickets) | Delayed Response on open Queries, need multiple followups | My role involves process improvement and enablement (EM's, SM's & Other folks responsible for process streamlining) |  | YES | NO | JIRA automations are not very clear. Closing the tracker is slightly tedious for the team now. |  | Yes | ChatGPT | 10% to 20% | Yes
2025-04-14 11:58 | Krishna Kishore Mothukuri | Ajitkumar kaller | Dev | Velocity | 4 | Yes | Interaction with PM: Started including PM in the team demo meeting | Yes | Well Managed | 5 | 5 | 5 | 5 | Yes | 5 | 4 | Scrum Team | 5 | 5 | Yes | YES | Moderate | Less than 10% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Continuous Epic Grooming | Sprint Closure/review | Jira Details - Epic breakdown, DoD, Exit criteria, CS Bugs | Change in Due date and QA Sign off Date restrictions | Release Planning, Strategy & Schedule (Proper Checkpoint and dates on jira tickets) | Non Release Activities | Less than 5% |  | YES | NA | N A |  | Yes | ChatGPT, CoPilot | 30% and Above | Yes
2025-04-11 12:19 | Mohammed Fayaz | SathishKumar D | QA | Optimus | 5 | Yes | yes actions items as per task were resolved during the release | Yes | Balanced | 4 | 4 | 5 | 4 | Yes | 5 | 5 | Scrum Team | 5 | 5 | No | YES | Moderate | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Some Information but still need further details | Yes | Average | Epic Breakdown | Sprint Closure/review | Jira Details - Epic breakdown, DoD, Exit criteria, CS Bugs | Blocking Scope change | Reduced over commit | Reviews | More than 10% but Less than 20% | -- | YES | its going good |  |  | Yes | ChatGPT | 20% to 30% | Yes
2025-04-09 23:20 | Jegadeesh Santhana Krishnan | Selvakumar Thiyagarajan | Dev | Iris | 4 | No |  | Yes | Balanced | 4 | 4 | 4 | 4 | Yes | 4 | 4 | Individual | 4 | 4 | Yes | YES | Moderate | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Some Information but still need further details | Yes | Average | Monitoring and Controlling Progress | Sprint Closure/review | Jira Details - Epic breakdown, DoD, Exit criteria, CS Bugs | Blocking Scope change | Better Estimations & Epic Breakdown | Partial or missing details on Jira Trackers Description | Less than 5% |  | YES | Nil |  |  | Yes | ChatGPT, CoPilot, GitHub AI review | 30% and Above | Yes
2025-04-09 16:21 | Jegadeesh Santhana Krishnan | Chandra Sekhar Kusupati | Dev | Helios | 2 | Yes | Na | Yes | Well Managed | 4 | 5 | 5 | 5 | Yes | 5 | 5 | Individual | 5 | 5 | Yes | YES | Moderate | Less than 10% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Release Kick Off | Sprint Closure/review | Jira Details - Epic breakdown, DoD, Exit criteria, CS Bugs | Strict Bug SLA's | None | Missing SLA's for Bugs, Trackers on Jira | Less than 5% |  | YES | Na | Na |  | Yes | ChatGPT, Gemini | 10% to 20% | Yes
2025-04-10 15:45 | Mohammed Fayaz | Varun Batra | QA | Sharks | 5 | Yes | Move subtasks to correct state before moving the tracker to QA Ready. | Yes | Well Managed | 5 |  |  |  | Yes |  |  | Individual |  |  | Yes | YES | Moderate | 10% to 20% | Yes | Moderate |  | Optimal information available | Yes |  | Committed Epic Prioritisation | Sprint DSU's | Jira Details - Epic breakdown, DoD, Exit criteria, CS Bugs | Blocking Scope change | Effective communication | Non Release Activities | More Than 5% but less than 10% |  | YES | Suggestion - We should mandatory to PM to join the scrum meetings and avoid such meetings in a daily time which consume lots of time to check the status of task with managers and other team member, Scrum should be implemented properly and any risk callout should be discussed in daily scrum meeting. | NA |  | Yes | ChatGPT | 10% to 20% | Yes
2025-04-11 17:22 | Mohammed Fayaz | Tharuni Sai Idupulapati | QA | Individual Capacity, Not Associated with any particular team | 3 | No |  | Yes | Balanced | 4 | 4 | 4 | 4 | Partially/Incomplete | 3 | 3 | Individual | 3 | 3 | Yes | Moderately | Moderate | More than 30% | Yes | Moderate | Balanced (80% - 90%) | Some Information but still need further details | Yes | Average | Continuous Epic Grooming | Sprint DSU's | Jira Details - Epic breakdown, DoD, Exit criteria, CS Bugs | Change in Due date and QA Sign off Date restrictions | Work allocation with sufficient capacity reserve | Improper Epic Breakdown & Estimations - Missing Sprint Backlog | More Than 5% but less than 10% | NA | Not Efficiently | NA | NA |  | Yes | ChatGPT, CoPilot | 10% to 20% | Yes
2025-04-09 15:56 | Jegadeesh Santhana Krishnan | Ashok Kumar Dantham | Dev | Iris | 5 | No |  | Yes | Balanced | 4 | 5 | 5 | 5 | Yes | 5 | 5 | Individual | 4 | 4 | Yes | YES | None | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Some Information but still need further details | Not aware of any such initiative. Though the release coordination among teams was better than previous releases among teams | Well Managed | Epic Breakdown | Sprint DSU's | Jira Details - Epic breakdown, DoD, Exit criteria, CS Bugs | Blocking Scope change | Better & transparent commitments | Delay in commitments from dependant team | More Than 5% but less than 10% | No | YES | No |  |  | Yes | ChatGPT, CoPilot, GitHub AI review | 10% to 20% | Yes
2025-04-10 17:18 | Jegadeesh Santhana Krishnan | Subhan Ansari | Dev | Skywalker | 5 | No |  | Yes | Balanced | 4 | 4 | 4 | 4 | Yes | 4 | 4 | Scrum Team | 4 | 4 | Yes | Moderately | Moderate | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Some Information but still need further details | Not aware of any such initiative. Though the release coordination among teams was better than previous releases among teams | Well Managed | Epic Breakdown | Sprint DSU's | Jira Details - Epic breakdown, DoD, Exit criteria, CS Bugs | Change in Due date and QA Sign off Date restrictions | Effective communication | PR Merges | More than 10% but Less than 20% |  | YES | Ensure thorough sprint planning, break down epics effectively, and maintain clear and detailed tracker descriptions. |  |  | Yes | CoPilot | 10% to 20% | Yes
2025-04-11 14:45 | Mohammed Fayaz | Prasad Deverakonda | QA & Scrum Master | Iota | 4 | No |  | Yes | Well Managed | 5 | 5 | 5 | 5 | Partially/Incomplete | 5 | 4 | Scrum Team | 4 | 4 | Yes | Moderately | Moderate | Less than 10% | Yes | None | Over Utilised (90% and Above) | Optimal information available | Yes | Well Managed | Epic Breakdown | Sprint DSU's | Jira Details - Epic breakdown, DoD, Exit criteria, CS Bugs | Blocking Scope change | Efficient Jira Usage (New Fields such as - Due date, QA Lead, QA Involvement, QA Signoff date) | Improper Epic Breakdown & Estimations - Missing Sprint Backlog | Less than 5% |  | Not Efficiently | NA | we need to enhance jira status work flow |  | Yes | ChatGPT | 30% and Above | Yes
2025-04-08 15:14 | Mohammed Fayaz | Mohammed Fayaz | EM |  |  |  |  | Yes | Balanced | 4 | 5 | 5 | 5 | Partially/Incomplete | 4 | 4 | Scrum Team | 4 | 4 | Yes | YES | Moderate | 10% to 20% | Yes | Moderate | Over Utilised (90% and Above) | Some Information but still need further details | Yes | Well Managed | Code Freeze Milestones and hardening phase | Sprint Planning | Jira Details - Epic breakdown, DoD, Exit criteria, CS Bugs | Risk call out during Weekly SoS | Sprint Planning Structure | PR Merges | My role involves process improvement and enablement (EM's, SM's & Other folks responsible for process streamlining) |  | YES | Patch, Hotfix PR merges to main release, Strict bug SLAs, better cloudOps dependencies tracking well advance | NA |  | Yes | ChatGPT, Gemini | 20% to 30% | Yes
2025-04-11 11:55 | Mohammed Fayaz | Varun Batra | QA | Chipmuks | 4 | Yes | NA | Yes | Balanced | 4 | 4 | 4 | 4 | Yes | 4 | 4 | Individual | 4 | 4 | Yes | YES | Moderate | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Code Freeze Milestones and hardening phase | Sprint Planning | Jira Details - Epic breakdown, DoD, Exit criteria, CS Bugs | Change in Due date and QA Sign off Date restrictions | Better Estimations & Epic Breakdown | Modifications on Approved Tech designs | More Than 5% but less than 10% | NA | YES | NA | NA |  | Yes | ChatGPT, CoPilot | 10% or below | Yes
2025-04-09 10:55 | Jegadeesh Santhana Krishnan | Ankur Sachdeva | Dev | Chipmuks | 4 | No |  | Yes | Balanced | 4 | 4 | 4 | 5 | Yes | 5 | 4 | Scrum Team | 4 | 4 | Yes | YES | Multiple | 10% to 20% | Yes | Multiple | Balanced (80% - 90%) | Some Information but still need further details | Yes | Well Managed | Committed Epic Prioritisation | Sprint Planning | Jira Details - Epic breakdown, DoD, Exit criteria, CS Bugs | Blocking Scope change | Better & transparent commitments | Ad-hoc Tasks & improper prioritisation | Less than 5% |  | YES | - |  |  | Yes | ChatGPT, CoPilot, Claude | 10% to 20% | Yes
2025-04-11 10:38 | Mohammed Fayaz | Anusha Jharupula | QA | Indus | 4 | Yes | on bandwidth allocation to debug production issues | Yes | Balanced | 4 | 4 | 4 | 4 | Yes | 4 | 4 | Scrum Team | 4 | 4 | Yes | YES | Multiple | 10% to 20% | Yes | Multiple | Balanced (80% - 90%) | Some Information but still need further details | Yes | Well Managed | Committed Epic Prioritisation | Sprint Planning | Jira Details - Epic breakdown, DoD, Exit criteria, CS Bugs | Risk call out during Weekly SoS | Release Planning, Strategy & Schedule (Proper Checkpoint and dates on jira tickets) | Ad-hoc Tasks & improper prioritisation | More Than 5% but less than 10% | NA | YES | NA | NA |  | Yes | ChatGPT | 10% to 20% | Yes
2025-04-08 18:20 | Mujtaba Ahmad | Raman Soni | Dev | Apollo | 4 | Yes | The JIRA trackers were not actively updated by team which improved in this release | Yes | Balanced | 4 | 4 | 4 | 5 | Yes | 4 | 3 | Scrum Team | 4 | 4 | Yes | Moderately | None | 10% to 20% | Yes | Moderate | Over Utilised (90% and Above) | Some Information but still need further details | Yes | Average | Continuous Epic Grooming | Sprint Planning | Jira Details - Epic breakdown, DoD, Exit criteria, CS Bugs | Change in Due date and QA Sign off Date restrictions | Better Estimations & Epic Breakdown | Ad-hoc Tasks & improper prioritisation | More Than 5% but less than 10% |  | Not Efficiently | There should be continuous monitoring of deviation from release deliveries and planned scope either dashboard or reports | work log not used properly , alerting on delays or too many date changes can be escalated and improved. |  | Yes | ChatGPT, CoPilot, Gemini | 10% to 20% | Yes
2025-04-10 13:34 | Jegadeesh Santhana Krishnan | Chandra Sekhar Kusupati | Dev | Eirene | 3 | Yes | Track new design bugs through design system story defects rather than io project bugs, after the retro, tracking was done through design trackers only | Yes | Well Managed | 5 | 5 | 5 | 5 | Yes | 4 | 4 | Scrum Team | 3 | 3 | Yes | YES | Multiple | 10% to 20% | Yes | None | Balanced (80% - 90%) | Some Information but still need further details | Yes | Well Managed | Continuous Epic Grooming | Sprint Planning | Jira Details - Epic breakdown, DoD, Exit criteria, CS Bugs | Blocking Scope change | Release Planning, Strategy & Schedule (Proper Checkpoint and dates on jira tickets) | Delay in commitments from dependant team | Less than 5% |  | YES | Epic details should either be in jira or docs entirely, having two different sources of truth causes confusion. |  |  | Yes | CoPilot | 10% or below | Yes
2025-04-08 15:01 | Mohammed Fayaz | Krishnamoorthy G | QA & Scrum Master | Dynamos | 5 | Yes | resolving environment issues to have a smooth release , we were facing issues with platform3 environement , now we are working on to check the infra and other details to have this sorted . working on local setup to eliminate integration issues. | Yes | Well Managed | 5 | 5 | 5 | 5 | Yes | 5 | 5 | Individual | 5 | 5 | Yes | YES | Moderate | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Some Information but still need further details | Yes | Well Managed | Continuous Epic Grooming | Sprint Planning | Jira Details - Epic breakdown, DoD, Exit criteria, CS Bugs | Blocking Scope change | Release Planning, Strategy & Schedule (Proper Checkpoint and dates on jira tickets) | Modifications on Approved Tech designs | My role involves process improvement and enablement (EM's, SM's & Other folks responsible for process streamlining) |  | YES | having continuous epic grooming and idnetifying and prioritising tasks will help . currently we started doing it in the scrum team . | anything which can be automated to reduce human effort . |  | Yes | ChatGPT, GitHub AI review, Langchain | 10% to 20% | Yes
2025-04-09 17:48 | Mohammed Fayaz | Anusha Jharupula | QA & Scrum Master | Falcon | 4 | Yes | correct sign-off date should be populated in trackers | Yes | Well Managed | 3 | 4 | 4 | 4 | Yes | 4 | 4 | Scrum Team | 4 | 5 | Yes | YES | Moderate | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Some Information but still need further details | Yes | Average | Continuous Epic Grooming | Sprint Planning | Jira Details - Epic breakdown, DoD, Exit criteria, CS Bugs | Risk call out during Weekly SoS | Better Estimations & Epic Breakdown | Communication gap b/w dependent teams | Less than 5% |  | YES | NA |  |  | Yes | ChatGPT, CoPilot | Just started using AI, need time to quantify | Yes
2025-04-09 16:58 | Krishna Kishore Mothukuri | Ajitkumar kaller | Dev & Scrum Master | Velocity | 5 | Yes | We conducted a meet on best activities for scrum and discussed about the things we should follow to make sure everyone in the team are on same page. | Yes | Balanced | 5 | 5 | 5 | 5 | Yes | 5 | 5 | Scrum Team | 4 | 5 | Yes | YES | Multiple | 10% to 20% | Yes | Moderate | Over Utilised (90% and Above) | Optimal information available | Yes | Well Managed | Continuous Epic Grooming | Sprint Planning | Jira Details - Epic breakdown, DoD, Exit criteria, CS Bugs | Risk call out during Weekly SoS | Efficient Jira Usage (New Fields such as - Due date, QA Lead, QA Involvement, QA Signoff date) | Improper Epic Breakdown & Estimations - Missing Sprint Backlog | My role involves process improvement and enablement (EM's, SM's & Other folks responsible for process streamlining) |  | YES | No |  |  | Yes | ChatGPT, CoPilot, Gemini | 30% and Above | Yes
2025-04-11 13:17 | Mohammed Fayaz | Komal Varma | QA | Hercules and Velocity | 4 | Yes | 1. Delay's and challenges discussing with Team and improving the plan considering the challenges. 2. TechDesign and TestDesign collective team reviews in a meeting | Yes | Balanced | 4 | 4 | 4 | 4 | No | 4 | 4 | Scrum Team | 4 | 4 | Yes | YES | Moderate | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Some Information but still need further details | Yes | Well Managed | Continuous Epic Grooming | Sprint Planning | Jira Details - Epic breakdown, DoD, Exit criteria, CS Bugs | Blocking Scope change | Work allocation with sufficient capacity reserve | Improper Epic Breakdown & Estimations - Missing Sprint Backlog | More Than 5% but less than 10% |  | YES | Road map and backlog discussion for next 3-4 releases |  |  | Yes | ChatGPT | 30% and Above | Yes
2025-04-11 14:45 | Mohammed Fayaz | Tharuni Sai Idupulapati | QA | Ganges | 5 | No |  | Yes | Well Managed | 5 | 5 | 5 | 5 | Yes | 5 | 5 | Scrum Team | 5 | 5 | Yes | YES | Moderate | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Continuous Epic Grooming | Sprint Planning | Jira Details - Epic breakdown, DoD, Exit criteria, CS Bugs | Blocking Scope change | Effective communication | Communication gap b/w dependent teams | Less than 5% |  | YES | nthg |  |  | Yes | ChatGPT, CoPilot, Gemini | 10% to 20% | Yes
2025-04-11 23:03 | Jegadeesh Santhana Krishnan | Subhan Ansari | Dev & Scrum Master | Skywalker | 2 | No |  | Yes | Balanced | 3 | 4 | 3 | 4 | Yes | 4 | 3 | Scrum Team | 4 | 3 | Yes | Moderately | Moderate | 10% to 20% | Yes | None | Balanced (80% - 90%) | Some Information but still need further details | Yes | Well Managed | Epic Breakdown | Sprint Planning | Jira Details - Epic breakdown, DoD, Exit criteria, CS Bugs | Risk call out during Weekly SoS | Sprint Planning Structure | CS Bugs higher than the reserved Capacity | More than 10% but Less than 20% |  | YES | No |  |  | Yes | ChatGPT, CoPilot | 10% to 20% | Yes
2025-04-08 12:53 | Mohammed Fayaz | Varun Batra | QA | Tranformers | 5 | Yes | Feature scope finalisation and it has been considered | Yes | Balanced | 5 | 5 | 5 | 5 | Yes | 5 | 5 | Scrum Team | 4 | 4 | Yes | YES | Moderate | Less than 10% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Epic Breakdown | Sprint Planning | Jira Details - Epic breakdown, DoD, Exit criteria, CS Bugs | Blocking Scope change | Better & transparent commitments | Modifications on Approved Tech designs | Less than 5% | - | YES | - | - |  | Yes | ChatGPT | 10% or below | Yes
2025-04-08 15:22 | Mohammed Fayaz | Tharuni Sai Idupulapati | QA | Zeta | 5 | Yes | connected dev to discuss on it related to 1 bug | Yes | Balanced | 5 | 5 |  | 5 | Yes | 4 | 5 | Individual | 5 | 5 | Yes | YES | Multiple | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Epic Breakdown | Sprint Planning | Jira Details - Epic breakdown, DoD, Exit criteria, CS Bugs | Change in Due date and QA Sign off Date restrictions | Better Estimations & Epic Breakdown | Ad-hoc Tasks & improper prioritisation | More Than 5% but less than 10% |  | YES | NA |  |  | Yes | ChatGPT | 10% to 20% | Yes
2025-04-11 14:54 | Mohammed Fayaz | Tharuni Sai Idupulapati | QA | Ganges | 1 | Yes | Documentation for devops trackers | Yes | Balanced | 4 | 4 | 4 | 4 | Partially/Incomplete | 4 | 4 | Scrum Team | 4 | 4 | Yes | YES | Multiple | Less than 10% | Yes | Moderate | Balanced (80% - 90%) | Some Information but still need further details | Yes | Average | Epic Breakdown | Sprint Planning | Jira Details - Epic breakdown, DoD, Exit criteria, CS Bugs | Change in Due date and QA Sign off Date restrictions | Better & transparent commitments | Improper Epic Breakdown & Estimations - Missing Sprint Backlog | More Than 5% but less than 10% |  | YES | No | No |  | Yes | ChatGPT, CoPilot, AI Test Designs Tool | 20% to 30% | Yes
2025-04-08 14:00 | Mujtaba Ahmad | Priya Vanteru | Dev | Phi | 4 | Yes | 1. Creating utility for FDR Generation Utility using Generic files. 2. Using Generic FDR Utility to generte Generic files. 3. Using FDR Validation Utility for validation of FDRs. | Yes | Balanced | 4 | 5 | 5 | 5 | Yes | 5 | 4 | Scrum Team | 5 | 4 | Yes | YES | Moderate | Less than 10% | Yes | Moderate | Balanced (80% - 90%) | Some Information but still need further details | Not aware and did not find any significant change in the release coordination among teams | Well Managed | Epic Breakdown | Sprint Planning | Jira Details - Epic breakdown, DoD, Exit criteria, CS Bugs | Change in Due date and QA Sign off Date restrictions | Release Planning, Strategy & Schedule (Proper Checkpoint and dates on jira tickets) | Reviews | Less than 5% |  | YES | NA |  |  | Yes | ChatGPT | Just started using AI, need time to quantify | Yes
2025-04-09 23:22 | Jegadeesh Santhana Krishnan | Ramakrishna Grandhi | Dev | Sharks | 5 | Yes | We decided to add more details on jira and communicate about the timelines | Yes | Well Managed | 5 | 5 | 5 | 5 | Yes | 5 | 5 | Scrum Team | 5 | 5 | Yes | YES | Moderate | 10% to 20% | Yes | Moderate | Over Utilised (90% and Above) | Optimal information available | Yes | Well Managed | Epic Breakdown | Sprint Planning | Jira Details - Epic breakdown, DoD, Exit criteria, CS Bugs | Change in Due date and QA Sign off Date restrictions | Release Planning, Strategy & Schedule (Proper Checkpoint and dates on jira tickets) | Delayed Response on open Queries, need multiple followups | More than 10% but Less than 20% |  | YES | The release process is well managed. |  |  | Yes | ChatGPT, CoPilot, Perplexity, Gemini | 10% to 20% | Yes
2025-04-09 15:12 | Jegadeesh Santhana Krishnan | Anusha Badveeti | Dev | Tranformers | 5 | Yes | - | Yes | Balanced | 5 | 5 | 5 | 5 | Yes | 5 | 5 | Individual | 5 | 5 | Yes | YES | Moderate | 10% to 20% | Yes | Moderate | Over Utilised (90% and Above) | Optimal information available | Yes | Average | Epic Breakdown | Sprint Planning | Jira Details - Epic breakdown, DoD, Exit criteria, CS Bugs | Blocking Scope change | Better & transparent commitments | Ad-hoc Tasks & improper prioritisation | More Than 5% but less than 10% |  | YES | - |  |  | Yes | ChatGPT, CoPilot | 10% to 20% | Yes
2025-04-09 15:56 | Jegadeesh Santhana Krishnan | Ashok Kumar Dantham | Dev | Aurora | 4 | No |  | Yes | Chaotic | 3 | 2 | 5 | 5 | Yes | 5 | 4 | Individual | 4 | 4 | Yes | YES | Multiple | 20% to 30% | Yes | None | Balanced (80% - 90%) | Some Information but still need further details | Yes | Not Well | Continuous Epic Grooming | Sprint Retrospective | Jira Details - Epic breakdown, DoD, Exit criteria, CS Bugs | Blocking Scope change | Reduced over commit | Partial or missing details on Jira Trackers Description | Less than 5% |  | YES | Communication between teams has to be improved |  |  | Yes | ChatGPT, CoPilot | 10% to 20% | Yes
2025-04-08 14:02 | Krishna Kishore Mothukuri | Ajitkumar kaller | Dev | Velocity | 5 | No |  | Yes | Balanced | 4 | 4 | 4 | 4 | Yes | 4 | 4 | Scrum Team | 4 | 4 | Yes | Moderately | Moderate | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Some Information but still need further details | Yes | Average | Continuous Epic Grooming | Sprint Retrospective | Jira Details - Epic breakdown, DoD, Exit criteria, CS Bugs | Change in Due date and QA Sign off Date restrictions | Effective communication | Ad-hoc Tasks & improper prioritisation | More than 10% but Less than 20% | NO | YES | NO | NO |  | Yes | ChatGPT, CoPilot, Langchain | 10% to 20% | Yes
2025-04-09 15:40 | Jegadeesh Santhana Krishnan | Selvakumar Thiyagarajan | Dev | Aurora | 4 | Yes | actions taken on time eg for the node upgrade | Yes | Balanced | 4 | 4 | 4 | 4 | No | 4 | 4 | Individual | 4 | 4 | No | YES | Moderate | 20% to 30% | Yes | Moderate | Balanced (80% - 90%) | Some Information but still need further details | Yes | Average | Committed Epic Prioritisation | Sprint Closure/review | KT and recording repository | Change in Due date and QA Sign off Date restrictions | Effective communication | Delay in commitments from dependant team | More Than 5% but less than 10% |  | YES | no |  |  | Yes | ChatGPT, CoPilot, Gemini, GitHub AI review, Claude | 30% and Above | Yes
2025-04-14 13:40 | Jegadeesh Santhana Krishnan | Selvakumar Thiyagarajan | Dev | Chloris | 4 | No |  | Yes | Balanced | 4 | 4 | 4 | 4 | Yes | 4 | 4 | Individual | 4 | 4 | Yes | YES | Moderate | Less than 10% | Yes | Moderate | Balanced (80% - 90%) | Some Information but still need further details | Not aware of any such initiative. Though the release coordination among teams was better than previous releases among teams | Average | Continuous Epic Grooming | Sprint Closure/review | KT and recording repository | Change in Due date and QA Sign off Date restrictions | Sprint Planning Structure | Ad-hoc Tasks & improper prioritisation | Less than 5% |  | YES | NA |  |  | Yes | CoPilot | 10% or below | Yes
2025-04-08 16:02 | Jegadeesh Santhana Krishnan | Chandra Sekhar Kusupati | Dev | Hercules | 4 | No |  | Yes | Well Managed | 5 | 5 | 5 | 5 | Yes | 5 | 5 | Scrum Team | 5 | 5 | Yes | YES | Moderate | 10% to 20% | Yes | Moderate | Over Utilised (90% and Above) | Optimal information available | Yes | Well Managed | Epic Breakdown | Sprint Closure/review | KT and recording repository | Blocking Scope change | Better & transparent commitments | Ad-hoc Tasks & improper prioritisation | Less than 5% |  | YES | no |  |  | Yes | ChatGPT, CoPilot, GitHub AI review | 10% to 20% | Yes
2025-04-11 14:11 | Mohammed Fayaz | Prasad Deverakonda | QA | Iota | 5 | Yes | We made improvements on planning front | Yes | Well Managed | 5 | 5 | 5 | 5 | Yes | 5 | 5 | Individual | 5 | 5 | Yes | YES | Moderate | Less than 10% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Monitoring and Controlling Progress | Sprint Closure/review | KT and recording repository | Blocking Scope change | Better & transparent commitments | Reviews | Less than 5% | . | YES | . | . |  | Yes | ChatGPT | 20% to 30% | Yes
2025-04-08 13:31 | Jegadeesh Santhana Krishnan | Ankur Sachdeva | Dev | Echo | 4 | No |  | Yes | Chaotic | 3 | 5 | 4 | 3 | Yes | 2 | 4 | Scrum Team | 4 | 4 | Yes | Moderately | Moderate | Less than 10% | Yes | None | Over Utilised (90% and Above) | Some Information but still need further details | Not aware and did not find any significant change in the release coordination among teams | Well Managed | Monitoring and Controlling Progress | Sprint Closure/review | KT and recording repository | Risk call out during Weekly SoS | None | Delayed Response on open Queries, need multiple followups | More Than 5% but less than 10% |  | YES | no |  |  | Yes | ChatGPT, CoPilot | 10% to 20% | Yes
2025-04-08 16:03 | Jegadeesh Santhana Krishnan | Ankur Sachdeva | Dev | Dexter | 5 | No |  | Yes | Balanced | 5 | 5 | 5 | 5 | Yes | 5 | 5 | Individual | 5 | 5 | Yes | YES | Multiple | Less than 10% | Yes | Moderate | Balanced (80% - 90%) | Some Information but still need further details | Yes | Well Managed | Committed Epic Prioritisation | Sprint Planning | KT and recording repository | Change in Due date and QA Sign off Date restrictions | Release Planning, Strategy & Schedule (Proper Checkpoint and dates on jira tickets) | Ad-hoc Tasks & improper prioritisation | Less than 5% |  | YES | - |  |  | Yes | ChatGPT, CoPilot | Just started using AI, need time to quantify | Yes
2025-04-08 13:35 | Mujtaba Ahmad | Priya Vanteru | Dev | Phi | 5 | Yes | it's about new sprint connector. | Yes | Well Managed | 5 | 5 | 5 | 5 | Yes |  | 5 | SME/Epic Owner/EM/QM (Pre Defined Efforts Estimates) | 5 | 5 | Yes | YES | Moderate | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Average | Continuous Epic Grooming | Sprint Planning | KT and recording repository | Strict Bug SLA's | Release Planning, Strategy & Schedule (Proper Checkpoint and dates on jira tickets) | Ad-hoc Tasks & improper prioritisation | More Than 5% but less than 10% |  | YES | Nothing |  |  | Yes | ChatGPT | 10% to 20% | Yes
2025-04-09 18:37 | Mohammed Fayaz | Anusha Jharupula | QA | Avengers | 3 | No |  | Yes | Balanced | 3 | 4 | 4 | 4 | Partially/Incomplete | 4 | 4 | Scrum Team | 4 | 3 | Yes | YES | Moderate | Less than 10% | Yes | Moderate | Balanced (80% - 90%) | Some Information but still need further details | Yes | Average | Epic Breakdown | Sprint Planning | KT and recording repository | Risk call out during Weekly SoS | Effective communication | Ad-hoc Tasks & improper prioritisation | More than 10% but Less than 20% |  | YES | no |  |  | Yes | ChatGPT | 10% or below | Yes
2025-04-10 13:48 | Mujtaba Ahmad | Diksha Khatri | Architect/Individual Contributors |  |  |  |  | Yes | Balanced | 5 | 5 | 5 | 5 | Partially/Incomplete | 4 | 5 | Scrum Team | 5 | 5 | Yes | YES | Moderate | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Some Information but still need further details | Yes | Well Managed | Epic Breakdown | Sprint Planning | KT and recording repository | Blocking Scope change | Release Planning, Strategy & Schedule (Proper Checkpoint and dates on jira tickets) | Improper Epic Breakdown & Estimations - Missing Sprint Backlog | Less than 5% | NA | YES | Enough time should be given to the team to understand the epic, and they should receive a knowledge transfer (KT) of the codebase if they are new to it. | NA |  | Yes | ChatGPT | 10% or below | Yes
2025-04-14 12:04 | Jegadeesh Santhana Krishnan | Anusha Badveeti | Dev | Tranformers | 3 | Yes | Just one or two day post sprint planning, there is a priority shift and we move things up and down, making sprint planning useless. --> Saw we started doing sprint planning a day before to make it effective at sprint start | Yes | Chaotic | 3 | 4 | 3 | 4 | Yes | 4 | 4 | Individual | 4 | 5 | Yes | Moderately | None | 10% to 20% | Yes | Moderate | Over Utilised (90% and Above) | Some Information but still need further details | Not aware of any such initiative. Though the release coordination among teams was better than previous releases among teams | Average | Monitoring and Controlling Progress | Sprint Planning | KT and recording repository | Blocking Scope change | Better Estimations & Epic Breakdown | PR Merges | Less than 5% | no | Not Efficiently | no | no |  | Yes | ChatGPT, CoPilot | 10% to 20% | Yes
2025-04-09 16:48 | Jegadeesh Santhana Krishnan | Jegadeesh Santhana Krishnan | EM |  |  |  |  | Yes | Well Managed | 5 | 5 | 5 | 5 | Yes | 5 | 5 | Scrum Team | 4 | 4 | Yes | YES | Moderate | More than 30% | Yes | None | Balanced (80% - 90%) | Some Information but still need further details | Yes | Well Managed | Code Freeze Milestones and hardening phase | Sprint Retrospective | KT and recording repository | Risk call out during Weekly SoS | Release Planning, Strategy & Schedule (Proper Checkpoint and dates on jira tickets) | Improper Epic Breakdown & Estimations - Missing Sprint Backlog | My role involves process improvement and enablement (EM's, SM's & Other folks responsible for process streamlining) |  | YES | none |  |  | Yes | ChatGPT | 10% to 20% | Yes
2025-04-10 23:50 | Mujtaba Ahmad | Priya Vanteru | Dev | Indus | 5 | No |  | Yes | Balanced | 4 | 4 | 4 | 4 | Yes | 4 | 5 | Individual | 4 | 4 | Yes | YES | Moderate | 10% to 20% | No | Moderate | Balanced (80% - 90%) | Optimal information available | Not aware of any such initiative. Though the release coordination among teams was better than previous releases among teams | Average | Code Freeze Milestones and hardening phase | Sprint Retrospective | KT and recording repository | Risk call out during Weekly SoS | Better Estimations & Epic Breakdown | Ad-hoc Tasks & improper prioritisation | Less than 5% |  | YES | no |  |  | Yes | ChatGPT, CoPilot | 20% to 30% | Yes
2025-04-09 01:16 | Mujtaba Ahmad | Raman Soni | Dev | Stark | 5 | No |  | Yes | Well Managed | 5 | 5 | 5 | 5 | Yes | 5 | 5 | Scrum Team | 5 | 5 | Yes | YES | Multiple | Less than 10% | Yes | Moderate | Over Utilised (90% and Above) | Optimal information available | Yes | Well Managed | Epic Breakdown | Sprint Retrospective | KT and recording repository | Change in Due date and QA Sign off Date restrictions | Effective communication | Ad-hoc Tasks & improper prioritisation | Less than 5% |  | YES | N/A |  |  | Yes | ChatGPT, CoPilot | 10% to 20% | Yes
2025-04-09 17:45 | Jegadeesh Santhana Krishnan | Ramakrishna Grandhi | Dev | Tintin | 4 | No |  | Yes | Balanced | 5 | 5 | 5 | 5 | Yes | 5 | 4 | Scrum Team | 5 | 4 | Yes | Moderately | Multiple | 20% to 30% | Yes | None | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Monitoring and Controlling Progress | Sprint Retrospective | KT and recording repository | Change in Due date and QA Sign off Date restrictions | Better & transparent commitments | Ad-hoc Tasks & improper prioritisation | Less than 5% |  | YES | No |  |  | Yes | ChatGPT, CoPilot | 20% to 30% | Yes
2025-04-11 11:34 | Mohammed Fayaz | Anusha Jharupula | QA | Enigma | 4 | No |  | Yes | Balanced | 3 | 3 | 3 | 3 | Partially/Incomplete | 3 | 3 | Individual | 3 | 3 | Yes | Moderately | Moderate | Less than 10% | No | Multiple | Balanced (80% - 90%) | Optimal information available | Yes | Average | Monitoring and Controlling Progress | Sprint Retrospective | KT and recording repository | Blocking Scope change | Risk call out (Release Confluence Page) | Reviews | More Than 5% but less than 10% |  | YES | NA |  |  | Yes | AI tool to generate test cases | Just started using AI, need time to quantify | Yes
2025-04-09 10:15 | Mujtaba Ahmad | Diksha Khatri | Dev & Scrum Master | Titans | 5 | Yes | One point was brought up regarding the jenkins failures on integrator-common-util, although the entire issue is not resolved but discussions are now underway with arch council and wider group to improve the situation. | Yes | Well Managed | 5 | 5 | 5 | 5 | Yes | 5 | 5 | Scrum Team | 5 | 5 | Yes | YES | Moderate | 10% to 20% | Yes | Moderate | Over Utilised (90% and Above) | Optimal information available | Yes | Well Managed | Code Freeze Milestones and hardening phase | Sprint Closure/review | Non Release Activity Identification & capacity reserve | Risk call out during Weekly SoS | Release Planning, Strategy & Schedule (Proper Checkpoint and dates on jira tickets) | CS Bugs higher than the reserved Capacity | My role involves process improvement and enablement (EM's, SM's & Other folks responsible for process streamlining) |  | YES | NA |  |  | Yes | ChatGPT, CoPilot | 10% to 20% | Yes
2025-04-09 20:33 | Mohammed Fayaz | Mohammed Fayaz | QA | Dynamos | 5 | Yes | Code review: Team priorities it properly before and during sprint. | Yes | Well Managed | 4 | 4 | 4 | 4 | Yes | 4 | 4 | Scrum Team | 4 | 5 | Yes | YES | Moderate | 20% to 30% | Yes | None | Balanced (80% - 90%) | Some Information but still need further details | Yes | Well Managed | Code Freeze Milestones and hardening phase | Sprint Closure/review | Non Release Activity Identification & capacity reserve | Change in Due date and QA Sign off Date restrictions | Sprint Planning Structure | Reviews | More Than 5% but less than 10% |  | YES | Please add Test / Feature Environment availability for --- What is the most probable reason that deviates the planned timelines? |  |  | Yes | ChatGPT | 10% to 20% | Yes
2025-04-09 00:23 | Mujtaba Ahmad | Diksha Khatri | Dev | Iota | 4 | Yes | Updating epics status | Yes | Balanced | 4 | 4 | 4 | 4 | Yes | 4 | 4 | SME/Epic Owner/EM/QM (Pre Defined Efforts Estimates) | 4 | 4 | Yes | YES | Moderate | Less than 10% | No | Multiple | Balanced (80% - 90%) | Optimal information available | Yes | Average | Code Freeze Milestones and hardening phase | Sprint Closure/review | Non Release Activity Identification & capacity reserve | Change in Due date and QA Sign off Date restrictions | Reduced over commit | Non Release Activities | More Than 5% but less than 10% |  | YES | NA |  |  | Yes | ChatGPT, CoPilot, GitHub AI review | 10% to 20% | No
2025-04-11 14:54 | Mohammed Fayaz | Tharuni Sai Idupulapati | QA | Stark | 4 | Yes | respecting code freeze and wrapping issues before that | Yes | Balanced | 4 | 4 | 4 | 4 | Yes | 4 | 4 | Scrum Team | 4 | 3 | Yes | YES | Moderate | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Average | Monitoring and Controlling Progress | Sprint Closure/review | Non Release Activity Identification & capacity reserve | Change in Due date and QA Sign off Date restrictions | Reduced over commit | Ad-hoc Tasks & improper prioritisation | Less than 5% |  | YES | - |  |  | Yes | ChatGPT | 10% or below | Yes
2025-04-10 13:57 | Mohammed Fayaz | Komal Varma | QA | Aurora | 4 | Yes | NA | Yes | Balanced | 4 | 4 | 4 | 4 | Yes | 4 | 4 | Scrum Team | 4 | 4 | Yes | YES | Moderate | 10% to 20% | Yes | Moderate | Over Utilised (90% and Above) | Some Information but still need further details | Not aware of any such initiative. Though the release coordination among teams was better than previous releases among teams | Average | Code Freeze Milestones and hardening phase | Sprint Planning | Non Release Activity Identification & capacity reserve | Change in Due date and QA Sign off Date restrictions | Release Planning, Strategy & Schedule (Proper Checkpoint and dates on jira tickets) | Missing SLA's for Bugs, Trackers on Jira | Less than 5% |  | YES | na |  |  | Yes | ChatGPT, CoPilot, GitHub AI review | 20% to 30% | Yes
2025-04-10 15:16 | Mohammed Fayaz | Komal Varma | QA | Individual Capacity, Not Associated with any particular team | 5 | Yes | including automations within the sprint timelines instead of moving to hardening phases | Yes | Balanced | 5 | 5 | 5 | 5 | Yes | 5 | 4 | Scrum Team | 5 | 5 | Yes | YES | Moderate | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Committed Epic Prioritisation | Sprint Planning | Non Release Activity Identification & capacity reserve | Blocking Scope change | Reduced over commit | Delay in commitments from dependant team | More Than 5% but less than 10% |  | YES | No |  |  | Yes | ChatGPT | 20% to 30% | Yes
2025-04-09 17:00 | Jegadeesh Santhana Krishnan | Ramakrishna Grandhi | Dev | Avengers | 4 | No |  | Yes | Well Managed | 5 | 5 | 5 | 5 | Yes | 3 | 4 | Individual | 5 | 5 | Yes | YES | Moderate | 20% to 30% | Yes | Moderate | Over Utilised (90% and Above) | Optimal information available | Not aware of any such initiative. Though the release coordination among teams was better than previous releases among teams | Well Managed | Continuous Epic Grooming | Sprint Planning | Non Release Activity Identification & capacity reserve | Blocking Scope change | Reduced over commit | Non Release Activities | More Than 5% but less than 10% |  | YES | NA |  |  | Yes | CoPilot, Gemini | 10% to 20% | Yes
2025-04-10 14:08 | Jegadeesh Santhana Krishnan | Rajesh Subramani | Dev | Hercules | 4 | No |  | Yes | Balanced | 4 | 4 | 4 | 5 | Yes | 5 | 5 | Individual | 4 | 5 | Yes | YES | Moderate | Less than 10% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Continuous Epic Grooming | Sprint Planning | Non Release Activity Identification & capacity reserve | Risk call out during Weekly SoS | Better & transparent commitments | Ad-hoc Tasks & improper prioritisation | More Than 5% but less than 10% |  | YES | nil |  |  | Yes | ChatGPT, CoPilot | 10% or below | Yes
2025-04-08 23:00 | Mujtaba Ahmad | Priya Vanteru | Dev | Phi | 4 | Yes | Better communication between docs and dev team, better coordination was achieved by more frequent discussions | Yes | Balanced | 4 | 3 | 3 | 4 | Yes | 4 | 4 | SME/Epic Owner/EM/QM (Pre Defined Efforts Estimates) | 4 | 4 | Yes | YES | Moderate | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Epic Breakdown | Sprint Planning | Non Release Activity Identification & capacity reserve | Risk call out during Weekly SoS | Better & transparent commitments | Ad-hoc Tasks & improper prioritisation | More than 10% but Less than 20% |  | YES | More details regarding deliverables |  |  | Yes | ChatGPT, Claude | 10% or below | No
2025-04-11 13:24 | Jegadeesh Santhana Krishnan | Chandra Sekhar Kusupati | Dev & Scrum Master | Helios | 4 | Yes | Planning the items ahead and restricting the trackers to be added in middle of sprint | Yes | Balanced | 4 | 4 | 4 | 4 | Yes | 4 | 4 | Individual | 4 | 4 | Yes | YES | Moderate | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Some Information but still need further details | Not aware of any such initiative. Though the release coordination among teams was better than previous releases among teams | Average | Monitoring and Controlling Progress | Sprint Planning | Non Release Activity Identification & capacity reserve | Blocking Scope change | Better & transparent commitments | Intra team collaboration | Less than 5% |  | YES | NA |  |  | Yes | ChatGPT, CoPilot | 10% to 20% | Yes
2025-04-11 16:54 | Mujtaba Ahmad | Raman Soni | Dev | Apollo | 5 | Yes | Various action items like team should revisit the previous retro during mid sprint review, team to check post commit for successful tag deployment, individuals should clear up their backlog and adding proper comments were seriously taken up by the team and by monitoring the action items during mid-sprint review were done to ensure all the action items were resolved. | Yes | Chaotic | 3 | 4 | 3 | 4 | Yes | 4 | 4 | Scrum Team | 5 | 5 | Yes | YES | Moderate | Less than 10% | No | Moderate | Under Utilisation (80% Below) | Some Information but still need further details | Yes | Average | Release Kick Off | Sprint Planning | Non Release Activity Identification & capacity reserve | Risk call out during Weekly SoS | Efficient Jira Usage (New Fields such as - Due date, QA Lead, QA Involvement, QA Signoff date) | Non Release Activities | More Than 5% but less than 10% |  | YES | NA |  |  | Yes | ChatGPT, CoPilot, Gemini | 10% to 20% | Yes
2025-04-11 12:00 | Mujtaba Ahmad | Raman Soni | Dev | Apollo | 3 | No |  | Yes | Balanced | 4 | 4 | 4 | 4 | Yes | 4 | 4 | Scrum Team | 5 | 4 | Yes | YES | Moderate | Less than 10% | No | Moderate | Over Utilised (90% and Above) | Optimal information available | Yes | Well Managed | Continuous Epic Grooming | Sprint Retrospective | Non Release Activity Identification & capacity reserve | Blocking Scope change | Effective communication | Improper Epic Breakdown & Estimations - Missing Sprint Backlog | Less than 5% |  | YES | NA | JIra should be made less complex with easier workflows |  | Yes | ChatGPT, CoPilot | 10% to 20% | Yes
2025-04-08 14:30 | Mujtaba Ahmad | Priya Vanteru | Dev | Phi | 4 | No |  | Yes | Balanced | 4 | 4 | 3 | 3 | Yes | 3 | 4 | Individual | 3 | 3 | Yes | Moderately | Moderate | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Continuous Epic Grooming | Sprint Retrospective | Non Release Activity Identification & capacity reserve | Risk call out during Weekly SoS | None | Non Release Activities | More Than 5% but less than 10% |  | YES | Nothing |  |  | Yes | ChatGPT | 10% or below | Yes
2025-04-08 15:44 | Jegadeesh Santhana Krishnan | Anusha Badveeti | Dev | Dynamos | 4 | Yes | NA | Yes | Balanced | 4 | 4 | 4 | 4 | Yes | 4 | 4 | Scrum Team | 4 | 4 | No | YES | Moderate | Less than 10% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Continuous Epic Grooming | Sprint Closure/review | Tech Design | Change in Due date and QA Sign off Date restrictions | None | Reviews | Less than 5% |  | YES | NA |  |  | Yes | ChatGPT, CoPilot | 10% or below | Yes
2025-04-10 21:48 | Mujtaba Ahmad | Diksha Khatri | Dev | Enigma | 4 | Yes | During the previous release, we encountered a canary deployment issue, which led to an action item in retro for re-verifying the error rate%. A tracker was put in place to monitor this. a through analysis after updated the proper error rate%. the NetSuite Distributed Adapter was deployed smoothly without any issues during the April release. | Yes | Balanced | 4 | 4 | 5 | 5 | Yes | 4 | 4 | Individual | 5 | 4 | Yes | YES | Moderate | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Release Kick Off | Sprint Closure/review | Tech Design | Change in Due date and QA Sign off Date restrictions | Effective communication | PR Merges | More Than 5% but less than 10% |  | YES | No |  |  | Yes | ChatGPT, CoPilot | 10% or below | Yes
2025-04-09 15:41 | Jegadeesh Santhana Krishnan | Rajesh Subramani | Dev | Hercules | 4 | Yes | Epic should be in right status before code freeze which we make sure by discussing the same in scrum call. Defining the sprint scope which we used to do in sprint planning. | Yes | Balanced | 4 | 4 | 4 | 4 | Yes | 4 | 4 | Scrum Team | 4 | 4 | Yes | Moderately | Moderate | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Some Information but still need further details | Yes | Average | Epic Breakdown | Sprint DSU's | Tech Design | Risk call out during Weekly SoS | Better & transparent commitments | Ad-hoc Tasks & improper prioritisation | More than 10% but Less than 20% |  | YES | NA |  |  | Yes | ChatGPT, CoPilot | 10% or below | Yes
2025-04-10 14:49 | Mujtaba Ahmad | Priya Vanteru | Dev | Indus | 5 | Yes | NA | Yes | Well Managed | 5 | 5 | 5 | 5 | Yes | 5 | 4 | Scrum Team | 4 | 4 | Yes | YES | Multiple | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Some Information but still need further details | Yes | Well Managed | Epic Breakdown | Sprint DSU's | Tech Design | Risk call out during Weekly SoS | Effective communication | Communication gap b/w dependent teams | More than 10% but Less than 20% |  | YES | NA |  |  | Yes | ChatGPT, CoPilot | 10% to 20% | Yes
2025-04-08 12:46 | Krishna Kishore Mothukuri | Ajitkumar kaller | Dev | Velocity | 5 | Yes | Breaking of EPIC | Yes | Well Managed | 3 | 4 | 4 | 4 | Partially/Incomplete | 4 | 5 | Scrum Team | 4 | 4 | Yes | YES | Multiple | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Some Information but still need further details | Yes | Well Managed | Continuous Epic Grooming | Sprint Planning | Tech Design | Blocking Scope change | Release Planning, Strategy & Schedule (Proper Checkpoint and dates on jira tickets) | Improper Epic Breakdown & Estimations - Missing Sprint Backlog | More Than 5% but less than 10% |  | YES | NA |  |  | Yes | ChatGPT, CoPilot, Perplexity, GitHub AI review | 20% to 30% | Yes
2025-04-11 15:11 | Mujtaba Ahmad | Raman Soni | Dev | Ganges | 5 | Yes | issue related to mongoose-util => dev's have to update the correct package version until adaptor and models breakdown is done | Yes | Balanced | 4 | 4 | 5 | 4 | Yes | 5 | 5 | Scrum Team | 4 | 5 | Yes | YES | Moderate | Less than 10% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Continuous Epic Grooming | Sprint Planning | Tech Design | Blocking Scope change | Sprint Planning Structure | Modifications on Approved Tech designs | Less than 5% |  | YES | - |  |  | Yes | ChatGPT | 10% or below | Yes
2025-04-09 01:00 | Jegadeesh Santhana Krishnan | Ankur Sachdeva | Dev | Echo | 5 | No |  | Yes | Balanced | 4 | 4 | 4 | 4 | Yes | 4 | 4 | Scrum Team | 4 | 4 | Yes | Moderately | Moderate | 20% to 30% | No | Moderate | Balanced (80% - 90%) | Some Information but still need further details | Not aware of any such initiative. Though the release coordination among teams was better than previous releases among teams | Average | Epic Breakdown | Sprint Planning | Tech Design | Change in Due date and QA Sign off Date restrictions | Better & transparent commitments | Ad-hoc Tasks & improper prioritisation | More than 20% |  | YES | NA | NA |  | Yes | ChatGPT, Claude | 20% to 30% | Yes
2025-04-09 21:07 | Jegadeesh Santhana Krishnan | Ashok Kumar Dantham | Dev | Iris | 5 | Yes | No scope change | Yes | Chaotic | 3 | 2 | 2 | 2 | Partially/Incomplete | 5 | 3 | Individual | 3 | 3 | Yes | Moderately | Moderate | 10% to 20% | Yes | Moderate | Over Utilised (90% and Above) | Not at All | No | Average | Epic Breakdown | Sprint Planning | Tech Design | Strict Bug SLA's | Release Planning, Strategy & Schedule (Proper Checkpoint and dates on jira tickets) | Improper Epic Breakdown & Estimations - Missing Sprint Backlog | Less than 5% |  | YES | Need clarity in code freeze dates and ease for exclusion | remove the qa signoff date required to move trackers to inprogress |  | Yes | ChatGPT, CoPilot | 10% to 20% | Yes
2025-04-11 10:50 | Mujtaba Ahmad | Diksha Khatri | Dev & Scrum Master | Enigma | 5 | Yes | Team coordination | Yes | Balanced | 4 | 4 | 5 |  | Yes | 5 | 5 | Scrum Team | 5 | 4 | Yes | YES | Moderate | 10% to 20% | Yes | None | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Monitoring and Controlling Progress | Sprint Planning | Tech Design | Risk call out during Weekly SoS | Better & transparent commitments | Non Release Activities | More than 10% but Less than 20% |  | YES | no |  |  | Yes | ChatGPT, CoPilot | 10% to 20% | Yes
2025-04-10 13:34 | Jegadeesh Santhana Krishnan | Chandra Sekhar Kusupati | Dev | Eirene | 5 | No |  | Yes | Well Managed | 5 | 5 | 5 | 5 | Yes | 5 | 5 | Individual | 5 | 5 | Yes | YES | None | Less than 10% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Code Freeze Milestones and hardening phase | Sprint Retrospective | Tech Design | Blocking Scope change | Better & transparent commitments | Ad-hoc Tasks & improper prioritisation | Less than 5% |  | YES | No |  |  | Yes | ChatGPT, CoPilot | 10% or below | Yes
2025-04-10 17:39 | Jegadeesh Santhana Krishnan | Subhan Ansari | Dev & Scrum Master | Aliens | 4 | No |  | Yes | Chaotic | 3 | 4 | 5 | 5 | Yes | 4 | 5 | Individual | 5 | 3 | Yes | YES | Moderate | 20% to 30% | No | Multiple | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Epic Breakdown | Sprint Retrospective | Tech Design | Strict Bug SLA's | None | Non Release Activities | More Than 5% but less than 10% |  | YES | na | na |  | Yes | ChatGPT | Just started using AI, need time to quantify | Yes
2025-04-11 10:23 | Mujtaba Ahmad | Mujtaba Ahmad | Dev | Edi | 5 | Yes | Edi and good | Yes | Well Managed | 2 | 5 | 1 | 5 | Partially/Incomplete | 5 | 5 | Individual | 5 | 5 | Yes | YES | None | More than 30% | Yes | Moderate | Balanced (80% - 90%) | Some Information but still need further details | Not aware of any such initiative. Though the release coordination among teams was better than previous releases among teams | Average | Monitoring and Controlling Progress | Sprint Retrospective | Tech Design | Strict Bug SLA's | None | Improper Epic Breakdown & Estimations - Missing Sprint Backlog | More than 20% | Nil | YES | Nil | Nil |  | Yes | ChatGPT, CoPilot, Perplexity, Gemini, GitHub AI review, Claude, Langchain, Scrapper | Just started using AI, need time to quantify | Yes
2025-04-10 17:01 | Mujtaba Ahmad | Priya Vanteru | Dev | Minions | 4 | Yes | Dedicated bandwidth for predictable non dev activities like monitoring after each release | Yes | Balanced | 4 | 3 | 5 | 4 | Partially/Incomplete | 4 | 4 | Individual | 4 | 4 | No | YES | Multiple | 20% to 30% | No | Multiple | Over Utilised (90% and Above) | Optimal information available | Yes | Well Managed | Monitoring and Controlling Progress | Sprint Closure/review | Test Design | Change in Due date and QA Sign off Date restrictions | Release Planning, Strategy & Schedule (Proper Checkpoint and dates on jira tickets) | Ad-hoc Tasks & improper prioritisation | More than 10% but Less than 20% |  | Not Efficiently | NA |  |  | Yes | ChatGPT, CoPilot, GitHub AI review | 30% and Above | No
2025-04-11 18:09 | Jegadeesh Santhana Krishnan | Chandra Sekhar Kusupati | Dev | Eirene | 5 | Yes | more communication | Yes | Well Managed | 4 | 5 | 5 | 5 | Yes | 4 | 4 | Individual | 4 | 4 | No | YES | Multiple | Less than 10% | Yes | None | Balanced (80% - 90%) | Optimal information available | Yes | Average | Release Kick Off | Sprint Closure/review | Test Design | Risk call out during Weekly SoS | Better Estimations & Epic Breakdown | Reviews | Less than 5% |  | YES | . |  |  | Yes | ChatGPT, CoPilot, Gemini, GitHub AI review | 10% to 20% | Yes
2025-04-08 12:44 | Mujtaba Ahmad | Raman Soni | Dev | Stark | 4 | No |  | Yes | Well Managed | 4 | 4 | 4 | 4 | Yes | 4 | 4 | Scrum Team | 4 | 4 | Yes | Moderately | Moderate | 20% to 30% | Yes | Moderate | Balanced (80% - 90%) | Some Information but still need further details | Not aware of any such initiative. Though the release coordination among teams was better than previous releases among teams | Average | Continuous Epic Grooming | Sprint Planning | Test Design | Blocking Scope change | Effective communication | Ad-hoc Tasks & improper prioritisation | More than 10% but Less than 20% |  | YES | NA |  |  | Yes | ChatGPT, CoPilot, Perplexity, Gemini, GitHub AI review | 10% to 20% | Yes
2025-04-09 16:00 | Jegadeesh Santhana Krishnan | Ashok Kumar Dantham | Dev & Scrum Master | Aurora | 4 | Yes | - | No | [33 empty] | Yes | ChatGPT, CoPilot | 10% to 20% | Yes
2025-04-10 07:00 | Jegadeesh Santhana Krishnan | Chandra Sekhar Kusupati | Dev | Helios | 4 | Yes | Meeting deadline | No | [32 empty] | The tasks done be me will be part lf May release | Yes | ChatGPT, CoPilot | 10% to 20% | Yes
2025-04-10 13:37 | Jegadeesh Santhana Krishnan | Rajesh Subramani | Dev | Helios | 5 | Yes | sprint planning was effective | No | [32 empty] | Working on the items deliverable in next release | Yes | ChatGPT, CoPilot | 20% to 30% | Yes
2025-04-10 14:23 | Jegadeesh Santhana Krishnan | Rajesh Subramani | Dev | Hercules | 5 | Yes | Sprint grooming was not present earlier, we discussed and now doing grooming. | No | [32 empty] | Development | Yes | ChatGPT, CoPilot | 20% to 30% | Yes
2025-04-11 12:45 | Jegadeesh Santhana Krishnan | Ramakrishna Grandhi | Dev | Avengers | 3 | Yes | NA | No | [32 empty] | NA | Yes | ChatGPT, CoPilot | 10% to 20% | Yes
2025-04-11 19:40 | Jegadeesh Santhana Krishnan | Subhan Ansari | Dev | Aliens | 4 | Yes | - | No | [33 empty] | Yes | ChatGPT, CoPilot, Perplexity, Gemini, Claude | 30% and Above | Yes
2025-04-14 12:17 | Jegadeesh Santhana Krishnan | Jegadeesh Santhana Krishnan | Architect/Individual Contributors |  |  |  |  | No | [32 empty] | Tech Debts & Architect Council Initiatives | Yes | ChatGPT, CoPilot, GitHub AI review, Langchain | 10% to 20% | Yes
2025-04-08 13:25 | Krishna Kishore Mothukuri | Krishna Kishore Mothukuri | Architect/Individual Contributors |  |  |  |  | No | [32 empty] | Research and POCs for future features of IO | Yes | ChatGPT, CoPilot, Langchain | 30% and Above | Yes
2025-04-09 12:01 | Krishna Kishore Mothukuri | Krishna Kishore Mothukuri | Architect/Individual Contributors |  |  |  |  | No | [32 empty] | Developmentof automated testcase generation for internal conasumption. | Yes | ChatGPT, CoPilot, Gemini, Langchain, Scrapper | 30% and Above | Yes
2025-04-11 15:30 | Krishna Kishore Mothukuri | Krishna Kishore Mothukuri | Dev | Inceris | 4 | No |  | No | [32 empty] | We were focusing on the localsetup on io microservices. This is a replica of integrator.io and can be useful for testing and development to increase the effectiveness and velocity of engineers. | Yes | ChatGPT, CoPilot | 10% to 20% | Yes
2025-04-11 15:35 | Krishna Kishore Mothukuri | Krishna Kishore Mothukuri | Dev | Inceris | 1 | No |  | No | [32 empty] | Localsetup development | Yes | ChatGPT, CoPilot, Gemini | 30% and Above | Yes
2025-04-08 13:00 | Mohammed Fayaz | Prasad Deverakonda | QA | Tetris | 5 | Yes | tag update to be done properly by scrum teams / microservice owners.use utility to get the latest tags from the cd and cd staging repo{ARGOCD} and inform to scrum QA teams | No | [33 empty] | Yes | ChatGPT | 10% to 20% | Yes
2025-04-08 15:45 | Mohammed Fayaz | Anusha Jharupula | QA | Individual Capacity, Not Associated with any particular team | 4 | No |  | No | [32 empty] | Backlog Rest API automation and stabilization | No | ChatGPT | Just started using AI, need time to quantify | Yes
2025-04-09 15:26 | Mohammed Fayaz | Prasad Deverakonda | QA | Tetris | 5 | Yes | Different action items were discussed during retro which were followed up and implemented | No | [32 empty] | E2E activities, Anomaly Detection, Deep Testing, ZD | Yes | Perplexity | 10% to 20% | Yes
2025-04-10 13:48 | Mohammed Fayaz | SathishKumar D | QA | Optimus | 4 | No |  | No | [32 empty] | TIme for Fun | Yes | ChatGPT, CoPilot | 20% to 30% | Yes
2025-04-10 13:56 | Mohammed Fayaz | Komal Varma | QA | Individual Capacity, Not Associated with any particular team | 4 | Yes | - | No | [32 empty] | Floating Staff QA role handling QA initiatives apart from Release items | Yes | ChatGPT | 30% and Above | Yes
2025-04-10 13:58 | Mohammed Fayaz | SathishKumar D | QA | Optimus | 4 | Yes | NA | No | [32 empty] | enhancements to the automation framework | Yes | ChatGPT, CoPilot | 10% to 20% | Yes
2025-04-11 22:54 | Mohammed Fayaz | Mohammed Fayaz | EM |  |  |  |  | No | [32 empty] | Managing releases as EM | Yes | ChatGPT | 30% and Above | Yes
2025-04-10 18:01 | Mohammed Fayaz | SathishKumar D | QA | Optimus | 5 | Yes | NA | No | [33 empty] | Yes | ChatGPT, CoPilot | 20% to 30% | Yes
2025-04-11 13:42 | Mohammed Fayaz | SathishKumar D | QA | Helios | 5 | Yes | worked on fixing automation failures | No | [32 empty] | Fixing Automation failures | Yes | CoPilot | 30% and Above | Yes
2025-04-11 17:24 | Mohammed Fayaz | SathishKumar D | QA | Optimus (Automation Team) | 5 | Yes | NA - I am from the automation team and we are not participating in the release activities. | No | [32 empty] | NA | Yes | ChatGPT, CoPilot | 30% and Above | Yes
2025-04-11 17:39 | Mohammed Fayaz | SathishKumar D | QA | Optimus(Automation Team) | 5 | No |  | No | [32 empty] | NA - Since We are Automation team, we do not take part in release activities | Yes | ChatGPT | 30% and Above | Yes
2025-04-11 15:47 | Mujtaba Ahmad | SWATANTRA ROUT | Dev | Nexus | 5 | No |  | No | [33 empty] | Yes | ChatGPT, CoPilot, GitHub AI review | 20% to 30% | Yes
2025-04-08 21:17 | Mujtaba Ahmad | Mujtaba Ahmad | EM |  |  |  |  | No | [32 empty] | Planning | Yes | ChatGPT | 10% to 20% | Yes
2025-04-08 23:19 | Mujtaba Ahmad | Mujtaba Ahmad | EM |  |  |  |  | No | [33 empty] | Yes | ChatGPT, Perplexity | 20% to 30% | Yes
2025-04-09 11:46 | Mujtaba Ahmad | Diksha Khatri | EM |  |  |  |  | No | [32 empty] | Overlooking Scrum activities since we have enabled Scrum masters to individually drive it without my much involvment. | Yes | ChatGPT, Gemini, GitHub AI review | Just started using AI, need time to quantify | No