## Form Responses 1
Timestamp | You are part of which of the following directors org | What's your primary role? | Enter the Team/Scrum team that you are mostly associated with during the release. (Select Only One) | Are you using AI for efficiency improvement in your day to day Dev/QA activity? | With the usage of AI what has been increase in your productivity? | Are you getting the required support and guidance within Engineering to explore and increase efficiency using AI? | Are you directly involved in the Release Deliverables for current release items or items planned and in progress for future releases? | How would you rate Release Overall (Individual Perspective) ? | How would you rate the release planning in comparison to previous release plannings? (1-Poor, 5- Improved) | How well were you as an individual aware of your teams commitments and scope of work prior to release implementation start ? (1-Not Aware, 5- Aware) | What was your involvement in Release planning and the selection of commitments? (1-Not Involved, 5- Fully Involved) | Were you as an individual aware of the Release timelines and your tasks in hand for the Release ? (1-Somewhat Aware, 5- Fully Aware) | Detailed Epic Breakdown with estimates and scrum team ownership were done for your trackers parent epic prior to Release Implementation Initiation. | How confident were you in terms of your teams commitments and deliverables? (1-Not Confident, 5- Full Confidence) | How would you rate effectiveness the Sprint Planning Meetings ? (1-Not Effective, 5- Effective) | Individual items efforts estimate for completion of the task is done by whom ? | How would you rate effectiveness of the Daily Standup connect to understand and analyse your tasks in hand ? (1-Not Effective, 5- Effective) | How would you rate effectiveness of the Sprint Closure / review meetings ? (1-Not Effective, 5- Effective) | Was Sprint retrospective Conducted for your Team at the end of each Sprint | Sprint Retrospective Effectiveness | Do you as an individual get sufficient opportunity to raise risk or concerns during agile ceremonies? | Do you get opportunity to learn new things in accordance to your role release over release? | What percentage of your capacity in the sprint was reserved for Items such as CS Support Bugs/Requests which cannot be estimated but as a team you reserve some bandwidth, as per history your are aware of such requests and your team reserves capacity for it ? | Is your reserved capacity for the Historical support activities such as CS Bugs/Support tickets and others, sufficient during the release. | How much Adhoc requests (Request for which no bandwidth was reserved during Release/Sprint Planning) were received during implementation Phase. | How was your available capacity utilised during the Release i.e. your workload. (1-Under Utilisation, 5- Over Utilisation) | Do you have sufficient details available on Jira to successfully and independently complete your assigned tasks | Was the Release Coordination Group initiated with representatives from each directors org, helpful and more efficient in managing the Release checkpoints and ensuring the key asks were routed better to the respective team/people? | How well were dependencies managed in the Release. | Check the Release Ceremony where there is need to spend more efforts to make the release more effective. | Check the Sprint Ceremony where there is need to spend more efforts to make the release more effective. | What is the top improvement area in the below list you would suggest to improve for a smoother release? | What do we need to improve in Release Implementation | Anything that you would like to call out which improved in this release as compared to the previous releases. | What is the most probable reason that deviates the planned timelines? | Applicable only for pure DEV or QA Resources - What percent of your available capacity is impacted by process changes and new processes enablement on regular tasks not the other cleanup activities from previous releases (Not Applicable to EM's, SM's & Other Folks responsible for process streamlining) | Any other thought you would like to share related to the releases. | In Your individual opinion are we considering the release Delivery Timelines and milestones while we are planning and delivering our assigned tasks | Do you have any suggestion for improving and streamlining the release further?
2024-08-14 11:51 | Mujtaba Ahmad | Dev | Stark | Yes | 10% or below | Yes | Yes | Chaotic | 3 | 4 | 3 | 4 | Yes | 4 | 4 | Scrum Team | 4 | 4 | Yes | 4 | YES | Multiple | 10% to 20% | No | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Not Well | Continuous Epic Grooming | Sprint Planning | Bugs Management & Deferring | Strict Bug SLA's | Release Planning, Strategy & Schedule (Proper Checkpoint and dates on jira tickets) | Ad-hoc Tasks & improper prioritisation | More Than 5% but less than 10% |  | YES | standard process regarding rebasing and dependency management across multiple repos
2024-08-14 11:51 | Mujtaba Ahmad | Dev & Scrum Master | Stark | Yes | 10% to 20% | Yes | Yes | Balanced | 4 | 4 | 4 | 4 | Yes | 4 | 4 | Individual | 4 | 4 | No |  | YES | Multiple | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Committed Epic Prioritisation | Sprint Planning | Tech Design | Blocking Scope change | Better Estimations & Epic Breakdown | Ad-hoc Tasks & improper prioritisation | More than 10% but Less than 20% |  | YES | NA
2024-08-14 11:51 | Jegadeesh Santhana Krishnan | Dev | Hercules | Yes | 10% to 20% | Yes | Yes | Well Managed | 5 | 5 | 5 | 5 | Yes | 4 | 5 | Scrum Team | 5 | 5 | Yes | 4 | YES | Multiple | 10% to 20% | Yes | Moderate | Over Utilised (90% and Above) | Optimal information available | Yes | Well Managed | Continuous Epic Grooming | Sprint Planning | Backlog & CS bugs prioritisation | Blocking Scope change | Release Planning, Strategy & Schedule (Proper Checkpoint and dates on jira tickets) | Improper Epic Breakdown & Estimations - Missing Sprint Backlog | Less than 5% |  | YES | No
2024-08-14 11:53 | Jegadeesh Santhana Krishnan | Dev | Eirene | Yes | 10% to 20% | Yes | Yes | Balanced | 5 | 5 | 4 | 5 | Yes | 4 | 5 | Individual | 5 | 5 | Yes | 5 | YES | Multiple | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Monitoring and Controlling Progress | Sprint Planning | CI/CD, Testing & Continuous planning | Change in Due date and QA Sign off Date restrictions | Release Planning, Strategy & Schedule (Proper Checkpoint and dates on jira tickets) | Delayed Response on open Queries, need multiple followups | Less than 5% |  | YES | nil
2024-08-14 11:58 | Krishna Kishore Mothukuri | Dev | Hercules | Yes | 20% to 30% | Yes | No
2024-08-14 12:07 | Mohammed Fayaz | QA | Phi | Yes | 10% or below | No | Yes | Balanced | 3 | 3 | 2 | 3 | No | 3 | 3 | Individual | 3 | 3 | Yes | 3 | YES | None | 20% to 30% | Yes | Moderate | Under Utilisation (80% Below) | Optimal information available | Not aware of any such initiative. Though the release coordination among teams was better than previous releases among teams | Average | Committed Epic Prioritisation | Sprint Planning | Jira Automation | Risk call out during Weekly SoS | Sprint Planning Structure | Ad-hoc Tasks & improper prioritisation | More than 20% | NS | Not Efficiently | NA
2024-08-14 12:11 | Mujtaba Ahmad | Dev | Apollo | Yes | 10% to 20% | Yes | Yes | Balanced | 4 | 4 | 5 | 4 | Yes | 4 | 3 | Scrum Team | 4 | 3 | Yes | 3 | YES | None | Less than 10% | No | Moderate | Over Utilised (90% and Above) | Some Information but still need further details | Yes | Not Well | Continuous Epic Grooming | Sprint Planning | Ad-hoc requests prioritisation and acceptance | Change in Due date and QA Sign off Date restrictions | Better Estimations & Epic Breakdown | Ad-hoc Tasks & improper prioritisation | More than 10% but Less than 20% |  | YES | The Adhoc reprioritisation within Sprint also impacts delivery .
2024-08-14 12:14 | Mujtaba Ahmad | EM | Stark | Yes | 10% to 20% | Yes | Yes | Balanced | 5 | 5 | 5 | 5 | Yes | 5 | 4 | Scrum Team | 4 | 4 | Yes | 4 | YES | Multiple | Less than 10% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Code Freeze Milestones and hardening phase | Sprint Closure/review | CI/CD, Testing & Continuous planning | Risk call out during Weekly SoS | Better Estimations & Epic Breakdown | PR Merges | My role involves process improvement and enablement (EM's, SM's & Other folks responsible for process streamlining) |  | YES | We need checklist for different components upgrade and their usage before code freeze and release branches creation.
2024-08-14 12:17 | Jegadeesh Santhana Krishnan | Dev | Pheonix | Yes | 30% and Above | Yes | Yes | Balanced | 5 | 5 | 5 | 5 | Yes | 5 | 5 | Individual | 5 | 5 | Yes | 5 | YES | Moderate | Less than 10% | Yes | Moderate | Balanced (80% - 90%) | Some Information but still need further details | Yes | Well Managed | Committed Epic Prioritisation | Sprint Planning | Non Release Activity Identification & capacity reserve | Risk call out during Weekly SoS | Better & transparent commitments | Partial or missing details on Jira Trackers Description | Less than 5% |  | YES | NA
2024-08-14 12:17 | Jegadeesh Santhana Krishnan | Dev | Hercules | Yes | 10% to 20% | Yes | Yes | Balanced | 4 | 4 | 4 | 4 | Yes | 4 | 4 | Individual | 4 | 5 | No |  | NO | Moderate | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Some Information but still need further details | Yes | Average | Epic Breakdown | Sprint Planning | Tech Design | Strict Bug SLA's | Better & transparent commitments | Improper Epic Breakdown & Estimations - Missing Sprint Backlog | More Than 5% but less than 10% |  | YES | Current process looks good to me.
2024-08-14 12:18 | Jegadeesh Santhana Krishnan | Others | Individual Capacity, Not Associated with any particular team | Yes | 10% or below | Yes | No
2024-08-14 12:32 | Mujtaba Ahmad | Dev | Chakra | Yes | 20% to 30% | Yes | Yes | Well Managed | 2 | 1 | 1 | 1 | Yes | 4 | 4 | Scrum Team | 4 | 4 | Yes | 4 | YES | Multiple | Less than 10% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Not aware of any such initiative. Though the release coordination among teams was better than previous releases among teams | Well Managed | Monitoring and Controlling Progress | Sprint Closure/review | Test Design | Change in Due date and QA Sign off Date restrictions | Work allocation with sufficient capacity reserve | Modifications on Approved Tech designs | Less than 5% |  | YES | -
2024-08-14 12:55 | Mohammed Fayaz | QA | Sharks | Yes | 10% or below | Yes | Yes | Well Managed | 5 | 5 | 5 | 5 | Yes | 5 | 5 | Individual | 5 | 5 | Yes | 5 | YES | Multiple | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Continuous Epic Grooming | Sprint Planning | Intra Team Collaboration - Dependency linking on Jira by Individual owners | Blocking Scope change | Risk call out (Release Confluence Page) | Intra team collaboration | More Than 5% but less than 10% |  | YES | NA
2024-08-14 12:56 | Sandeep Kumar | Dev | Omega | Yes | 30% and Above | Yes | No
2024-08-14 13:06 | Mohammed Fayaz | QA | Falcon | Yes | 10% to 20% | Yes | Yes | Balanced | 5 | 4 | 5 | 4 | Yes | 4 | 5 | SME/Epic Owner/EM/QM (Pre Defined Efforts Estimates) | 5 |  | Yes | 5 | YES | Moderate | Less than 10% | No | Moderate | Over Utilised (90% and Above) | Optimal information available | Yes | Well Managed | Committed Epic Prioritisation | Sprint Retrospective | Ad-hoc requests prioritisation and acceptance | Blocking Scope change | Release Planning, Strategy & Schedule (Proper Checkpoint and dates on jira tickets) | Ad-hoc Tasks & improper prioritisation | More Than 5% but less than 10% | NA | YES | NA
2024-08-14 13:30 | Mohammed Fayaz | QA | Zeta | Yes | 10% or below | Yes | Yes | Balanced | 4 | 4 | 4 | 4 | Yes | 3 | 4 | Individual | 4 | 4 | Yes | 4 | YES | Moderate | Less than 10% | Yes | Moderate | Over Utilised (90% and Above) | Some Information but still need further details | Yes | Average | Committed Epic Prioritisation | Sprint Planning | Ad-hoc requests prioritisation and acceptance | Strict Bug SLA's | Effective communication | Ad-hoc Tasks & improper prioritisation | More Than 5% but less than 10% |  | YES | No
2024-08-14 13:47 | Mujtaba Ahmad | Dev | Stark | Yes | 10% to 20% | Yes | Yes | Balanced | 4 | 5 | 5 | 5 | Yes | 4 | 4 | Individual | 5 | 5 | Yes | 5 | Moderately | Moderate | 10% to 20% | No | Multiple | Over Utilised (90% and Above) | Optimal information available | Yes | Average | Continuous Epic Grooming | Sprint Planning | Ad-hoc requests prioritisation and acceptance | Risk call out during Weekly SoS | Better Estimations & Epic Breakdown | Ad-hoc Tasks & improper prioritisation | More Than 5% but less than 10% |  | YES | N/A
2024-08-14 14:12 | Mujtaba Ahmad | Dev & Scrum Master | Apollo | Yes | 10% or below | Yes | Yes | Chaotic | 2 | 4 | 4 | 5 | Yes | 4 | 4 | Individual | 4 | 3 | Yes | 3 | Moderately | Moderate | 10% to 20% | Yes | Multiple | Over Utilised (90% and Above) | Some Information but still need further details | Yes | Average | Code Freeze Milestones and hardening phase | Sprint Retrospective | Ad-hoc requests prioritisation and acceptance | Risk call out during Weekly SoS | Dependency management | Intra team collaboration | Less than 5% |  | YES | If dates & time for code-freeze for normal release & patch could be strictly adhered to and and changes should be informed via email rather than slack, where some people on a channel may/maynot be there.
2024-08-14 14:59 | Jegadeesh Santhana Krishnan | Dev | Chipmuks | Yes | 10% to 20% | Yes | Yes | Balanced | 3 | 4 | 5 | 4 | Yes | 4 | 4 | Scrum Team | 5 | 4 | Yes | 4 | YES | Moderate | 10% to 20% | Yes | Moderate | Over Utilised (90% and Above) | Some Information but still need further details | Not aware of any such initiative. Though the release coordination among teams was better than previous releases among teams | Average | Epic Breakdown | Sprint Retrospective | KT and recording repository | Blocking Scope change | Reduced over commit | Partial or missing details on Jira Trackers Description | More Than 5% but less than 10% |  | Not Efficiently | no
2024-08-14 15:50 | Mohammed Fayaz | QA | Invincibles | No |  |  | Yes | Chaotic | 2 | 5 | 3 | 4 | No | 4 | 3 | Scrum Team | 4 | 4 | Yes | 5 | YES | None | 10% to 20% | No | Multiple | Balanced (80% - 90%) | Not at All | Not aware and did not find any significant change in the release coordination among teams | Average | Monitoring and Controlling Progress | Sprint Planning | Non Release Activity Identification & capacity reserve | Blocking Scope change | Effective communication | Non Release Activities | More than 10% but Less than 20% | NA | Not Efficiently | NA
2024-08-14 15:59 | Mohammed Fayaz | QA | Gryffindor | Yes | 10% to 20% | Yes | Yes | Balanced | 4 | 5 | 5 | 4 | Yes | 5 | 4 | Individual | 5 | 5 | Yes | 5 | YES | None | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Average | Committed Epic Prioritisation | Sprint Planning | Ad-hoc requests prioritisation and acceptance | Change in Due date and QA Sign off Date restrictions | Better & transparent commitments | Reviews | More Than 5% but less than 10% |  | YES | no
2024-08-14 16:21 | Jegadeesh Santhana Krishnan | Dev | Pheonix | Yes | 10% to 20% | Yes | Yes | Well Managed | 4 | 5 | 2 | 5 | Yes | 5 | 5 | Individual | 5 | 3 | Yes | 5 | YES | Moderate | Less than 10% | Yes | None | Balanced (80% - 90%) | Optimal information available | Not aware and did not find any significant change in the release coordination among teams | Well Managed | Committed Epic Prioritisation | Sprint Closure/review | Intra Team Collaboration - Dependency linking on Jira by Individual owners | Blocking Scope change | None | Intra team collaboration | Less than 5% |  | YES | none
2024-08-14 16:38 | Jegadeesh Santhana Krishnan | Dev | Aurora | Yes | 30% and Above | Yes | Yes | Balanced | 4 | 3 | 4 | 4 | Yes | 4 | 4 | SME/Epic Owner/EM/QM (Pre Defined Efforts Estimates) | 4 | 4 | No |  | YES | Multiple | 20% to 30% | Yes | None | Balanced (80% - 90%) | Optimal information available | Not aware and did not find any significant change in the release coordination among teams | Well Managed | Epic Breakdown | Sprint Retrospective | KT and recording repository | Change in Due date and QA Sign off Date restrictions | Sprint Planning Structure | Modifications on Approved Tech designs | More than 10% but Less than 20% |  | YES | Retrospective should be done at the end of the sprint
2024-08-14 16:44 | Mohammed Fayaz | QA | Chloris | Yes | 10% or below | Yes | Yes | Balanced | 5 | 5 | 5 | 5 | Yes | 5 | 4 | Individual | 4 | 3 | Yes | 3 | Moderately | Moderate | Less than 10% | Yes | Moderate | Over Utilised (90% and Above) | Some Information but still need further details | Not aware of any such initiative. Though the release coordination among teams was better than previous releases among teams | Average | Code Freeze Milestones and hardening phase | Sprint Closure/review | Intra Team Collaboration - Dependency linking on Jira by Individual owners | Blocking Scope change | Efficient Jira Usage (New Fields such as - Due date, QA Lead, QA Involvement, QA Signoff date) | Delayed Response on open Queries, need multiple followups | More Than 5% but less than 10% |  | YES | NO
2024-08-14 16:53 | Mujtaba Ahmad | Dev | Titans | No |  |  | Yes | Well Managed | 4 | 5 | 2 | 5 | Yes | 5 | 5 | Individual | 5 | 5 | Yes | 5 | YES | Moderate | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Committed Epic Prioritisation | Sprint Closure/review | Jira Automation | Change in Due date and QA Sign off Date restrictions | Release Planning, Strategy & Schedule (Proper Checkpoint and dates on jira tickets) | Reviews | Less than 5% |  | YES | NA
2024-08-14 17:05 | Mohammed Fayaz | QA | Skywalker | No |  |  | Yes | Balanced | 3 | 4 | 4 | 4 | Yes | 4 | 4 | Individual | 4 | 4 | Yes | 4 | YES | Moderate | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Some Information but still need further details | Yes | Average | Code Freeze Milestones and hardening phase | Sprint Planning | KT and recording repository | Blocking Scope change | None | Ad-hoc Tasks & improper prioritisation | More Than 5% but less than 10% |  | YES | no
2024-08-14 17:12 | Jegadeesh Santhana Krishnan | Others | Individual Capacity, Not Associated with any particular team | Yes | 20% to 30% | Yes | No
2024-08-14 17:39 | Jegadeesh Santhana Krishnan | Dev & Scrum Master | Hercules | Yes | 10% or below | Yes | Yes | Balanced | 3 | 3 | 4 | 3 | Yes | 4 | 4 | Individual | 4 | 3 | Yes | 3 | YES | Multiple | Less than 10% | Yes | None | Balanced (80% - 90%) | Optimal information available | Yes | Average | Continuous Epic Grooming | Sprint Closure/review | CI/CD, Testing & Continuous planning | Risk call out during Weekly SoS | Release Planning, Strategy & Schedule (Proper Checkpoint and dates on jira tickets) | Improper Epic Breakdown & Estimations - Missing Sprint Backlog | My role involves process improvement and enablement (EM's, SM's & Other folks responsible for process streamlining) |  | YES | N/A
2024-08-14 17:46 | Jegadeesh Santhana Krishnan | Dev | Echo | Yes | 20% to 30% | Yes | Yes | Well Managed | 5 | 5 | 5 | 5 | Yes | 4 | 4 | Individual | 5 | 4 | No |  | YES | Multiple | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Not aware of any such initiative. Though the release coordination among teams was better than previous releases among teams | Well Managed | Code Freeze Milestones and hardening phase | Sprint Planning | Ad-hoc requests prioritisation and acceptance | Risk call out during Weekly SoS | Efficient Jira Usage (New Fields such as - Due date, QA Lead, QA Involvement, QA Signoff date) | CS Bugs higher than the reserved Capacity | More Than 5% but less than 10% |  | YES | It went pretty well
2024-08-14 18:19 | Jegadeesh Santhana Krishnan | Dev | Aurora | Yes | 20% to 30% | Yes | No
2024-08-14 19:31 | Mohammed Fayaz | QA | Gryffindor | Yes | 10% to 20% | Yes | Yes | Balanced | 4 | 4 | 4 | 4 | Partially/Incomplete | 3 | 4 | Scrum Team | 3 | 2 | Yes | 3 | Moderately | Moderate | 20% to 30% | No | Moderate | Over Utilised (90% and Above) | Some Information but still need further details | Yes | Average | Monitoring and Controlling Progress | Sprint Closure/review | Non Release Activity Identification & capacity reserve | Change in Due date and QA Sign off Date restrictions | Sprint Planning Structure | PR Merges | More Than 5% but less than 10% |  | YES | Due date adherence is being missed drastically. There is no monitoring on this delay. Also, no proper risk analysis for any such trackers which deviates from the planned dates. This is causing issues with QA planning and cascading the impact for release over release.
2024-08-14 19:42 | Sandeep Kumar | Dev & Scrum Master | Phi | Yes | 10% to 20% | No | Yes | Balanced | 4 | 4 | 4 | 4 | Yes | 4 | 3 | Individual | 4 | 4 | Yes | 4 | YES | Moderate | 20% to 30% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Average | Monitoring and Controlling Progress | Sprint Planning | Non Release Activity Identification & capacity reserve | Change in Due date and QA Sign off Date restrictions | Better Estimations & Epic Breakdown | Ad-hoc Tasks & improper prioritisation | More Than 5% but less than 10% |  | Not Efficiently | NA
2024-08-14 20:16 | Jegadeesh Santhana Krishnan | EM | Skywalker | Yes | 20% to 30% | Yes | Yes | Well Managed | 4 | 5 | 5 | 5 | Yes | 5 | 5 | Scrum Team | 5 | 5 | Yes | 5 | YES | Multiple | 20% to 30% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Code Freeze Milestones and hardening phase | Sprint Retrospective | Jira Automation | Risk call out during Weekly SoS | Effective communication | Ad-hoc Tasks & improper prioritisation | My role involves process improvement and enablement (EM's, SM's & Other folks responsible for process streamlining) | NA | YES | NA
2024-08-14 23:03 | Mohammed Fayaz | EM | Chipmuks | Yes | 10% to 20% | Yes | Yes | Balanced | 5 | 5 | 5 | 5 | Partially/Incomplete | 4 | 3 | Individual | 4 | 3 | Yes | 3 | YES | Moderate | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Some Information but still need further details | No | Well Managed | Epic Breakdown | Sprint Planning | Jira Details - Epic breakdown, DoD, Exit criteria, CS Bugs | Change in Due date and QA Sign off Date restrictions | Better & transparent commitments | Missing SLA's for Bugs, Trackers on Jira | My role involves process improvement and enablement (EM's, SM's & Other folks responsible for process streamlining) |  | YES | NA
2024-08-16 09:02 | Jegadeesh Santhana Krishnan | Dev | Helios | Yes | 20% to 30% | Yes | Yes | Well Managed | 4 | 4 | 4 | 5 | Partially/Incomplete | 4 | 4 | Individual | 5 | 5 | Yes | 5 | YES | Moderate | Less than 10% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Epic Breakdown | Sprint Planning | Jira Details - Epic breakdown, DoD, Exit criteria, CS Bugs | Risk call out during Weekly SoS | Better & transparent commitments | Intra team collaboration | Less than 5% |  | YES | -
2024-08-16 09:22 | Jegadeesh Santhana Krishnan | Dev & Scrum Master | Chloris | Yes | 10% to 20% | Yes | Yes | Well Managed | 5 | 5 | 5 | 5 | Yes | 5 | 5 | Individual | 5 | 4 | Yes | 5 | YES | Multiple | Less than 10% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Committed Epic Prioritisation | Sprint Planning | Intra Team Collaboration - Dependency linking on Jira by Individual owners | Blocking Scope change | Efficient Jira Usage (New Fields such as - Due date, QA Lead, QA Involvement, QA Signoff date) | Ad-hoc Tasks & improper prioritisation | My role involves process improvement and enablement (EM's, SM's & Other folks responsible for process streamlining) | NIL | YES | NO
2024-08-16 09:46 | Jegadeesh Santhana Krishnan | Dev | Helios | Yes | 10% to 20% | Yes | Yes | Balanced | 3 | 5 | 5 | 5 | Yes | 5 | 5 | Individual | 5 | 5 | Yes | 5 | YES | Multiple | 10% to 20% | Yes | None | Balanced (80% - 90%) | Optimal information available | Yes | Average | Epic Breakdown | Sprint Planning | Intra Team Collaboration - Dependency linking on Jira by Individual owners | Change in Due date and QA Sign off Date restrictions | None | Intra team collaboration | More Than 5% but less than 10% |  | YES | NA
2024-08-16 10:14 | Jegadeesh Santhana Krishnan | Dev | Iris | Yes | 10% to 20% | Yes | Yes | Well Managed | 5 | 5 | 5 | 5 | Yes | 5 | 5 | Individual | 5 | 5 | Yes | 5 | YES | Multiple | Less than 10% | Yes | Moderate | Over Utilised (90% and Above) | Optimal information available | Yes | Well Managed | Continuous Epic Grooming | Sprint Planning | Non Release Activity Identification & capacity reserve | Change in Due date and QA Sign off Date restrictions | Better Estimations & Epic Breakdown | Modifications on Approved Tech designs | My role involves process improvement and enablement (EM's, SM's & Other folks responsible for process streamlining) |  | YES | NA
2024-08-16 10:24 | Jegadeesh Santhana Krishnan | Dev | Aurora | Yes | 10% to 20% | Yes | No
2024-08-16 10:25 | Sandeep Kumar | QA | Omega | Yes | 10% or below | Yes | Yes | Balanced | 4 | 4 | 4 | 4 | Yes | 4 | 4 | Scrum Team | 5 | 4 | Yes | 5 | NO | None | 10% to 20% | No | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Average | Code Freeze Milestones and hardening phase | Sprint Planning | Tech Design | Strict Bug SLA's | None | Ad-hoc Tasks & improper prioritisation | More than 10% but Less than 20% |  | YES | Improve sprint palnning and Adhoc reaquest planning needed
2024-08-16 10:29 | Jegadeesh Santhana Krishnan | Dev | Iris | Yes | 20% to 30% | Yes | Yes | Well Managed | 4 | 4 | 4 | 4 | Yes | 4 | 4 | Individual | 4 | 3 | Yes | 4 | YES | Moderate | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Continuous Epic Grooming | Sprint Closure/review | Jira Details - Epic breakdown, DoD, Exit criteria, CS Bugs | Strict Bug SLA's | Better & transparent commitments | Reviews | More Than 5% but less than 10% |  | YES | No
2024-08-16 10:30 | Jegadeesh Santhana Krishnan | Dev & Scrum Master | Pheonix | Yes | 10% or below | Yes | Yes | Balanced | 3 | 5 | 5 | 5 | Yes | 4 | 5 | Individual | 5 | 4 | Yes | 4 | YES | Moderate | Less than 10% | Yes | None | Balanced (80% - 90%) | Some Information but still need further details | Yes | Well Managed | Continuous Epic Grooming | Sprint Closure/review | Jira Automation | Blocking Scope change | Reduced over commit | Intra team collaboration | More Than 5% but less than 10% |  | YES | NA
2024-08-16 10:30 | Jegadeesh Santhana Krishnan | Dev | Aurora | Yes | 10% to 20% | Yes | Yes | Well Managed | 3 | 4 | 5 | 5 | Yes | 5 | 3 | Individual | 5 | 3 | No |  | YES | Multiple | 20% to 30% | Yes | Moderate | Balanced (80% - 90%) | Some Information but still need further details | Not aware and did not find any significant change in the release coordination among teams | Average | Monitoring and Controlling Progress | Sprint Planning | Intra Team Collaboration - Dependency linking on Jira by Individual owners | Risk call out during Weekly SoS | Better Estimations & Epic Breakdown | Delayed Response on open Queries, need multiple followups | Less than 5% |  | YES | No
2024-08-16 10:33 | Sandeep Kumar | Dev | Zeta | Yes | 30% and Above | Yes | Yes | Chaotic | 3 | 3 | 3 | 4 | Yes | 4 | 3 | Individual | 3 | 3 | Yes | 5 | YES | Moderate | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Not Well | Epic Breakdown | Sprint Retrospective | KT and recording repository | Change in Due date and QA Sign off Date restrictions | Work allocation with sufficient capacity reserve | PR Merges | More Than 5% but less than 10% |  | YES | none
2024-08-16 10:35 | Jegadeesh Santhana Krishnan | EM | Chloris | Yes | Just started using AI, need time to quantify | Yes | Yes | Well Managed | 5 | 5 | 5 | 5 | Yes | 5 | 4 | Individual | 5 | 4 | Yes | 4 | YES | Multiple | 10% to 20% | Yes | None | Balanced (80% - 90%) | Optimal information available | Yes | Average | Code Freeze Milestones and hardening phase | Sprint Closure/review | Jira Details - Epic breakdown, DoD, Exit criteria, CS Bugs | Change in Due date and QA Sign off Date restrictions | Better Estimations & Epic Breakdown | Delayed Response on open Queries, need multiple followups | My role involves process improvement and enablement (EM's, SM's & Other folks responsible for process streamlining) |  | YES | Dependency with other teams should be managed well
2024-08-16 10:35 | Jegadeesh Santhana Krishnan | Dev | Iris | Yes | 10% to 20% | Yes | Yes | Balanced | 3 | 5 | 5 | 5 | Yes | 5 | 4 | Individual | 5 | 3 | Yes | 4 | YES | Moderate | 10% to 20% | Yes | Moderate | Over Utilised (90% and Above) | Optimal information available | Yes | Well Managed | Code Freeze Milestones and hardening phase | Sprint DSU's | Jira Details - Epic breakdown, DoD, Exit criteria, CS Bugs | Blocking Scope change | Better & transparent commitments | Ad-hoc Tasks & improper prioritisation | More Than 5% but less than 10% |  | YES | No
2024-08-16 10:38 | Jegadeesh Santhana Krishnan | Dev | Helios | Yes | 20% to 30% | Yes | No
2024-08-16 10:41 | Jegadeesh Santhana Krishnan | Dev | Iris | Yes | 10% or below | Yes | Yes | Balanced | 4 | 4 | 4 | 4 | Yes | 4 | 5 | Individual | 5 | 5 | Yes | 5 | YES | Moderate | 10% to 20% | Yes | None | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Monitoring and Controlling Progress | Sprint Closure/review | Bugs Management & Deferring | Strict Bug SLA's | Effective communication | Ad-hoc Tasks & improper prioritisation | More Than 5% but less than 10% |  | YES | no
2024-08-16 10:41 | Jegadeesh Santhana Krishnan | EM | Aurora | Yes | 30% and Above | Yes | Yes | Well Managed | 5 | 5 | 5 | 5 | Yes | 5 | 5 | Individual | 5 | 5 | Yes | 5 | YES | Multiple | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Some Information but still need further details | Yes | Well Managed | Continuous Epic Grooming | Sprint Retrospective | KT and recording repository | Risk call out during Weekly SoS | Efficient Jira Usage (New Fields such as - Due date, QA Lead, QA Involvement, QA Signoff date) | Intra team collaboration | My role involves process improvement and enablement (EM's, SM's & Other folks responsible for process streamlining) |  | YES | No
2024-08-16 10:41 | Jegadeesh Santhana Krishnan | EM | Individual Capacity, Not Associated with any particular team | No |  |  | Yes | Well Managed | 5 | 5 | 5 | 5 | Yes | 5 | 5 | Individual | 5 | 5 | Yes | 5 | YES | Multiple | Less than 10% | Yes | None | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Continuous Epic Grooming | Sprint Planning | Backlog & CS bugs prioritisation | Risk call out during Weekly SoS | Better & transparent commitments | Improper Epic Breakdown & Estimations - Missing Sprint Backlog | My role involves process improvement and enablement (EM's, SM's & Other folks responsible for process streamlining) |  | YES | NO
2024-08-16 10:51 | Jegadeesh Santhana Krishnan | Dev | Chloris | Yes | 20% to 30% | Yes | Yes | Balanced | 4 | 5 | 4 | 5 | Yes | 5 | 4 | Individual | 4 | 4 | Yes | 4 | YES | Moderate | 10% to 20% | Yes | Moderate | Over Utilised (90% and Above) | Some Information but still need further details | Yes |  | Committed Epic Prioritisation | Sprint Closure/review | Ad-hoc requests prioritisation and acceptance | Blocking Scope change | Better & transparent commitments | Ad-hoc Tasks & improper prioritisation | Less than 5% |  | YES | -
2024-08-16 11:10 | Jegadeesh Santhana Krishnan | Dev & Scrum Master | Eirene | Yes | 10% or below | Yes | Yes | Balanced | 4 | 5 | 3 | 5 | Yes | 5 | 4 | Individual | 4 | 4 | Yes | 4 | YES | Moderate | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Some Information but still need further details | Yes | Average | Continuous Epic Grooming | Sprint Planning | Jira Details - Epic breakdown, DoD, Exit criteria, CS Bugs | Blocking Scope change | Release Planning, Strategy & Schedule (Proper Checkpoint and dates on jira tickets) | Modifications on Approved Tech designs | My role involves process improvement and enablement (EM's, SM's & Other folks responsible for process streamlining) |  | YES | na
2024-08-16 11:11 | Sandeep Kumar | Dev | Omega | Yes | 10% or below | Yes | Yes | Well Managed | 4 | 4 | 4 | 4 | Partially/Incomplete | 3 | 4 | Individual | 4 | 3 | Yes | 4 | Moderately | None | Less than 10% | No | Moderate | Over Utilised (90% and Above) | Some Information but still need further details | Yes | Average | Epic Breakdown | Sprint Planning | Backlog & CS bugs prioritisation | Blocking Scope change | Dependency management | Ad-hoc Tasks & improper prioritisation | More than 10% but Less than 20% |  | YES | NA
2024-08-16 11:15 | Jegadeesh Santhana Krishnan | Dev | Pheonix | Yes | 10% to 20% | Yes | Yes | Balanced | 4 | 4 | 3 | 4 | Yes | 4 | 4 | Individual | 4 | 4 | Yes | 4 | YES | Moderate | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Not aware of any such initiative. Though the release coordination among teams was better than previous releases among teams | Well Managed | Continuous Epic Grooming | Sprint Planning | Intra Team Collaboration - Dependency linking on Jira by Individual owners | Blocking Scope change | Sprint Planning Structure | Modifications on Approved Tech designs | More Than 5% but less than 10% |  | YES | N/A
2024-08-16 11:26 | Jegadeesh Santhana Krishnan | Dev | Hercules | Yes | 20% to 30% | Yes | No
2024-08-16 11:26 | Jegadeesh Santhana Krishnan | Dev | Hercules | Yes | 10% or below | Yes | No
2024-08-16 11:28 | Jegadeesh Santhana Krishnan | Dev & Scrum Master | Dexter | Yes | 10% to 20% | Yes | Yes | Balanced | 5 | 4 | 5 | 4 | Yes | 4 | 4 | Individual | 5 | 4 | No |  | YES | Multiple | 10% to 20% | No | Multiple | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Committed Epic Prioritisation | Sprint Closure/review | KT and recording repository | Blocking Scope change | Reduced over commit | Ad-hoc Tasks & improper prioritisation | My role involves process improvement and enablement (EM's, SM's & Other folks responsible for process streamlining) |  | YES | More process pipelines to tackle different types of issues faced by all dev/qa
2024-08-16 12:00 | Sandeep Kumar | Dev | Omega | Yes | 20% to 30% | No | Yes | Balanced | 3 | 3 | 3 | 3 | Yes | 2 | 3 | SME/Epic Owner/EM/QM (Pre Defined Efforts Estimates) | 3 | 3 | Yes | 3 | YES | Moderate | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Not aware of any such initiative. Though the release coordination among teams was better than previous releases among teams | Well Managed | Committed Epic Prioritisation | Sprint Planning | KT and recording repository | Change in Due date and QA Sign off Date restrictions | Work allocation with sufficient capacity reserve | Ad-hoc Tasks & improper prioritisation | More than 10% but Less than 20% |  | YES | Better prioritisation of important deliverables
2024-08-16 12:02 | Jegadeesh Santhana Krishnan | Dev | Tintin | Yes | 10% to 20% | Yes | Yes | Balanced |  |  |  |  | Yes |  |  | Individual |  |  | Yes | 4 | YES | Moderate | 10% to 20% | Yes |  |  | Some Information but still need further details | Yes |  | Monitoring and Controlling Progress | Sprint Planning | Intra Team Collaboration - Dependency linking on Jira by Individual owners | Risk call out during Weekly SoS | Better & transparent commitments | Missing SLA's for Bugs, Trackers on Jira | Less than 5% |  | YES | No
2024-08-16 12:09 | Mujtaba Ahmad | Dev | Apollo | Yes | 20% to 30% | Yes | Yes | Balanced | 4 | 5 | 5 | 4 | Yes | 4 | 5 | Scrum Team | 5 | 5 | Yes | 5 | YES | Multiple | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Committed Epic Prioritisation | Sprint Planning | Non Release Activity Identification & capacity reserve | Blocking Scope change | Efficient Jira Usage (New Fields such as - Due date, QA Lead, QA Involvement, QA Signoff date) | Non Release Activities | More Than 5% but less than 10% |  | YES | NA
2024-08-16 15:52 | Jegadeesh Santhana Krishnan | Dev & Scrum Master | Sharks | Yes | 10% or below | Yes | Yes | Well Managed | 5 | 5 | 5 | 5 | Yes | 5 | 5 | SME/Epic Owner/EM/QM (Pre Defined Efforts Estimates) | 5 | 5 | Yes | 5 | YES | Moderate | Less than 10% | Yes | Moderate | Over Utilised (90% and Above) | Optimal information available | Yes | Well Managed | Monitoring and Controlling Progress | Sprint Closure/review | Intra Team Collaboration - Dependency linking on Jira by Individual owners | Risk call out during Weekly SoS | None | Intra team collaboration | My role involves process improvement and enablement (EM's, SM's & Other folks responsible for process streamlining) |  | YES | na
2024-08-16 16:35 | Mujtaba Ahmad | Dev | Apollo | Yes | 10% to 20% | No | Yes | Balanced | 4 | 4 | 4 | 4 | Yes | 3 | 3 | Scrum Team | 3 | 3 | Yes | 3 | YES | Moderate | 20% to 30% | Yes | Moderate | Over Utilised (90% and Above) | Some Information but still need further details | Yes | Well Managed | Epic Breakdown | Sprint Planning | Jira Details - Epic breakdown, DoD, Exit criteria, CS Bugs | Risk call out during Weekly SoS | Better Estimations & Epic Breakdown | Partial or missing details on Jira Trackers Description | Less than 5% |  | YES | no
2024-08-16 18:39 | Jegadeesh Santhana Krishnan | Dev | Chipmuks | Yes | 10% to 20% | Yes | Yes | Balanced | 4 | 5 | 4 | 4 | Yes | 5 | 5 | Scrum Team | 4 | 3 | Yes | 4 | YES | Moderate | 10% to 20% | No | Moderate | Balanced (80% - 90%) | Some Information but still need further details | Yes | Well Managed | Committed Epic Prioritisation | Sprint Planning | Bugs Management & Deferring | Blocking Scope change | Better & transparent commitments | Ad-hoc Tasks & improper prioritisation | More Than 5% but less than 10% |  | YES | No
2024-08-17 00:04 | Jegadeesh Santhana Krishnan | EM | EM | Yes | 30% and Above | Yes | Yes | Well Managed | 5 | 5 | 5 | 5 | Yes | 5 | 4 | SME/Epic Owner/EM/QM (Pre Defined Efforts Estimates) | 5 | 5 | Yes | 3 | YES | Multiple | Less than 10% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Code Freeze Milestones and hardening phase | Sprint Closure/review | Non Release Activity Identification & capacity reserve | Risk call out during Weekly SoS | Better Estimations & Epic Breakdown | Modifications on Approved Tech designs | My role involves process improvement and enablement (EM's, SM's & Other folks responsible for process streamlining) |  | YES | NA
2024-08-17 21:30 | Jegadeesh Santhana Krishnan | Dev | Dexter | Yes | 10% or below | Yes | Yes | Balanced |  |  |  |  | Yes |  |  | Scrum Team |  |  | Yes | 4 | YES | Moderate | Less than 10% | Yes |  |  | Optimal information available | Not aware of any such initiative. Though the release coordination among teams was better than previous releases among teams |  | Code Freeze Milestones and hardening phase | Sprint Planning | Backlog & CS bugs prioritisation | Risk call out during Weekly SoS | Sprint Planning Structure | PR Merges | Less than 5% |  | YES | NA
2024-08-18 11:55 | Mohammed Fayaz | QA | Stark | No |  |  | Yes | Chaotic | 4 | 3 | 5 | 4 | Yes | 5 | 3 | Individual | 4 | 3 | Yes | 4 | Moderately | Multiple | 20% to 30% | No | Multiple | Over Utilised (90% and Above) | Some Information but still need further details | Yes | Well Managed | Committed Epic Prioritisation | Sprint Closure/review | Ad-hoc requests prioritisation and acceptance | Change in Due date and QA Sign off Date restrictions | Effective communication | Ad-hoc Tasks & improper prioritisation | More than 20% |  | YES | NA
2024-08-19 08:56 | Jegadeesh Santhana Krishnan | Dev | Dexter | Yes | 10% to 20% | Yes | Yes | Well Managed | 4 | 5 | 5 | 4 | Yes | 4 |  | Scrum Team | 3 | 3 | Yes | 5 | Moderately | Moderate | Less than 10% | No | Moderate | Over Utilised (90% and Above) | Optimal information available | Yes | Average | Monitoring and Controlling Progress | Sprint Closure/review | Backlog & CS bugs prioritisation | Blocking Scope change | Sprint Planning Structure | Ad-hoc Tasks & improper prioritisation | Less than 5% |  | YES | None as of now
2024-08-19 09:57 | Jegadeesh Santhana Krishnan | Dev | Eirene | Yes | 20% to 30% | Yes | Yes | Well Managed | 5 | 5 | 5 | 5 | Yes | 5 | 5 | Individual | 5 | 5 | Yes | 5 | YES | Multiple | Less than 10% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Committed Epic Prioritisation | Sprint Planning | Tech Design | Change in Due date and QA Sign off Date restrictions | Effective communication | Improper Epic Breakdown & Estimations - Missing Sprint Backlog | Less than 5% |  | YES | No
2024-08-19 10:34 | Jegadeesh Santhana Krishnan | Dev | Chipmuks | Yes | 10% to 20% | Yes | Yes | Well Managed | 5 | 5 | 5 | 5 | Yes | 5 | 4 | Scrum Team | 4 | 4 | Yes | 5 | YES | Multiple | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Continuous Epic Grooming | Sprint Planning | Ad-hoc requests prioritisation and acceptance | Strict Bug SLA's | None | PR Merges | More Than 5% but less than 10% |  | YES | no
2024-08-19 10:55 | Jegadeesh Santhana Krishnan | Dev & Scrum Master | Echo | Yes | 10% or below | Yes | Yes | Balanced | 3 | 3 | 4 | 4 | Yes | 4 | 4 | Scrum Team | 4 | 4 | Yes | 4 | YES | Moderate | More than 30% | Yes | Multiple | Balanced (80% - 90%) | Some Information but still need further details | Yes | Average | Epic Breakdown | Sprint DSU's | Non Release Activity Identification & capacity reserve | Risk call out during Weekly SoS | Better Estimations & Epic Breakdown | Reviews | More than 20% |  | YES | NA
2024-08-19 11:00 | Jegadeesh Santhana Krishnan | Dev | Dexter | Yes | 10% to 20% | Yes | No
2024-08-19 11:54 | Mujtaba Ahmad | Dev | Chakra | Yes | 10% or below | Yes | Yes | Balanced | 3 | 3 | 3 | 4 | Partially/Incomplete | 4 | 4 | Scrum Team | 4 | 4 | Yes | 5 | YES | Moderate | Less than 10% | Yes | Moderate | Over Utilised (90% and Above) | Some Information but still need further details | Not aware of any such initiative. Though the release coordination among teams was better than previous releases among teams | Average | Epic Breakdown | Sprint Planning | Test Design | Blocking Scope change | None | Improper Epic Breakdown & Estimations - Missing Sprint Backlog | More Than 5% but less than 10% |  | YES | -
2024-08-19 12:11 | Mujtaba Ahmad | EM | Falcon and Indus | Yes | 30% and Above | Yes | Yes | Balanced | 4 | 4 | 4 | 4 | Partially/Incomplete | 4 | 4 | Scrum Team | 4 | 4 | Yes | 4 | YES | Moderate | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Average | Continuous Epic Grooming | Sprint Planning | Ad-hoc requests prioritisation and acceptance | Risk call out during Weekly SoS | None | CS Bugs higher than the reserved Capacity | My role involves process improvement and enablement (EM's, SM's & Other folks responsible for process streamlining) |  | YES | NA
2024-08-19 12:18 | Jegadeesh Santhana Krishnan | Dev | Chloris | No |  |  | Yes | Chaotic | 3 | 4 | 5 | 4 | Partially/Incomplete | 3 | 3 | Individual | 5 | 4 | Yes | 5 | YES | Moderate | Less than 10% | No | Moderate | Over Utilised (90% and Above) | Some Information but still need further details | Not aware and did not find any significant change in the release coordination among teams | Average | Monitoring and Controlling Progress | Sprint Planning | Jira Details - Epic breakdown, DoD, Exit criteria, CS Bugs | Blocking Scope change | Risk call out (Release Confluence Page) | Reviews | Less than 5% |  | YES | No
2024-08-19 12:26 | Jegadeesh Santhana Krishnan | Dev | Eirene | Yes | 10% or below | Yes | Yes | Balanced | 3 | 3 | 3 | 3 | Yes | 3 | 3 | Individual | 3 | 3 | Yes | 3 | YES | Moderate | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Average | Committed Epic Prioritisation | Sprint Planning | Jira Details - Epic breakdown, DoD, Exit criteria, CS Bugs | Risk call out during Weekly SoS | Better Estimations & Epic Breakdown | Intra team collaboration | Less than 5% |  | YES | no
2024-08-19 12:27 | Jegadeesh Santhana Krishnan | Dev | Skywalker | Yes | Just started using AI, need time to quantify | No | No
2024-08-19 12:29 | Jegadeesh Santhana Krishnan | Dev | Chipmuks | Yes | 10% to 20% | Yes | Yes | Well Managed | 4 | 4 | 4 | 5 | Yes | 5 | 5 | Scrum Team | 5 | 4 | Yes | 5 | YES | Multiple | Less than 10% | Yes | None | Balanced (80% - 90%) | Optimal information available | Not aware of any such initiative. Though the release coordination among teams was better than previous releases among teams | Well Managed | Committed Epic Prioritisation | Sprint Planning | KT and recording repository | Blocking Scope change | Better Estimations & Epic Breakdown | Modifications on Approved Tech designs | Less than 5% |  | YES | -
2024-08-19 12:30 | Mohammed Fayaz | QA | Dexter | Yes | Just started using AI, need time to quantify | Yes | Yes | Balanced | 4 | 4 | 4 | 4 | Yes | 4 | 5 | Scrum Team | 4 | 4 | Yes | 4 | YES | Moderate | Less than 10% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Epic Breakdown | Sprint Planning | Jira Details - Epic breakdown, DoD, Exit criteria, CS Bugs | Change in Due date and QA Sign off Date restrictions | Effective communication | Improper Epic Breakdown & Estimations - Missing Sprint Backlog | Less than 5% |  | YES | NA
2024-08-19 12:31 | Mujtaba Ahmad | Dev & Scrum Master | Falcon | Yes | 10% to 20% | Yes | Yes | Balanced | 4 | 4 | 4 | 4 | Yes | 4 | 4 | Scrum Team | 5 | 4 | Yes | 4 | YES | Moderate | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Some Information but still need further details | Yes | Average | Epic Breakdown | Sprint Planning | KT and recording repository | Change in Due date and QA Sign off Date restrictions | Sprint Planning Structure | Ad-hoc Tasks & improper prioritisation | More than 10% but Less than 20% |  | YES | We need to have better estimates of trackers
2024-08-19 12:32 | Jegadeesh Santhana Krishnan | Dev | Tintin | Yes | 10% to 20% | Yes | Yes | Balanced | 5 | 5 | 4 | 5 | Yes | 5 | 4 | Individual | 4 | 4 | Yes | 4 | Moderately | Moderate | 20% to 30% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Continuous Epic Grooming | Sprint Planning | Backlog & CS bugs prioritisation | Risk call out during Weekly SoS | Better Estimations & Epic Breakdown | PR Merges | More Than 5% but less than 10% |  | YES | na
2024-08-19 12:33 | Mujtaba Ahmad | Dev & Scrum Master | Invincibles | Yes | 10% to 20% | Yes | Yes | Balanced | 4 | 5 | 5 | 5 | Partially/Incomplete | 5 | 4 | Scrum Team | 5 | 5 | Yes | 5 | YES | Multiple | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Monitoring and Controlling Progress | Sprint DSU's | CI/CD, Testing & Continuous planning | Blocking Scope change | Effective communication | Modifications on Approved Tech designs | My role involves process improvement and enablement (EM's, SM's & Other folks responsible for process streamlining) |  | YES | NA
2024-08-19 12:36 | Mohammed Fayaz | QA | Chipmuks | No |  |  | Yes | Balanced | 4 | 4 | 4 | 4 | Yes | 4 | 4 | Scrum Team | 4 | 4 | Yes | 4 | Moderately | Moderate | Less than 10% | Yes | Moderate | Balanced (80% - 90%) | Some Information but still need further details | Yes | Average | Code Freeze Milestones and hardening phase | Sprint Planning | Jira Details - Epic breakdown, DoD, Exit criteria, CS Bugs | Change in Due date and QA Sign off Date restrictions | Better Estimations & Epic Breakdown | Delay in commitments from dependant team | More Than 5% but less than 10% |  | YES | NA
2024-08-19 12:38 | Sandeep Kumar | Dev | Iota | Yes | 10% or below | No | Yes | Balanced | 4 | 3 | 4 | 4 | Yes | 4 | 5 | Scrum Team | 4 | 4 | Yes | 5 | YES | Multiple | 10% to 20% | Yes | Moderate | Over Utilised (90% and Above) | Some Information but still need further details | Not aware and did not find any significant change in the release coordination among teams | Average | Committed Epic Prioritisation | Sprint Planning | Intra Team Collaboration - Dependency linking on Jira by Individual owners | Risk call out during Weekly SoS | Release Planning, Strategy & Schedule (Proper Checkpoint and dates on jira tickets) | Modifications on Approved Tech designs | More than 10% but Less than 20% |  | YES | NA
2024-08-19 12:39 | Jegadeesh Santhana Krishnan | Dev | Skywalker | Yes | 10% to 20% | Yes | Yes | Balanced | 4 | 4 | 4 | 4 | Yes | 4 | 2 | Individual | 5 | 3 | Yes | 3 | YES | Moderate | Less than 10% | Yes | None | Over Utilised (90% and Above) | Optimal information available | Yes | Well Managed | Committed Epic Prioritisation | Sprint Planning | Ad-hoc requests prioritisation and acceptance | Blocking Scope change | None | Reviews | Less than 5% |  | Not Efficiently | None
2024-08-19 12:40 | Sandeep Kumar | EM | Transformer, Leo, Dynamos | No |  |  | Yes | Well Managed | 5 | 5 | 5 | 5 | Yes | 5 | 5 | Individual | 5 | 5 | Yes | 5 | YES | Multiple | 10% to 20% | Yes | None | Over Utilised (90% and Above) | Some Information but still need further details | Yes | Well Managed | Code Freeze Milestones and hardening phase | Sprint Closure/review | Jira Details - Epic breakdown, DoD, Exit criteria, CS Bugs | Strict Bug SLA's | Release Planning, Strategy & Schedule (Proper Checkpoint and dates on jira tickets) | Intra team collaboration | My role involves process improvement and enablement (EM's, SM's & Other folks responsible for process streamlining) |  | YES | .
2024-08-19 12:41 | Mohammed Fayaz | QA | E2E | Yes | 20% to 30% | Yes | Yes | Balanced | 4 | 4 | 4 | 4 | Yes | 4 | 4 | Individual | 4 | 4 | No |  | YES | Multiple | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Average | Committed Epic Prioritisation | Sprint Planning | KT and recording repository | Risk call out during Weekly SoS | Better Estimations & Epic Breakdown | Delay in commitments from dependant team | More Than 5% but less than 10% | NA | YES | Better planning and not hurrying on things. Having sufficient buffer time.
2024-08-19 12:41 | Krishna Kishore Mothukuri | Dev | Velocity | Yes | 10% to 20% | Yes | Yes | Balanced | 4 | 4 | 4 | 5 | Yes | 5 | 5 | Individual | 5 | 5 | Yes | 5 | YES | Multiple | 20% to 30% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Epic Breakdown | Sprint Planning | Jira Details - Epic breakdown, DoD, Exit criteria, CS Bugs | Blocking Scope change | Release Planning, Strategy & Schedule (Proper Checkpoint and dates on jira tickets) | Improper Epic Breakdown & Estimations - Missing Sprint Backlog | More Than 5% but less than 10% |  | Not Efficiently | Proper Epic Breakdown
2024-08-19 12:45 | Sandeep Kumar | Dev | Tranformers | Yes | 20% to 30% | No | Yes | Chaotic | 1 | 2 | 3 | 3 | Partially/Incomplete | 1 | 3 | Scrum Team | 3 | 3 | Yes | 3 | Moderately | Moderate | More than 30% | Yes | Multiple | Balanced (80% - 90%) | Some Information but still need further details | Not aware and did not find any significant change in the release coordination among teams | Average | Continuous Epic Grooming | Sprint Closure/review | Intra Team Collaboration - Dependency linking on Jira by Individual owners | Risk call out during Weekly SoS | None | Non Release Activities | More than 20% |  | Not Efficiently | no
2024-08-19 12:46 | Krishna Kishore Mothukuri | Dev | Velocity | Yes | 10% to 20% | Yes | Yes | Balanced | 4 | 5 | 5 | 5 | Yes | 5 | 4 | Individual | 4 | 4 | Yes | 5 | YES | Moderate | 10% to 20% | Yes | None | Balanced (80% - 90%) | Optimal information available | Yes | Not Well | Code Freeze Milestones and hardening phase | Sprint Closure/review | Intra Team Collaboration - Dependency linking on Jira by Individual owners | Risk call out during Weekly SoS | Efficient Jira Usage (New Fields such as - Due date, QA Lead, QA Involvement, QA Signoff date) | Delayed Test Designs | Less than 5% |  | YES | N/A
2024-08-19 12:46 | Sandeep Kumar | Dev | Leo | Yes | 20% to 30% | Yes | Yes | Balanced | 3 | 3 | 3 | 4 | Yes | 4 | 4 | Individual | 4 | 3 | Yes | 2 | YES | Moderate | 20% to 30% | Yes | Moderate | Balanced (80% - 90%) | Some Information but still need further details | Yes | Well Managed | Epic Breakdown | Sprint Planning | Bugs Management & Deferring | Risk call out during Weekly SoS | None | Reviews | Less than 5% |  | YES | NA
2024-08-19 12:49 | Jegadeesh Santhana Krishnan | Dev & Scrum Master | Skywalker | Yes | 10% to 20% | Yes | Yes | Balanced | 4 | 3 | 4 | 3 | Yes | 4 | 3 | Individual | 4 | 3 | Yes | 4 | YES | Multiple | 20% to 30% | Yes | Moderate | Balanced (80% - 90%) | Some Information but still need further details | Not aware of any such initiative. Though the release coordination among teams was better than previous releases among teams | Well Managed | Continuous Epic Grooming | Sprint Closure/review | Ad-hoc requests prioritisation and acceptance | Blocking Scope change | Release Planning, Strategy & Schedule (Proper Checkpoint and dates on jira tickets) | Ad-hoc Tasks & improper prioritisation | More Than 5% but less than 10% | None | YES | None
2024-08-19 12:50 | Jegadeesh Santhana Krishnan | Dev | Skywalker | Yes | Just started using AI, need time to quantify | Yes | Yes | Balanced | 4 | 4 | 4 | 4 | Yes | 4 | 4 | Scrum Team | 4 | 4 | Yes | 4 | YES | Moderate | Less than 10% | Yes | None | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Committed Epic Prioritisation | Sprint Planning | Ad-hoc requests prioritisation and acceptance | Change in Due date and QA Sign off Date restrictions | Dependency management | Reviews | Less than 5% |  | YES | NA
2024-08-19 12:51 | Jegadeesh Santhana Krishnan | Dev | Helios | Yes | 10% to 20% | Yes | Yes | Well Managed | 4 | 4 | 4 | 4 | Yes | 4 | 3 | Individual | 5 | 4 | Yes | 4 | YES | Moderate | 20% to 30% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Continuous Epic Grooming | Sprint Planning | Intra Team Collaboration - Dependency linking on Jira by Individual owners | Blocking Scope change | Release Planning, Strategy & Schedule (Proper Checkpoint and dates on jira tickets) | Intra team collaboration | Less than 5% |  | YES | NA
2024-08-19 12:53 | Mohammed Fayaz | QA | Tintin | Yes | 20% to 30% | Yes | Yes | Balanced | 5 | 5 | 5 | 5 | Yes | 5 | 5 | Scrum Team | 5 | 5 | Yes | 5 | YES | None | Less than 10% | Yes | Multiple | Over Utilised (90% and Above) | Some Information but still need further details | Yes | Well Managed | Epic Breakdown | Sprint Closure/review | Intra Team Collaboration - Dependency linking on Jira by Individual owners | Blocking Scope change | Release Planning, Strategy & Schedule (Proper Checkpoint and dates on jira tickets) | PR Merges | Less than 5% |  | YES | NA
2024-08-19 12:55 | Mujtaba Ahmad | Dev | Invincibles | Yes | 10% or below | Yes | Yes | Balanced | 5 | 5 | 5 | 5 | Yes | 5 | 4 | Scrum Team | 5 | 5 | Yes | 5 | YES | Multiple | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Some Information but still need further details | Yes | Well Managed | Continuous Epic Grooming | Sprint Planning | KT and recording repository | Blocking Scope change | Better Estimations & Epic Breakdown | Modifications on Approved Tech designs | Less than 5% |  | YES | Better knowledge transfer (KT) needs to be documented for complex projects. If new developers are added to the team, we should give them sufficient time to understand the repository managed by the team.
2024-08-19 13:05 | Mohammed Fayaz | QA | Chakra | Yes | 10% or below | Yes | Yes | Well Managed | 5 | 5 | 5 | 5 | Yes | 5 | 5 | Individual |  | 5 | Yes | 5 | YES | Multiple | Less than 10% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Continuous Epic Grooming | Sprint Planning | Jira Details - Epic breakdown, DoD, Exit criteria, CS Bugs | Strict Bug SLA's | Better Estimations & Epic Breakdown | Improper Epic Breakdown & Estimations - Missing Sprint Backlog | More Than 5% but less than 10% |  | YES | No
2024-08-19 13:11 | Sandeep Kumar | Dev & Scrum Master | Iota | Yes | 10% to 20% | Yes | Yes | Balanced | 4 | 5 | 5 | 5 | Yes | 4 | 4 | Scrum Team | 4 | 3 | Yes | 4 | YES | Multiple | 10% to 20% | Yes | None | Balanced (80% - 90%) | Some Information but still need further details | Yes | Well Managed | Continuous Epic Grooming | Sprint Closure/review | Tech Design | Blocking Scope change | Better Estimations & Epic Breakdown | CS Bugs higher than the reserved Capacity | My role involves process improvement and enablement (EM's, SM's & Other folks responsible for process streamlining) |  | YES | NA
2024-08-19 13:18 | Jegadeesh Santhana Krishnan | Dev | Skywalker | Yes | 20% to 30% | Yes | Yes | Well Managed | 5 | 5 | 5 | 5 | Yes | 5 | 4 | Scrum Team | 5 | 5 | No |  | YES | Moderate | Less than 10% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Epic Breakdown | Sprint Planning | Jira Details - Epic breakdown, DoD, Exit criteria, CS Bugs | Strict Bug SLA's | Release Planning, Strategy & Schedule (Proper Checkpoint and dates on jira tickets) | Ad-hoc Tasks & improper prioritisation | More Than 5% but less than 10% |  | YES | N/A
2024-08-19 13:22 | Mohammed Fayaz | QA & Scrum Master | Leo | Yes | 10% or below | Yes | Yes | Well Managed | 5 | 5 | 5 | 5 | Yes | 5 | 5 | Individual | 5 | 5 | Yes | 4 | YES | Moderate | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Continuous Epic Grooming | Sprint Closure/review | KT and recording repository | Strict Bug SLA's | Efficient Jira Usage (New Fields such as - Due date, QA Lead, QA Involvement, QA Signoff date) | Ad-hoc Tasks & improper prioritisation | Less than 5% |  | YES | good
2024-08-19 13:27 | Sandeep Kumar | Dev | Gryffindor | Yes | 10% to 20% | Yes | Yes | Balanced | 4 | 4 | 4 | 4 | Yes | 4 | 4 | Scrum Team | 5 | 3 | Yes | 5 | Moderately | Multiple | 20% to 30% | Yes | Multiple | Balanced (80% - 90%) | Optimal information available | Yes | Average | Monitoring and Controlling Progress | Sprint Closure/review | Bugs Management & Deferring | Risk call out during Weekly SoS | Sprint Planning Structure | Ad-hoc Tasks & improper prioritisation | Less than 5% |  | YES | NA
2024-08-19 13:53 | Sandeep Kumar | EM | Iota | No |  |  | No
2024-08-19 14:07 | Mujtaba Ahmad | Dev | Invincibles | Yes | 10% to 20% | Yes | Yes | Well Managed | 5 | 5 | 5 | 5 | Yes | 5 | 5 | Individual | 5 | 5 | Yes | 5 | YES | Moderate | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Epic Breakdown | Sprint DSU's | CI/CD, Testing & Continuous planning | Risk call out during Weekly SoS | Reduced over commit | Improper Epic Breakdown & Estimations - Missing Sprint Backlog | More than 10% but Less than 20% |  | YES | ‎
2024-08-19 14:29 | Mujtaba Ahmad | Dev | Chakra | No |  |  | Yes | Balanced | 5 | 5 | 5 | 5 | Partially/Incomplete | 5 | 4 | Scrum Team | 5 | 5 | Yes | 5 | YES | Multiple | Less than 10% | Yes | Moderate | Over Utilised (90% and Above) | Optimal information available | Yes | Average | Monitoring and Controlling Progress | Sprint DSU's | Jira Details - Epic breakdown, DoD, Exit criteria, CS Bugs | Change in Due date and QA Sign off Date restrictions | Effective communication | Reviews | Less than 5% |  | YES | -
2024-08-19 14:47 | Jegadeesh Santhana Krishnan | Dev | Helios | Yes | 20% to 30% | Yes | Yes | Balanced | 4 | 4 | 4 | 5 | Yes | 4 | 4 | Individual | 5 | 4 | Yes | 5 | YES | Moderate | Less than 10% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Average | Release Kick Off | Sprint Closure/review | Jira Automation | Blocking Scope change | Better & transparent commitments | Ad-hoc Tasks & improper prioritisation | Less than 5% |  | YES | .
2024-08-19 14:56 | Mohammed Fayaz | QA | Iota | No |  |  | Yes | Balanced | 4 | 4 | 4 | 4 | Yes | 4 | 4 | Individual | 4 | 4 | Yes | 4 | YES | None | Less than 10% | Yes | None | Balanced (80% - 90%) | Optimal information available | Yes | Average | Epic Breakdown | Sprint Closure/review | KT and recording repository | Blocking Scope change | Reduced over commit | Improper Epic Breakdown & Estimations - Missing Sprint Backlog | Less than 5% |  | YES
2024-08-19 15:52 | Sandeep Kumar | Dev | Tranformers | Yes | 10% or below | Yes | Yes | Balanced | 5 | 5 | 5 | 5 | Yes | 5 | 5 | Scrum Team | 5 | 5 | Yes | 5 | YES | Moderate | Less than 10% | Yes | Moderate | Balanced (80% - 90%) | Some Information but still need further details | Yes | Average | Epic Breakdown | Sprint Planning | Tech Design | Blocking Scope change | Release Planning, Strategy & Schedule (Proper Checkpoint and dates on jira tickets) | Ad-hoc Tasks & improper prioritisation | Less than 5% |  | YES | no
2024-08-19 16:19 | Jegadeesh Santhana Krishnan | Dev | Sharks | Yes | 20% to 30% | Yes | Yes | Balanced | 4 | 4 | 4 | 5 | Yes | 3 | 3 | Individual | 5 | 5 | Yes | 4 | YES | Moderate | Less than 10% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Average | Epic Breakdown | Sprint Retrospective | Bugs Management & Deferring | Blocking Scope change | Release Planning, Strategy & Schedule (Proper Checkpoint and dates on jira tickets) | Improper Epic Breakdown & Estimations - Missing Sprint Backlog | More Than 5% but less than 10% |  | Not Efficiently | none
2024-08-19 16:51 | Jegadeesh Santhana Krishnan | Dev & Scrum Master | Tintin | Yes | 10% to 20% | Yes | Yes | Balanced | 5 | 4 | 1 | 5 | Yes | 3 | 3 | SME/Epic Owner/EM/QM (Pre Defined Efforts Estimates) | 5 | 1 | No |  | YES | None | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Some Information but still need further details | Yes | Well Managed | Code Freeze Milestones and hardening phase | Sprint Planning | Tech Design | Change in Due date and QA Sign off Date restrictions | Efficient Jira Usage (New Fields such as - Due date, QA Lead, QA Involvement, QA Signoff date) | Modifications on Approved Tech designs | Less than 5% | This survey has too many questions. Maybe we can weed out the ones where we're consistently getting good feedback. | Not Efficiently | Release related overhead is more. Checklists, merges etc. Either we can do bigger releases, or automate some processes
2024-08-19 19:15 | Jegadeesh Santhana Krishnan | Dev | Chipmuks | Yes | 20% to 30% | Yes | Yes | Well Managed | 5 | 5 | 4 | 4 | Yes | 5 | 5 | Scrum Team | 5 | 5 | Yes | 5 | YES | Multiple | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Epic Breakdown | Sprint Closure/review | Ad-hoc requests prioritisation and acceptance | Blocking Scope change | Release Planning, Strategy & Schedule (Proper Checkpoint and dates on jira tickets) | Intra team collaboration | More than 10% but Less than 20% |  | YES | No suggestions.
2024-08-19 19:16 | Mohammed Fayaz | QA | Ganges | Yes | 10% or below | Yes | Yes | Balanced | 5 | 5 | 5 | 5 | Yes | 5 | 5 | Scrum Team | 5 | 5 | Yes | 5 | YES | Multiple | 10% to 20% | Yes | None | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Epic Breakdown | Sprint Closure/review | Backlog & CS bugs prioritisation | Risk call out during Weekly SoS | Better Estimations & Epic Breakdown | CS Bugs higher than the reserved Capacity | More Than 5% but less than 10% |  | YES | Nothing
2024-08-19 19:55 | Mohammed Fayaz | QA | Dynamos | Yes | Just started using AI, need time to quantify | Yes | No
2024-08-19 20:16 | Jegadeesh Santhana Krishnan | EM | Hercules | Yes | 20% to 30% | Yes | Yes | Well Managed | 5 | 5 | 5 | 5 | Yes | 5 | 5 | Individual | 5 | 5 | Yes | 5 | YES | Moderate | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Code Freeze Milestones and hardening phase | Sprint Retrospective | Intra Team Collaboration - Dependency linking on Jira by Individual owners | Blocking Scope change | None | Partial or missing details on Jira Trackers Description | My role involves process improvement and enablement (EM's, SM's & Other folks responsible for process streamlining) |  | YES | -
2024-08-19 20:23 | Mohammed Fayaz | QA | Helios | No |  |  | Yes | Balanced | 5 | 5 | 5 | 5 | Yes | 5 | 5 | Scrum Team | 5 | 4 | Yes | 4 | YES | None | Less than 10% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Monitoring and Controlling Progress | Sprint Closure/review | Ad-hoc requests prioritisation and acceptance | Blocking Scope change | None | Delayed Response on open Queries, need multiple followups | More Than 5% but less than 10% |  | YES | no
2024-08-19 21:08 | Mujtaba Ahmad | Dev | Stark | Yes | 10% to 20% | Yes | Yes | Balanced | 5 | 5 | 4 | 4 | Yes | 4 | 4 | Scrum Team | 4 | 4 | Yes | 4 | YES | Multiple | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Epic Breakdown | Sprint Planning | Ad-hoc requests prioritisation and acceptance | Blocking Scope change | Better Estimations & Epic Breakdown | Ad-hoc Tasks & improper prioritisation | More Than 5% but less than 10% |  | YES | NA
2024-08-19 21:42 | Sandeep Kumar | EM | Zeta | Yes | 10% to 20% | Yes | Yes | Balanced | 4 | 4 | 5 | 5 | Yes | 5 | 4 | Scrum Team | 5 | 4 | Yes | 5 | YES | Multiple | 20% to 30% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Continuous Epic Grooming | Sprint Planning | Non Release Activity Identification & capacity reserve | Change in Due date and QA Sign off Date restrictions | Work allocation with sufficient capacity reserve | Reviews | My role involves process improvement and enablement (EM's, SM's & Other folks responsible for process streamlining) |  | YES | NA
2024-08-19 22:22 | Mujtaba Ahmad | Dev & Scrum Master | Enigma | No |  |  | Yes | Balanced | 4 | 5 | 5 | 5 | Yes | 4 | 4 | Individual | 5 | 4 | Yes | 5 | YES | Moderate | 10% to 20% | Yes | None | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Epic Breakdown | Sprint Planning | CI/CD, Testing & Continuous planning | Risk call out during Weekly SoS | Better Estimations & Epic Breakdown | Non Release Activities | More Than 5% but less than 10% |  | YES | No
2024-08-20 00:04 | Jegadeesh Santhana Krishnan | Dev | Chloris | Yes | 10% or below | Yes | Yes | Balanced | 4 | 4 | 4 | 4 | Yes | 4 | 4 | Individual | 4 | 4 | Yes | 4 | YES | Moderate | Less than 10% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Not aware of any such initiative. Though the release coordination among teams was better than previous releases among teams | Average | Continuous Epic Grooming | Sprint Closure/review | Test Design | Change in Due date and QA Sign off Date restrictions | Release Planning, Strategy & Schedule (Proper Checkpoint and dates on jira tickets) | Improper Epic Breakdown & Estimations - Missing Sprint Backlog | Less than 5% |  | YES | NA
2024-08-20 09:24 | Sandeep Kumar | Dev | Gryffindor | Yes | 10% to 20% | No | Yes | Balanced | 4 | 4 | 4 | 4 | Yes | 3 | 3 | Individual | 5 | 4 | Yes | 4 | Moderately | Moderate | Less than 10% | No | None | Balanced (80% - 90%) | Optimal information available | Not aware of any such initiative. Though the release coordination among teams was better than previous releases among teams | Average | Monitoring and Controlling Progress | Sprint Planning | CI/CD, Testing & Continuous planning | Change in Due date and QA Sign off Date restrictions | Release Planning, Strategy & Schedule (Proper Checkpoint and dates on jira tickets) | PR Merges | More Than 5% but less than 10% | no | Not Efficiently | no
2024-08-20 09:55 | Jegadeesh Santhana Krishnan | Dev | Chipmuks | Yes | 10% to 20% | Yes | Yes | Balanced | 5 | 5 | 5 | 5 | Yes | 5 | 4 | Scrum Team | 4 | 4 | No |  | YES | Moderate | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Monitoring and Controlling Progress | Sprint Planning | Tech Design | Risk call out during Weekly SoS | Effective communication | Ad-hoc Tasks & improper prioritisation | More Than 5% but less than 10% |  | YES | nil
2024-08-20 10:02 | Mohammed Fayaz | QA | Ganges | Yes | 10% to 20% | Yes | Yes | Balanced | 4 | 4 | 3 | 4 | Partially/Incomplete | 4 | 4 | Scrum Team | 4 | 4 | Yes | 4 | YES | Moderate | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Some Information but still need further details | Yes | Average | Continuous Epic Grooming | Sprint Planning | Jira Details - Epic breakdown, DoD, Exit criteria, CS Bugs | Blocking Scope change | Better & transparent commitments | Improper Epic Breakdown & Estimations - Missing Sprint Backlog | Less than 5% |  | YES | No
2024-08-20 10:25 | Sandeep Kumar | Dev | Iota | Yes | 10% or below | No | Yes | Balanced | 4 | 3 | 3 | 4 | Yes | 4 | 4 | Scrum Team | 4 | 4 | Yes | 4 | Moderately | Moderate | Less than 10% | Yes | Multiple | Balanced (80% - 90%) | Some Information but still need further details | Not aware of any such initiative. Though the release coordination among teams was better than previous releases among teams | Average | Epic Breakdown | Sprint Planning | Jira Details - Epic breakdown, DoD, Exit criteria, CS Bugs | Change in Due date and QA Sign off Date restrictions | Efficient Jira Usage (New Fields such as - Due date, QA Lead, QA Involvement, QA Signoff date) | Ad-hoc Tasks & improper prioritisation | More Than 5% but less than 10% |  | YES | NA
2024-08-20 10:26 | Mujtaba Ahmad | Dev | Ganges | Yes | 10% or below | Yes | Yes | Balanced | 4 | 5 | 5 | 5 | Yes | 4 | 4 | Scrum Team | 4 | 4 | Yes | 5 | YES | Multiple | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Some Information but still need further details | Not aware of any such initiative. Though the release coordination among teams was better than previous releases among teams | Average | Epic Breakdown | Sprint Closure/review | Tech Design | Change in Due date and QA Sign off Date restrictions | Effective communication | Modifications on Approved Tech designs | More Than 5% but less than 10% |  | YES | not for now
2024-08-20 10:29 | Mohammed Fayaz | QA | Skywalker | Yes | 10% or below | Yes | Yes | Balanced | 4 | 4 | 3 | 5 | Yes | 4 | 3 | Individual | 5 | 4 | Yes | 4 | YES | Moderate | Less than 10% | Yes | Moderate | Over Utilised (90% and Above) | Optimal information available | Not aware of any such initiative. Though the release coordination among teams was better than previous releases among teams | Well Managed | Continuous Epic Grooming | Sprint Planning | Jira Details - Epic breakdown, DoD, Exit criteria, CS Bugs | Blocking Scope change | Reduced over commit | Modifications on Approved Tech designs | Less than 5% |  | Not Efficiently | We can avoid over committing
2024-08-20 10:36 | Sandeep Kumar | Dev | Zeta | Yes | 20% to 30% | Yes | Yes | Chaotic | 3 | 5 | 4 | 5 | Yes | 5 | 5 | Scrum Team | 5 | 4 | Yes | 5 | YES | Moderate | Less than 10% | Yes | Moderate | Over Utilised (90% and Above) | Optimal information available | Not aware of any such initiative. Though the release coordination among teams was better than previous releases among teams | Well Managed | Continuous Epic Grooming | Sprint Planning | Jira Details - Epic breakdown, DoD, Exit criteria, CS Bugs | Blocking Scope change | Risk call out (Release Confluence Page) | Non Release Activities | More Than 5% but less than 10% |  | YES | none
2024-08-20 10:53 | Sandeep Kumar | Dev | Sudo | Yes | 10% to 20% | Yes | Yes | Balanced | 4 | 4 | 4 | 4 | Yes | 4 | 4 | Individual | 4 | 4 | Yes | 4 | YES | Multiple | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Epic Breakdown | Sprint Planning | Backlog & CS bugs prioritisation | Strict Bug SLA's | Efficient Jira Usage (New Fields such as - Due date, QA Lead, QA Involvement, QA Signoff date) | PR Merges | More than 10% but Less than 20% |  | YES | NA
2024-08-20 10:53 | Sandeep Kumar | Dev | Iota | Yes | 20% to 30% | No | Yes | Balanced | 4 | 5 | 5 | 4 | Partially/Incomplete | 3 | 3 | Individual | 4 | 2 | Yes | 4 | YES | Moderate | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Some Information but still need further details | Yes | Average | Continuous Epic Grooming | Sprint Closure/review | Tech Design | Change in Due date and QA Sign off Date restrictions | Better & transparent commitments | Improper Epic Breakdown & Estimations - Missing Sprint Backlog | More Than 5% but less than 10% |  | YES | NA
2024-08-20 10:59 | Mujtaba Ahmad | EM | Enigma | No |  |  | Yes | Balanced | 4 | 4 | 5 | 5 | No | 4 | 4 | Scrum Team | 5 | 4 | Yes | 4 | YES | Moderate | Less than 10% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Continuous Epic Grooming | Sprint Planning | Tech Design | Blocking Scope change | Release Planning, Strategy & Schedule (Proper Checkpoint and dates on jira tickets) | Modifications on Approved Tech designs | My role involves process improvement and enablement (EM's, SM's & Other folks responsible for process streamlining) |  | YES | na
2024-08-20 11:02 | Mohammed Fayaz | EM | Individual Capacity, Not Associated with any particular team | Yes | 20% to 30% | Yes | Yes | Balanced | 4 | 5 | 4 | 5 | Partially/Incomplete | 4 | 4 | Scrum Team | 4 | 4 | Yes | 4 | YES | Moderate | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Some Information but still need further details | Yes | Well Managed | Code Freeze Milestones and hardening phase | Sprint Planning | CI/CD, Testing & Continuous planning | Change in Due date and QA Sign off Date restrictions | Effective communication | PR Merges | My role involves process improvement and enablement (EM's, SM's & Other folks responsible for process streamlining) |  | YES | 1. Intermittent tests failures leading to CI failures and causing delays in PR merges. 2. Repo/services dependencies management documentation is missing and caused lot of kiosk during code freeze of Aug release.
2024-08-20 11:09 | Mujtaba Ahmad | Dev | Apollo | Yes | 10% to 20% | Yes | Yes | Chaotic | 3 | 3 | 4 | 4 | Yes | 4 | 4 | Scrum Team | 4 | 4 | Yes | 4 | YES | Moderate | Less than 10% | No | Moderate | Over Utilised (90% and Above) | Optimal information available | Yes | Well Managed | Committed Epic Prioritisation | Sprint Planning | Non Release Activity Identification & capacity reserve | Blocking Scope change | Efficient Jira Usage (New Fields such as - Due date, QA Lead, QA Involvement, QA Signoff date) | PR Merges | Less than 5% |  | YES | We can introduce half sprint buffer for QA vs Dev activities closure.
2024-08-20 11:18 | Sandeep Kumar | Dev | Sudo | Yes | 10% to 20% | Yes | Yes | Balanced | 4 | 4 | 3 | 4 | Yes | 4 | 4 | SME/Epic Owner/EM/QM (Pre Defined Efforts Estimates) | 4 | 2 | Yes | 3 | YES | Moderate | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Code Freeze Milestones and hardening phase | Sprint Closure/review | Ad-hoc requests prioritisation and acceptance | Risk call out during Weekly SoS | Release Planning, Strategy & Schedule (Proper Checkpoint and dates on jira tickets) | Intra team collaboration | More Than 5% but less than 10% |  | YES
2024-08-20 11:19 | Sandeep Kumar | Dev & Scrum Master | Sudo | Yes | 20% to 30% | Yes | Yes | Balanced | 3 | 3 | 3 | 3 | Yes | 3 | 4 | SME/Epic Owner/EM/QM (Pre Defined Efforts Estimates) | 4 | 4 | No |  | YES | Moderate | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Monitoring and Controlling Progress | Sprint Retrospective | Intra Team Collaboration - Dependency linking on Jira by Individual owners | Risk call out during Weekly SoS | Release Planning, Strategy & Schedule (Proper Checkpoint and dates on jira tickets) | Partial or missing details on Jira Trackers Description | More than 10% but Less than 20% |  | YES | NA
2024-08-20 11:31 | Mujtaba Ahmad | Dev | Enigma | Yes | 10% to 20% | Yes | Yes | Balanced | 4 | 5 | 2 | 4 | Yes | 4 | 5 | Scrum Team | 5 | 2 | Yes | 5 | YES | Moderate | Less than 10% | No | Moderate | Balanced (80% - 90%) | Optimal information available | Not aware of any such initiative. Though the release coordination among teams was better than previous releases among teams | Well Managed | Continuous Epic Grooming | Sprint Closure/review | Ad-hoc requests prioritisation and acceptance | Risk call out during Weekly SoS | Better & transparent commitments | Ad-hoc Tasks & improper prioritisation | More Than 5% but less than 10% |  | YES | No
2024-08-20 11:36 | Sandeep Kumar | Dev | Leo | Yes | 10% to 20% | Yes | Yes | Balanced | 4 | 4 | 3 | 5 | Yes | 4 | 5 | SME/Epic Owner/EM/QM (Pre Defined Efforts Estimates) | 4 | 4 | Yes | 4 | YES | Multiple | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Not aware of any such initiative. Though the release coordination among teams was better than previous releases among teams | Well Managed | Continuous Epic Grooming | Sprint DSU's | CI/CD, Testing & Continuous planning | Blocking Scope change | Work allocation with sufficient capacity reserve | PR Merges | Less than 5% |  | YES | No
2024-08-20 11:38 | Krishna Kishore Mothukuri | Dev | Pathfinders | Yes | 30% and Above | Yes | No
2024-08-20 11:38 | Mohammed Fayaz | QA | Helios | Yes | 10% or below | Yes | Yes | Well Managed | 4 | 4 | 4 | 4 | Yes | 5 | 5 | Individual | 4 | 4 | Yes | 5 | Moderately | Moderate | 20% to 30% | Yes | Moderate | Balanced (80% - 90%) | Some Information but still need further details | Not aware of any such initiative. Though the release coordination among teams was better than previous releases among teams | Well Managed | Continuous Epic Grooming | Sprint Closure/review | Jira Details - Epic breakdown, DoD, Exit criteria, CS Bugs | Strict Bug SLA's | None | Ad-hoc Tasks & improper prioritisation | More Than 5% but less than 10% | no | YES | no
2024-08-20 11:43 | Mohammed Fayaz | QA | Aurora | Yes | 20% to 30% | Yes | Yes | Balanced | 4 | 4 | 4 | 4 | Yes | 4 | 4 | Individual | 4 | 4 | Yes | 4 | YES | Moderate | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Some Information but still need further details | Yes | Average | Code Freeze Milestones and hardening phase | Sprint Planning | Non Release Activity Identification & capacity reserve | Change in Due date and QA Sign off Date restrictions | None | Ad-hoc Tasks & improper prioritisation | Less than 5% |  | YES | No
2024-08-20 11:57 | Sandeep Kumar | Dev & Scrum Master | Iota | Yes | 10% to 20% | Yes | Yes | Balanced | 4 | 4 | 3 | 5 | Partially/Incomplete | 4 | 4 | Individual | 4 | 3 | Yes | 4 | YES | Moderate | Less than 10% | Yes | Moderate | Balanced (80% - 90%) | Some Information but still need further details | Yes | Well Managed | Epic Breakdown | Sprint Retrospective | Intra Team Collaboration - Dependency linking on Jira by Individual owners | Blocking Scope change | Release Planning, Strategy & Schedule (Proper Checkpoint and dates on jira tickets) | Improper Epic Breakdown & Estimations - Missing Sprint Backlog | More Than 5% but less than 10% |  | YES | NA
2024-08-20 11:57 | Sandeep Kumar | Dev & Scrum Master | Dynamos | Yes | 10% to 20% | Yes | Yes | Well Managed | 4 | 5 | 4 | 5 | Yes | 5 | 5 | Scrum Team | 4 | 5 | Yes | 4 | YES | Multiple | Less than 10% | No | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Release Kick Off | Sprint Planning | Intra Team Collaboration - Dependency linking on Jira by Individual owners | Change in Due date and QA Sign off Date restrictions | Effective communication | PR Merges | More Than 5% but less than 10% |  | YES | NA
2024-08-20 12:00 | Sandeep Kumar | Dev & Scrum Master | Gryffindor | Yes | 10% to 20% | Yes | Yes | Balanced | 4 | 5 | 5 | 5 | Yes | 5 | 5 | Scrum Team | 5 | 5 | Yes | 5 | YES | Moderate | 10% to 20% | Yes | Moderate | Over Utilised (90% and Above) | Optimal information available | Yes | Well Managed | Continuous Epic Grooming | Sprint DSU's | Ad-hoc requests prioritisation and acceptance | Risk call out during Weekly SoS | Effective communication | Reviews | More Than 5% but less than 10% |  | YES | NA
2024-08-20 12:01 | Mujtaba Ahmad | Dev | Titans | Yes | 10% to 20% | Yes | Yes | Balanced | 4 | 4 | 4 | 5 | Partially/Incomplete | 5 | 5 | Individual | 5 | 4 | Yes | 5 | YES | Moderate | 10% to 20% | Yes | Moderate | Over Utilised (90% and Above) | Optimal information available | Yes | Well Managed | Committed Epic Prioritisation | Sprint Planning | Ad-hoc requests prioritisation and acceptance | Blocking Scope change | Better Estimations & Epic Breakdown | Ad-hoc Tasks & improper prioritisation | Less than 5% |  | YES | N/A
2024-08-20 12:01 | Sandeep Kumar | Dev | Dynamos | No |  |  | No
2024-08-20 12:03 | Mohammed Fayaz | QA | Stark | Yes | 20% to 30% | Yes | Yes | Balanced | 4 | 4 | 5 | 4 | Yes | 4 | 5 | Individual | 5 | 5 | Yes | 4 | YES | Multiple | 20% to 30% | Yes | Multiple | Balanced (80% - 90%) | Some Information but still need further details | Yes | Average | Epic Breakdown | Sprint Closure/review | Intra Team Collaboration - Dependency linking on Jira by Individual owners | Risk call out during Weekly SoS | Better & transparent commitments | Intra team collaboration | Less than 5% | no | YES | na
2024-08-20 12:10 | Mohammed Fayaz | EM | Hercules | No |  |  | Yes | Balanced | 4 | 4 | 4 | 4 | Yes | 4 | 4 | Individual | 3 | 3 | Yes | 3 | YES | Moderate | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Some Information but still need further details | Yes | Average | Continuous Epic Grooming | Sprint Planning | Intra Team Collaboration - Dependency linking on Jira by Individual owners | Change in Due date and QA Sign off Date restrictions | Work allocation with sufficient capacity reserve | Delay in commitments from dependant team | My role involves process improvement and enablement (EM's, SM's & Other folks responsible for process streamlining) |  | YES | No
2024-08-20 12:11 | Sandeep Kumar | Dev | Dynamos | Yes | 20% to 30% | Yes | Yes | Balanced | 4 | 4 | 3 | 4 | Partially/Incomplete | 4 | 3 | SME/Epic Owner/EM/QM (Pre Defined Efforts Estimates) | 3 | 3 | Yes | 4 | Moderately | Moderate | 10% to 20% | No | Multiple | Over Utilised (90% and Above) | Some Information but still need further details | Not aware and did not find any significant change in the release coordination among teams | Average | Code Freeze Milestones and hardening phase | Sprint Planning | Ad-hoc requests prioritisation and acceptance | Blocking Scope change | None | Ad-hoc Tasks & improper prioritisation | More than 10% but Less than 20% |  | YES | Tasks prioritisation should be consistent and effort estimation should be done properly
2024-08-20 12:13 | Mohammed Fayaz | QA | Hercules | Yes | Just started using AI, need time to quantify | Yes | Yes | Chaotic | 3 | 4 | 5 | 5 | Yes | 5 | 5 | Individual | 5 | 5 | Yes | 5 | YES | Moderate | 20% to 30% | Yes | Moderate | Balanced (80% - 90%) | Some Information but still need further details | Yes | Well Managed | Code Freeze Milestones and hardening phase | Sprint DSU's | Ad-hoc requests prioritisation and acceptance | Blocking Scope change | Efficient Jira Usage (New Fields such as - Due date, QA Lead, QA Involvement, QA Signoff date) | CS Bugs higher than the reserved Capacity | My role involves process improvement and enablement (EM's, SM's & Other folks responsible for process streamlining) | NA | YES | Please try to improve the process either let a person to focus on scrum activities or suite analysis. Both way will pressurize a person.
2024-08-20 12:16 | Mohammed Fayaz | QA | Pheonix | Yes | 20% to 30% | Yes | Yes | Well Managed | 5 | 5 | 5 | 5 | Yes | 5 | 5 | Individual | 5 | 5 | Yes | 5 | YES | Moderate | 20% to 30% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Monitoring and Controlling Progress | Sprint Planning | Ad-hoc requests prioritisation and acceptance | Risk call out during Weekly SoS | Better Estimations & Epic Breakdown | CS Bugs higher than the reserved Capacity | More Than 5% but less than 10% | NA | YES | NA
2024-08-20 12:28 | Mujtaba Ahmad | Dev | Titans | Yes | 20% to 30% | Yes | No
2024-08-20 12:37 | Mohammed Fayaz | QA | Enigma | Yes | Just started using AI, need time to quantify | Yes | Yes | Chaotic | 4 | 4 | 5 | 4 | Yes | 4 | 4 | Scrum Team | 5 | 5 | Yes | 4 | YES | Moderate | Less than 10% | No | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Monitoring and Controlling Progress | Sprint Planning | Intra Team Collaboration - Dependency linking on Jira by Individual owners | Change in Due date and QA Sign off Date restrictions | Better & transparent commitments | Ad-hoc Tasks & improper prioritisation | More than 10% but Less than 20% |  | YES | Prioritisation of Patch trackers, having multiple patch trackers from a team might impact the release commitments
2024-08-20 12:37 | Mohammed Fayaz | QA | Titans | No |  |  | Yes | Well Managed | 5 | 5 | 5 | 5 | Yes | 5 | 5 | Individual | 4 | 4 | Yes | 5 | YES | None | Less than 10% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Code Freeze Milestones and hardening phase | Sprint Retrospective | Non Release Activity Identification & capacity reserve | Risk call out during Weekly SoS | Effective communication | Non Release Activities | Less than 5% |  | YES | NA
2024-08-20 12:41 | Mujtaba Ahmad | Dev | Indus | Yes | 20% to 30% | Yes | Yes | Balanced | 4 | 4 | 4 | 4 | Yes | 4 | 5 | Scrum Team | 5 | 4 | Yes | 4 | YES | Moderate | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Not aware of any such initiative. Though the release coordination among teams was better than previous releases among teams | Average | Continuous Epic Grooming | Sprint Planning | Test Design | Risk call out during Weekly SoS | Release Planning, Strategy & Schedule (Proper Checkpoint and dates on jira tickets) | PR Merges | Less than 5% |  | YES | Nil
2024-08-20 12:53 | Sandeep Kumar | QA | Iota | Yes | 10% or below | Yes | Yes | Balanced | 4 | 5 | 5 | 5 | Yes | 4 | 4 | Individual | 5 | 4 | Yes | 4 | YES | Moderate | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Committed Epic Prioritisation | Sprint Planning | Jira Details - Epic breakdown, DoD, Exit criteria, CS Bugs | Blocking Scope change | Better & transparent commitments | Modifications on Approved Tech designs | More Than 5% but less than 10% |  | YES | NA
2024-08-20 12:56 | Sandeep Kumar | Dev | Gryffindor | Yes | 10% to 20% | Yes | Yes | Balanced | 4 | 4 | 4 | 4 | Yes | 4 | 4 | Scrum Team | 5 | 5 | Yes | 4 | YES | Moderate | Less than 10% | Yes | Moderate | Over Utilised (90% and Above) | Some Information but still need further details | Yes | Average | Epic Breakdown | Sprint Planning | Jira Details - Epic breakdown, DoD, Exit criteria, CS Bugs | Blocking Scope change | Better Estimations & Epic Breakdown | Ad-hoc Tasks & improper prioritisation | More than 10% but Less than 20% |  | YES | NA
2024-08-20 13:08 | Mohammed Fayaz | QA | Eirene | No |  |  | Yes | Balanced | 5 | 5 | 5 | 5 | Yes | 5 | 4 | Individual | 4 | 4 | Yes | 4 | YES | Moderate | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Not aware of any such initiative. Though the release coordination among teams was better than previous releases among teams | Well Managed | Committed Epic Prioritisation | Sprint Retrospective | Backlog & CS bugs prioritisation | Blocking Scope change | None | Non Release Activities | Less than 5% |  | YES | N/A
2024-08-20 13:08 | Mohammed Fayaz | QA | Iota | Yes | 10% or below | Yes | Yes | Well Managed | 5 | 5 | 5 | 5 | Yes | 5 | 4 | Individual | 5 | 5 | Yes | 4 | YES | Moderate | 10% to 20% | Yes | Moderate | Over Utilised (90% and Above) | Optimal information available | Yes | Well Managed | Committed Epic Prioritisation | Sprint Retrospective | Backlog & CS bugs prioritisation | Change in Due date and QA Sign off Date restrictions | Work allocation with sufficient capacity reserve | Intra team collaboration | Less than 5% |  | YES | no
2024-08-20 14:10 | Mohammed Fayaz | QA | Iota | Yes | 10% or below | Yes | Yes | Balanced | 5 | 5 | 4 | 5 | Yes | 5 | 4 | Individual | 4 | 4 | Yes | 4 | YES | Moderate | Less than 10% | Yes | Moderate | Balanced (80% - 90%) | Some Information but still need further details | Yes | Well Managed | Epic Breakdown | Sprint Closure/review | Test Design | Risk call out during Weekly SoS | Release Planning, Strategy & Schedule (Proper Checkpoint and dates on jira tickets) | Improper Epic Breakdown & Estimations - Missing Sprint Backlog | Less than 5% | na | YES | na
2024-08-20 14:15 | Mujtaba Ahmad | Others | Indus | Yes | 10% to 20% | No | No
2024-08-20 14:16 | Mujtaba Ahmad | Dev | Falcon | Yes | 10% or below | Yes | No
2024-08-20 14:27 | Sandeep Kumar | Dev & Scrum Master | Phi | Yes | 30% and Above | Yes | Yes | Balanced | 4 | 5 | 5 | 5 | Yes | 4 | 4 | Scrum Team | 4 | 4 | Yes | 4 | YES | Moderate | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Average | Monitoring and Controlling Progress | Sprint Closure/review | Ad-hoc requests prioritisation and acceptance | Blocking Scope change | Risk call out (Release Confluence Page) | Improper Epic Breakdown & Estimations - Missing Sprint Backlog | My role involves process improvement and enablement (EM's, SM's & Other folks responsible for process streamlining) |  | YES | na
2024-08-20 14:28 | Sandeep Kumar | Dev | Iota | Yes | 10% or below | Yes | Yes | Balanced | 4 | 5 | 3 | 5 | Yes | 4 | 4 | Individual | 4 | 4 | Yes | 5 | YES | Moderate | Less than 10% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Not aware of any such initiative. Though the release coordination among teams was better than previous releases among teams | Well Managed | Code Freeze Milestones and hardening phase | Sprint Planning | KT and recording repository | Change in Due date and QA Sign off Date restrictions | Sprint Planning Structure | Delayed Response on open Queries, need multiple followups | Less than 5% |  | YES | -
2024-08-20 14:33 | Krishna Kishore Mothukuri | Dev | Velocity | Yes | Just started using AI, need time to quantify | Yes | Yes | Well Managed | 5 | 5 | 5 | 5 | Yes | 5 | 5 | Individual | 5 | 5 | Yes | 4 | YES | Moderate | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Some Information but still need further details | Yes | Average | Epic Breakdown | Sprint DSU's | Test Design | Change in Due date and QA Sign off Date restrictions | None | Improper Epic Breakdown & Estimations - Missing Sprint Backlog | More than 10% but Less than 20% | NO | YES | NO
2024-08-20 14:49 | Mujtaba Ahmad | Dev | Indus | Yes | 20% to 30% | Yes | Yes | Well Managed | 4 | 5 | 5 | 4 | Yes | 4 | 5 | Scrum Team | 5 | 4 | Yes | 4 | YES | Multiple | 20% to 30% | Yes | Moderate | Over Utilised (90% and Above) | Optimal information available | Yes | Well Managed | Monitoring and Controlling Progress | Sprint DSU's | Ad-hoc requests prioritisation and acceptance | Blocking Scope change | Work allocation with sufficient capacity reserve | PR Merges | Less than 5% |  | YES | N/A
2024-08-20 15:04 | Krishna Kishore Mothukuri | Dev | Velocity | Yes | 30% and Above | Yes | Yes | Well Managed | 4 | 4 | 4 | 5 | Yes | 4 | 5 | Scrum Team | 4 | 4 | Yes | 5 | Moderately | Multiple | 10% to 20% | Yes | Multiple | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Continuous Epic Grooming | Sprint Planning | Backlog & CS bugs prioritisation | Risk call out during Weekly SoS | Release Planning, Strategy & Schedule (Proper Checkpoint and dates on jira tickets) | Improper Epic Breakdown & Estimations - Missing Sprint Backlog | More than 20% | NA | YES | NA
2024-08-20 16:30 | Sandeep Kumar | Dev & Scrum Master | Zeta | Yes | 10% to 20% | Yes | Yes | Balanced | 4 | 5 | 5 | 5 | Yes | 5 | 5 | Scrum Team | 4 | 4 | Yes | 4 | YES | Moderate | 10% to 20% | No | Multiple | Over Utilised (90% and Above) | Some Information but still need further details | Yes | Well Managed | Committed Epic Prioritisation | Sprint Closure/review | Ad-hoc requests prioritisation and acceptance | Change in Due date and QA Sign off Date restrictions | None | Reviews | More than 20% |  | YES | none
2024-08-20 16:32 | Mohammed Fayaz | QA | Echo | Yes | Just started using AI, need time to quantify | Yes | Yes | Well Managed | 5 | 5 | 4 | 5 | Yes | 5 | 5 | Individual | 5 | 5 | Yes | 5 | YES | Multiple | More than 30% | Yes | None | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Monitoring and Controlling Progress | Sprint Retrospective | Non Release Activity Identification & capacity reserve | Strict Bug SLA's | Better Estimations & Epic Breakdown | Missing SLA's for Bugs, Trackers on Jira | More Than 5% but less than 10% |  | YES | NA
2024-08-20 16:51 | Mohammed Fayaz | EM | Iota | Yes | 10% or below | Yes | No
2024-08-20 16:55 | Sandeep Kumar | Dev | Iota | Yes | 10% or below | Yes | Yes | Balanced | 2 | 2 | 3 | 5 | Partially/Incomplete | 4 | 3 | Individual | 3 | 2 | No |  | Moderately | Moderate | 10% to 20% | Yes | Multiple |  | Some Information but still need further details | Not aware of any such initiative. Though the release coordination among teams was better than previous releases among teams | Average | Release Kick Off | Sprint DSU's | Tech Design | Strict Bug SLA's | Effective communication | Delayed Test Designs | More Than 5% but less than 10% |  | YES | na
2024-08-20 16:56 | Mohammed Fayaz | QA | Falcon | Yes | 10% to 20% | Yes | Yes | Balanced | 4 | 4 | 4 | 4 | Partially/Incomplete | 4 | 4 | Individual | 4 | 4 | No |  | YES | Multiple | Less than 10% | Yes | Moderate | Over Utilised (90% and Above) | Optimal information available | Yes | Well Managed | Committed Epic Prioritisation | Sprint Planning | Intra Team Collaboration - Dependency linking on Jira by Individual owners | Strict Bug SLA's | Better Estimations & Epic Breakdown | PR Merges | Less than 5% | nil | YES | nil
2024-08-20 17:07 | Mohammed Fayaz | QA | Iota | Yes | 10% to 20% | Yes | Yes | Balanced | 4 | 4 | 4 | 4 | Partially/Incomplete | 4 | 3 | Scrum Team | 4 | 4 | Yes | 4 | YES | Moderate | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Some Information but still need further details | Yes | Well Managed | Epic Breakdown | Sprint Planning | Tech Design | Change in Due date and QA Sign off Date restrictions | Reduced over commit | Improper Epic Breakdown & Estimations - Missing Sprint Backlog | Less than 5% | NA | YES | NA
2024-08-20 17:32 | Mohammed Fayaz | QA | Chipmuks | No |  |  | Yes | Balanced | 4 | 4 | 4 | 4 | Partially/Incomplete | 3 | 2 | Scrum Team | 4 | 3 | Yes | 3 | Moderately | Moderate | Less than 10% | Yes | Moderate | Balanced (80% - 90%) | Some Information but still need further details | Yes | Average | Continuous Epic Grooming | Sprint Planning | Intra Team Collaboration - Dependency linking on Jira by Individual owners | Change in Due date and QA Sign off Date restrictions | Sprint Planning Structure | Modifications on Approved Tech designs | Less than 5% | NA | YES | NA
2024-08-20 18:08 | Mohammed Fayaz | QA | Sudo | Yes | 10% to 20% | Yes | Yes | Balanced | 5 | 5 | 5 | 5 | Yes | 5 | 5 | Individual | 5 | 4 | Yes | 4 | YES | Moderate | 10% to 20% | Yes | Moderate | Over Utilised (90% and Above) | Some Information but still need further details | Yes | Well Managed | Code Freeze Milestones and hardening phase | Sprint Planning | Tech Design | Strict Bug SLA's | Release Planning, Strategy & Schedule (Proper Checkpoint and dates on jira tickets) | Missing SLA's for Bugs, Trackers on Jira | Less than 5% |  | YES | no
2024-08-20 21:14 | Krishna Kishore Mothukuri | Dev | Pathfinders | Yes | 30% and Above | Yes | Yes | Balanced | 4 | 4 | 1 | 4 | Partially/Incomplete | 5 | 4 | Individual | 4 | 4 | Yes | 4 | YES | Multiple | 20% to 30% | Yes | Moderate | Over Utilised (90% and Above) | Some Information but still need further details | Yes | Well Managed | Epic Breakdown | Sprint Planning | Non Release Activity Identification & capacity reserve | Change in Due date and QA Sign off Date restrictions | Reduced over commit | Ad-hoc Tasks & improper prioritisation | More Than 5% but less than 10% |  | YES | None
2024-08-20 21:55 | Mujtaba Ahmad | Dev | Enigma | No |  |  | Yes | Balanced | 4 | 4 | 4 | 4 | Yes | 4 | 4 | Scrum Team | 4 | 4 | Yes | 4 | YES | Moderate | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Not aware of any such initiative. Though the release coordination among teams was better than previous releases among teams | Average | Code Freeze Milestones and hardening phase | Sprint Closure/review | Ad-hoc requests prioritisation and acceptance | Blocking Scope change | Sprint Planning Structure | CS Bugs higher than the reserved Capacity | More Than 5% but less than 10% |  | YES | N/A
2024-08-20 22:38 | Mujtaba Ahmad | Dev | Ganges | No |  |  | Yes | Balanced | 3 | 5 | 4 | 4 | Yes | 3 | 5 | Scrum Team | 4 | 3 | Yes | 3 | YES | Multiple | Less than 10% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Not aware of any such initiative. Though the release coordination among teams was better than previous releases among teams | Average | Epic Breakdown | Sprint Retrospective | Intra Team Collaboration - Dependency linking on Jira by Individual owners | Change in Due date and QA Sign off Date restrictions | Sprint Planning Structure | Intra team collaboration | Less than 5% |  | YES | Inter team dependencies can be managed
2024-08-20 23:27 | Sandeep Kumar | Dev | Leo | Yes | 10% to 20% | No | Yes | Balanced | 4 | 3 | 3 | 3 | Partially/Incomplete | 4 | 3 | Scrum Team | 4 | 3 | Yes | 4 | Moderately | Moderate | 10% to 20% | No | Moderate | Balanced (80% - 90%) | Not at All | Not aware of any such initiative. Though the release coordination among teams was better than previous releases among teams | Average | Epic Breakdown | Sprint Planning | Tech Design | Strict Bug SLA's | Better Estimations & Epic Breakdown | PR Merges | More than 10% but Less than 20% |  | Not Efficiently | NA
2024-08-21 09:43 | Mujtaba Ahmad | Dev & Scrum Master | Indus | Yes | 10% to 20% | Yes | Yes | Well Managed | 5 | 5 | 5 | 5 | Yes | 5 | 5 | Scrum Team | 3 | 5 | Yes | 4 | YES | Moderate | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Continuous Epic Grooming | Sprint Closure/review | Jira Details - Epic breakdown, DoD, Exit criteria, CS Bugs | Risk call out during Weekly SoS | Release Planning, Strategy & Schedule (Proper Checkpoint and dates on jira tickets) | Partial or missing details on Jira Trackers Description | Less than 5% |  | YES | No
2024-08-21 09:52 | Mujtaba Ahmad | Dev | Falcon | Yes | 20% to 30% | Yes | Yes | Balanced | 4 | 4 | 4 | 4 | Partially/Incomplete | 4 | 3 | Scrum Team | 4 | 2 | Yes | 3 | Moderately | Moderate | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Some Information but still need further details | Not aware of any such initiative. Though the release coordination among teams was better than previous releases among teams | Average | Continuous Epic Grooming | Sprint Closure/review | KT and recording repository | Blocking Scope change | Better & transparent commitments | Ad-hoc Tasks & improper prioritisation | More Than 5% but less than 10% |  | YES | No
2024-08-21 11:09 | Mohammed Fayaz | QA | Eirene | Yes | 10% or below | Yes | Yes | Balanced | 3 | 4 | 5 | 5 | Yes | 4 | 4 | Individual | 4 | 4 | Yes | 3 | YES | Moderate | Less than 10% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Epic Breakdown | Sprint Planning | Non Release Activity Identification & capacity reserve | Change in Due date and QA Sign off Date restrictions | Sprint Planning Structure | Non Release Activities | Less than 5% | NA | YES | NA
2024-08-21 11:25 | Sandeep Kumar | Dev | Zeta | Yes | 20% to 30% | Yes | Yes | Balanced | 5 | 5 | 3 | 4 | Partially/Incomplete | 4 | 4 | Scrum Team | 4 | 4 | Yes | 4 | YES | Moderate | 10% to 20% | No | Multiple | Over Utilised (90% and Above) | Optimal information available | Not aware of any such initiative. Though the release coordination among teams was better than previous releases among teams | Well Managed | Committed Epic Prioritisation | Sprint Closure/review | Ad-hoc requests prioritisation and acceptance | Risk call out during Weekly SoS | Effective communication | Delayed Response on open Queries, need multiple followups | More than 10% but Less than 20% |  | YES
2024-08-21 11:53 | Mujtaba Ahmad | Dev & Scrum Master | Titans | Yes | 20% to 30% | Yes | Yes | Well Managed | 5 | 5 | 5 | 5 | Yes | 5 | 5 | Individual | 4 | 4 | Yes | 4 | YES | Moderate | 20% to 30% | Yes | Moderate | Balanced (80% - 90%) | Some Information but still need further details | Yes | Well Managed | Committed Epic Prioritisation | Sprint Planning | CI/CD, Testing & Continuous planning | Blocking Scope change | Release Planning, Strategy & Schedule (Proper Checkpoint and dates on jira tickets) | Ad-hoc Tasks & improper prioritisation | More than 10% but Less than 20% |  | YES | n/a
2024-08-21 14:01 | Mohammed Fayaz | QA | Indus | Yes | 10% or below | Yes | Yes | Balanced | 4 | 4 | 5 | 5 | Yes | 5 | 5 | Scrum Team | 5 | 5 | Yes | 4 | YES | Moderate | Less than 10% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Committed Epic Prioritisation | Sprint Retrospective | Jira Details - Epic breakdown, DoD, Exit criteria, CS Bugs | Risk call out during Weekly SoS | Release Planning, Strategy & Schedule (Proper Checkpoint and dates on jira tickets) | Ad-hoc Tasks & improper prioritisation | More Than 5% but less than 10% |  | YES | No
2024-08-21 14:33 | Mohammed Fayaz | QA | Iris | Yes | Just started using AI, need time to quantify | Yes | Yes | Balanced | 3 | 5 | 5 | 5 | Yes | 4 | 5 | Individual | 5 | 5 | Yes | 5 | YES | Moderate | 10% to 20% | Yes | Moderate | Over Utilised (90% and Above) | Optimal information available | Not aware of any such initiative. Though the release coordination among teams was better than previous releases among teams | Well Managed | Continuous Epic Grooming | Sprint Planning | Ad-hoc requests prioritisation and acceptance | Blocking Scope change | Efficient Jira Usage (New Fields such as - Due date, QA Lead, QA Involvement, QA Signoff date) | Ad-hoc Tasks & improper prioritisation | More Than 5% but less than 10% |  | YES | no
2024-08-21 16:50 | Sandeep Kumar | Dev & Scrum Master | Tranformers | Yes | 10% or below | Yes | Yes | Balanced | 4 | 4 | 5 | 4 | Yes | 4 | 4 | Scrum Team | 4 | 3 | Yes | 5 | YES | Moderate | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Monitoring and Controlling Progress | Sprint Closure/review | Backlog & CS bugs prioritisation | Strict Bug SLA's | Release Planning, Strategy & Schedule (Proper Checkpoint and dates on jira tickets) | Ad-hoc Tasks & improper prioritisation | My role involves process improvement and enablement (EM's, SM's & Other folks responsible for process streamlining) |  | YES | NA
2024-08-21 23:14 | Mujtaba Ahmad | Dev | Falcon | Yes | 20% to 30% | Yes | Yes | Balanced | 4 | 5 | 5 | 5 | Yes | 5 | 5 | Scrum Team | 4 | 4 | Yes | 5 | YES | Multiple | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Not aware of any such initiative. Though the release coordination among teams was better than previous releases among teams | Well Managed | Monitoring and Controlling Progress | Sprint Closure/review | Ad-hoc requests prioritisation and acceptance | Change in Due date and QA Sign off Date restrictions | None | CS Bugs higher than the reserved Capacity | More Than 5% but less than 10% |  | YES | None