## Form Responses 1
Timestamp | You are part of which of the following directors org | Select reporting manager per Sage? | What's your primary role for the release? | Enter the Team/Scrum team that you are mostly associated with during the release. (Select Only One) Note: If associated with multiple teams, please select individual capacity | Sprint Retrospective Effectiveness | Were the action item from the Sprint retrospectives addressed during this release? | What was the action item and how was it resolved during the release? | Are you directly involved in the Release Deliverables for current release items or items planned and in progress for future releases? | How would you rate Release Overall (Individual Perspective) ? | How would you rate the release planning in comparison to previous release plannings? (1-Poor, 5- Improved) | How well were you as an individual aware of your teams commitments and scope of work prior to release implementation start ? (1-Not Aware, 5- Aware) | What was your involvement in Release planning and the selection of commitments? (1-Not Involved, 5- Fully Involved) | Were you as an individual aware of the Release timelines and your tasks in hand for the Release ? (1-Somewhat Aware, 5- Fully Aware) | Detailed Epic Breakdown with estimates and scrum team ownership were done for your trackers parent epic prior to Release Implementation Initiation. | How confident were you in terms of your teams commitments and deliverables? (1-Not Confident, 5- Full Confidence) | How would you rate effectiveness the Sprint Planning Meetings ? (1-Not Effective, 5- Effective) | Individual items efforts estimate for completion of the task is done by whom ? (Desired state is by scrum team) | How would you rate effectiveness of the Daily Standup connect to understand and analyse your tasks in hand ? (1-Not Effective, 5- Effective) | How would you rate effectiveness of the Sprint Closure / review meetings ? (1-Not Effective, 5- Effective) | Was Sprint retrospective Conducted for your Team at the end of each Sprint | Do you as an individual get sufficient opportunity to raise risk or concerns during agile ceremonies? | Do you get opportunity to learn new things in accordance to your role release over release? | What percentage of your capacity in the sprint was reserved for Items such as CS Support Bugs/Requests which cannot be estimated but as a team you reserve some bandwidth, as per history you are aware of such requests and your team reserves capacity for it ?(individual capacity reserved) | Is your reserved capacity for the Historical support activities such as CS Bugs/Support tickets and others, sufficient during the release. | How much Adhoc requests (Request for which no bandwidth was reserved during Release/Sprint Planning) were received post sprint planning. | How was your available capacity utilised during the Release i.e. your workload. (1-Under Utilisation, 5- Over Utilisation) | Do you have sufficient details available on Jira to successfully and independently complete your assigned tasks(details like description, acceptance criteria and timeline) | Was the Release Coordination Group initiated with representatives from each directors org, helpful and more efficient in managing the Release checkpoints and ensuring the key asks were routed better to the respective team/people? | How well were dependencies managed in the Release. | Check the Release Ceremony where there is need to spend more efforts to make the release more effective. | Check the Sprint Ceremony where there is need to spend more efforts to make the release more effective. | What is the top improvement area in the below list you would suggest to improve for a smoother release? | What do we need to improve in Release Implementation | Anything that you would like to call out which improved in this release as compared to the previous releases. | What is the most probable reason that deviates the planned timelines? | Applicable only for pure DEV or QA Resources - What percent of your available capacity is impacted by process changes and new processes enablement on regular tasks not the other cleanup activities from previous releases (Not Applicable to EM's, SM's & Other Folks responsible for process streamlining) | Any other thought you would like to share related to the releases. | In Your individual opinion are we considering the release Delivery Timelines and milestones while we are planning and delivering our assigned tasks | Do you have any suggestion for improving and streamlining the release further? | Any Suggestions for Jira enhancements? | What was your engagement area during this release while not associated with the release deliverables? | Are you using AI for efficiency improvement in your day to day Dev/QA activity? | Which Tool are you using for your AI tasks | With the usage of AI what has been increase in your productivity as compared to previous release? | Are you getting the required support and guidance within Engineering to explore and increase efficiency using AI?
2025-05-19 20:51 | Krishna Kishore Mothukuri | Ajitkumar kaller | Dev | Velocity | 4 | Yes | More meeting with PM | Yes | Well Managed | 4 | 4 | 4 | 4 | Yes | 4 | 4 | Individual | 4 | 4 | Yes | YES | Moderate | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Epic Breakdown | Sprint Planning | Jira Details - Epic breakdown, DoD, Exit criteria, CS Bugs | Blocking Scope change | Better Estimations & Epic Breakdown | Improper Epic Breakdown & Estimations - Missing Sprint Backlog | More Than 5% but less than 10% |  | YES | NA |  |  | Yes | ChatGPT, CoPilot | 20% to 30% | Yes
2025-05-19 20:52 | Jegadeesh Santhana Krishnan | Chandra Sekhar Kusupati | Dev | Helios | 5 | Yes | Adding story points before sprint start | Yes | Balanced | 4 | 5 | 4 | 4 | Yes | 4 | 4 | Individual | 5 | 5 | Yes | YES | Multiple | More than 30% | No | Moderate | Over Utilised (90% and Above) | Optimal information available | Not aware of any such initiative. Though the release coordination among teams was better than previous releases among teams | Well Managed | Epic Breakdown | Sprint DSU's | Tech Design | Change in Due date and QA Sign off Date restrictions | Reduced over commit | Ad-hoc Tasks & improper prioritisation | More Than 5% but less than 10% |  | YES | NA |  |  | Yes | ChatGPT, CoPilot, Gemini | 20% to 30% | Yes
2025-05-19 20:52 | Mohammed Fayaz | Varun Batra | QA | Avengers | 4 | No |  | Yes | Balanced | 4 | 4 | 3 | 4 | Yes | 4 | 4 | Scrum Team | 5 | 4 | Yes | YES | Moderate | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Some Information but still need further details | Yes | Average | Committed Epic Prioritisation | Sprint Planning | Ad-hoc requests prioritisation and acceptance | Risk call out during Weekly SoS | Better & transparent commitments | Ad-hoc Tasks & improper prioritisation | More Than 5% but less than 10% |  | YES | NA |  |  | Yes | ChatGPT | 10% to 20% | Yes
2025-05-19 20:57 | Mohammed Fayaz | Varun Batra | EM |  |  |  |  | No | [33 empty] | Yes | ChatGPT | 30% and Above | Yes
2025-05-19 21:11 | Mohammed Fayaz | Prasad Deverakonda | QA | E2E tetris | 5 | Yes | Many inputs like sticking to single plan, more epic testing was discussed and action item documented -- which were implemented, along with knowledge sharing sessions with team | Yes | Balanced | 4 | 5 | 5 | 5 | Yes | 5 | 5 | Individual | 5 | 5 | Yes | YES | Multiple | 20% to 30% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Average | Committed Epic Prioritisation | Sprint Planning | Bugs Management & Deferring | Risk call out during Weekly SoS | Better & transparent commitments | Partial or missing details on Jira Trackers Description | More than 10% but Less than 20% |  | YES | NA |  |  | Yes | ChatGPT, Perplexity, Gemini | 10% to 20% | Yes
2025-05-19 21:24 | Jegadeesh Santhana Krishnan | Subhan Ansari | Dev | Aliens | 5 | Yes | Adhock Task tracker was created | Yes | Balanced |  |  |  |  | Yes |  |  | Scrum Team |  |  | Yes | Moderately | Moderate | 10% to 20% | Yes |  |  | Optimal information available | Yes |  | Code Freeze Milestones and hardening phase | Sprint Planning | Backlog & CS bugs prioritisation | Risk call out during Weekly SoS | Effective communication | Ad-hoc Tasks & improper prioritisation | More Than 5% but less than 10% |  | YES | NA |  |  | Yes | ChatGPT, CoPilot, Gemini, Claude | 10% to 20% | Yes
2025-05-19 21:38 | Mohammed Fayaz | Tharuni Sai Idupulapati | QA | Gryffindor | 4 | Yes | Reviewing PR by a call and Doing Sprint closure | Yes | Balanced | 5 | 5 | 5 | 5 | Partially/Incomplete | 5 | 4 | Individual | 5 | 3 | Yes | YES | Moderate | 10% to 20% | No | None | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Epic Breakdown | Sprint Closure/review | Jira Details - Epic breakdown, DoD, Exit criteria, CS Bugs | Risk call out during Weekly SoS | Effective communication | Reviews | More Than 5% but less than 10% | NA | Not Efficiently | NA | NA |  | Yes | ChatGPT | 30% and Above | Yes
2025-05-19 21:40 | Mohammed Fayaz | Varun Batra | Architect/Individual Contributors |  |  |  |  | Yes | Balanced | 3 | 4 | 4 | 4 | Yes | 5 | 4 | Scrum Team | 4 | 3 | No | YES | Moderate | 20% to 30% | Yes | Moderate | Over Utilised (90% and Above) | Optimal information available | Yes | Average | Release Kick Off | Sprint Closure/review | Intra Team Collaboration - Dependency linking on Jira by Individual owners | Change in Due date and QA Sign off Date restrictions | Reduced over commit | Ad-hoc Tasks & improper prioritisation | More Than 5% but less than 10% |  | YES | Yes there should be better coordination between intra team dependancies like trackers which are related and dependant in between adaptor and core teams etc. This better coordination might help in streamlining of things early leading to lesser resource and time wastage. |  |  | Yes | ChatGPT, Gemini | 10% to 20% | Yes
2025-05-19 21:51 | Mohammed Fayaz | Anusha Jharupula | QA | Indus | 4 | Yes | to reserve bandwidth for adhoc trackers in planning phase | Yes | Balanced | 4 | 4 | 4 | 4 | Yes | 4 | 4 | Individual | 4 | 4 | Yes | YES | Moderate | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Some Information but still need further details | Yes | Average | Continuous Epic Grooming | Sprint Planning | Ad-hoc requests prioritisation and acceptance | Risk call out during Weekly SoS | Better & transparent commitments | Ad-hoc Tasks & improper prioritisation | More Than 5% but less than 10% | na | YES | na | na |  | Yes | ChatGPT | 10% or below | Yes
2025-05-19 22:05 | Jegadeesh Santhana Krishnan | Chandra Sekhar Kusupati | Dev | Hercules | 5 | No |  | Yes | Well Managed | 5 | 5 | 5 | 5 | Yes | 5 | 5 | Scrum Team | 5 | 5 | Yes | YES | Moderate | 10% to 20% | Yes | Moderate | Over Utilised (90% and Above) | Optimal information available | Yes | Well Managed | Epic Breakdown | Sprint DSU's | Test Design | Blocking Scope change | Better Estimations & Epic Breakdown | Communication gap b/w dependent teams | More Than 5% but less than 10% |  | YES | no |  |  | Yes | ChatGPT, CoPilot, GitHub AI review | 10% to 20% | Yes
2025-05-19 22:37 | Mohammed Fayaz | Tharuni Sai Idupulapati | EM |  |  |  |  | Yes | Well Managed | 5 | 5 | 5 | 5 | Partially/Incomplete | 5 | 5 | Scrum Team | 5 | 4 | Yes | YES | Multiple | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Continuous Epic Grooming | Sprint Planning | Jira Details - Epic breakdown, DoD, Exit criteria, CS Bugs | Strict Bug SLA's | None | Missing SLA's for Bugs, Trackers on Jira | My role involves process improvement and enablement (EM's, SM's & Other folks responsible for process streamlining) |  | YES |  |  |  | Yes | ChatGPT | 10% to 20% | Yes
2025-05-20 09:19 | Mujtaba Ahmad | Priya Vanteru | Dev | Indus | 4 | Yes | NA | Yes | Balanced | 5 | 5 | 5 | 5 | Yes | 5 | 4 | Scrum Team | 5 | 4 | Yes | YES | Multiple | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Monitoring and Controlling Progress | Sprint DSU's | CI/CD, Testing & Continuous planning | Risk call out during Weekly SoS | Sprint Planning Structure | Reviews | More Than 5% but less than 10% |  | YES | NA |  |  | Yes | ChatGPT, CoPilot | 10% to 20% | Yes
2025-05-20 09:48 | Mohammed Fayaz | Tharuni Sai Idupulapati | QA | Zeta | 5 | Yes | some challenges and doubts resolved with help of dev | Yes | Balanced | 5 | 5 | 5 | 5 | Yes | 5 | 5 | Individual | 5 | 5 | Yes | YES | Multiple | Less than 10% | Yes | Moderate | Over Utilised (90% and Above) | Optimal information available | Yes | Well Managed | Epic Breakdown | Sprint Planning | Jira Details - Epic breakdown, DoD, Exit criteria, CS Bugs | Change in Due date and QA Sign off Date restrictions | Better Estimations & Epic Breakdown | Ad-hoc Tasks & improper prioritisation | Less than 5% | NA | YES | NA | NA |  | Yes | ChatGPT | 10% or below | Yes
2025-05-20 09:55 | Mohammed Fayaz | Varun Batra | QA & Scrum Master | Dynamos | 5 | Yes | Expedite PR review process | Yes | Well Managed | 5 | 5 | 5 | 5 | Yes | 5 | 5 | Scrum Team | 5 | 5 | Yes | YES | Moderate | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Some Information but still need further details | Yes | Well Managed | Continuous Epic Grooming | Sprint Closure/review | Jira Details - Epic breakdown, DoD, Exit criteria, CS Bugs | Blocking Scope change | Better Estimations & Epic Breakdown | Modifications on Approved Tech designs | More Than 5% but less than 10% |  | YES | Good for this release |  |  | Yes | ChatGPT, CoPilot | 10% or below | Yes
2025-05-20 10:02 | Jegadeesh Santhana Krishnan | Ramakrishna Grandhi | Dev & Scrum Master | Avengers | 3 | No |  | Yes | Well Managed | 4 | 4 | 3 | 4 | Yes | 4 | 3 | Scrum Team | 4 | 3 | Yes | Moderately | Moderate | Less than 10% | No | Moderate | Over Utilised (90% and Above) | Optimal information available | Yes | Well Managed | Continuous Epic Grooming | Sprint Retrospective | Backlog & CS bugs prioritisation | Blocking Scope change | Effective communication | CS Bugs higher than the reserved Capacity | My role involves process improvement and enablement (EM's, SM's & Other folks responsible for process streamlining) |  | YES | Reserve bandwidth for CS issues. |  |  | Yes | ChatGPT, CoPilot, Gemini | 10% to 20% | Yes
2025-05-20 10:06 | Mohammed Fayaz | Varun Batra | QA | Tintin | 5 | Yes | PR merging is taking time, so they have reduced it by providing access to more members | Yes | Balanced | 5 | 4 | 5 | 4 | Partially/Incomplete | 5 | 5 | Scrum Team | 4 | 4 | No | YES | None | Less than 10% | Yes | Moderate | Balanced (80% - 90%) | Some Information but still need further details | Yes | Average | Code Freeze Milestones and hardening phase | Sprint Closure/review | Bugs Management & Deferring | Blocking Scope change | Effective communication | Ad-hoc Tasks & improper prioritisation | More Than 5% but less than 10% | NA | YES | Can we restrict Jira status transitions beyond code freeze to only managers? This would help us track exactly where delays are occurring. | NA |  | Yes | ChatGPT, CoPilot, Gemini | 10% to 20% | No
2025-05-20 10:09 | Mohammed Fayaz | Mohammed Fayaz | EM |  |  |  |  | Yes | Balanced | 3 | 4 | 2 | 4 | Partially/Incomplete | 4 | 2 | Individual | 2 | 3 | Yes | YES | Moderate | Less than 10% | No | Multiple | Balanced (80% - 90%) | Some Information but still need further details | Yes | Average | Epic Breakdown | Sprint DSU's | Bugs Management & Deferring | Blocking Scope change | Better & transparent commitments | Delay in commitments from dependant team | My role involves process improvement and enablement (EM's, SM's & Other folks responsible for process streamlining) |  | YES | No |  |  | Yes | ChatGPT | Just started using AI, need time to quantify | Yes
2025-05-20 10:21 | Mujtaba Ahmad | Ranjith Kumar M | Dev | Zeta | 4 | Yes | PR review was taking some time. So we addressed this by scheduled daily meet for PR review itself to fastrack this. | Yes | Balanced | 4 | 5 | 5 | 5 | Yes | 5 | 5 | Scrum Team | 5 | 4 | Yes | YES | Moderate | 10% to 20% | Yes | Moderate | Over Utilised (90% and Above) | Some Information but still need further details | Yes | Average | Code Freeze Milestones and hardening phase | Sprint Closure/review | Ad-hoc requests prioritisation and acceptance | Risk call out during Weekly SoS | Better Estimations & Epic Breakdown | Ad-hoc Tasks & improper prioritisation | Less than 5% |  | YES | N/A |  |  | Yes | ChatGPT, CoPilot | 10% to 20% | Yes
2025-05-20 10:28 | Jegadeesh Santhana Krishnan | Selvakumar Thiyagarajan | EM |  |  |  |  | Yes | Well Managed | 5 | 5 | 5 | 5 | Yes | 5 | 5 | Individual | 5 | 5 | Yes | YES | Multiple | Less than 10% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Continuous Epic Grooming | Sprint Retrospective | Intra Team Collaboration - Dependency linking on Jira by Individual owners | Change in Due date and QA Sign off Date restrictions | Reduced over commit | Delay in commitments from dependant team | My role involves process improvement and enablement (EM's, SM's & Other folks responsible for process streamlining) |  | YES | No | No |  | Yes | ChatGPT, CoPilot, GitHub AI review | 20% to 30% | Yes
2025-05-20 10:44 | Mohammed Fayaz | Prasad Deverakonda | QA | Tetris | 4 | Yes | Good | Yes | Balanced | 4 | 5 | 4 | 5 | Yes | 4 | 4 | Scrum Team | 4 | 4 | Yes | YES | Multiple | 10% to 20% | Yes | Moderate | Over Utilised (90% and Above) | Optimal information available | Yes | Well Managed | Monitoring and Controlling Progress | Sprint Planning | Test Design | Blocking Scope change | Release Planning, Strategy & Schedule (Proper Checkpoint and dates on jira tickets) | Ad-hoc Tasks & improper prioritisation | More Than 5% but less than 10% |  | YES | NA |  |  | Yes | ChatGPT | 10% to 20% | Yes
2025-05-20 10:47 | Mohammed Fayaz | Varun Batra | QA | Aliens | 5 | Yes | NA | Yes | Balanced | 4 | 4 | 4 | 4 | Yes | 4 | 4 | Scrum Team | 4 | 4 | Yes | YES | Moderate | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Average | Code Freeze Milestones and hardening phase | Sprint Closure/review | Ad-hoc requests prioritisation and acceptance | Strict Bug SLA's | Better Estimations & Epic Breakdown | Communication gap b/w dependent teams | Less than 5% |  | YES | stick to code freeze timelines |  |  | Yes | ChatGPT | 10% to 20% | Yes
2025-05-20 10:53 | Mohammed Fayaz | Prasad Deverakonda | QA | Tetris | 4 | No |  | Yes | Chaotic | 4 | 4 | 4 | 4 | Yes | 4 | 4 | Individual | 4 | 4 | Yes | Moderately | None | Less than 10% | Yes | Moderate | Balanced (80% - 90%) | Some Information but still need further details | Yes | Average | Monitoring and Controlling Progress | Sprint Planning | Backlog & CS bugs prioritisation | Risk call out during Weekly SoS | Reduced over commit | Non Release Activities | Less than 5% |  | YES |  |  |  | Yes | ChatGPT, CoPilot | Just started using AI, need time to quantify | No
2025-05-20 10:53 | Diksha Khatri | Diksha Khatri | Architect/Individual Contributors |  |  |  |  | Yes | Balanced | 3 | 4 | 4 | 4 | Yes | 3 | 4 | Individual | 4 | 4 | Yes | YES | Moderate | 10% to 20% | Yes | Moderate | Over Utilised (90% and Above) | Some Information but still need further details | Yes | Average | Code Freeze Milestones and hardening phase | Sprint Closure/review | Non Release Activity Identification & capacity reserve | Change in Due date and QA Sign off Date restrictions | Sprint Planning Structure | Ad-hoc Tasks & improper prioritisation | Less than 5% |  | YES | NA |  |  | Yes | ChatGPT, CoPilot, GitHub AI review | 30% and Above | No
2025-05-20 10:54 | Mohammed Fayaz | Prasad Deverakonda | QA & Scrum Master | Iota | 4 | Yes | Epic status updation | Yes | Well Managed | 4 | 5 | 5 | 5 | Partially/Incomplete | 5 | 4 | Scrum Team | 5 | 5 | Yes | YES | Moderate | Less than 10% | Yes | Moderate | Over Utilised (90% and Above) | Some Information but still need further details | Yes | Well Managed | Continuous Epic Grooming | Sprint Planning | Jira Automation | Blocking Scope change | Better Estimations & Epic Breakdown | Non Release Activities | More Than 5% but less than 10% |  | YES | NA |  |  | Yes | ChatGPT | 20% to 30% | Yes
2025-05-20 10:55 | Diksha Khatri | Diksha Khatri | EM |  |  |  |  | No | [32 empty] | Overlooking Scrum team and ensuring Release deliverable process is followed | No | CoPilot, Gemini | Just started using AI, need time to quantify | No
2025-05-20 10:55 | Mohammed Fayaz | Prasad Deverakonda | QA | Iota | 5 | Yes | Need more clarity on the Sprint/release backlog for the upcoming sprints or releases and we worked on that | Yes | Well Managed | 5 | 5 | 5 | 5 | Yes | 5 | 5 | Individual | 4 | 4 | No | YES | Moderate | 10% to 20% | Yes | Moderate | Over Utilised (90% and Above) | Optimal information available | Yes | Well Managed | Committed Epic Prioritisation | Sprint Closure/review | Backlog & CS bugs prioritisation | Risk call out during Weekly SoS | Reduced over commit | Improper Epic Breakdown & Estimations - Missing Sprint Backlog | Less than 5% |  | YES | no |  |  | Yes | ChatGPT | 10% or below | Yes
2025-05-20 10:56 | Diksha Khatri | SWATANTRA ROUT | Dev | Iota | 5 | Yes | Check on the sprint backlog for the upcoming sprint | Yes | Balanced | 4 | 4 | 4 | 3 | Partially/Incomplete | 4 | 4 | Individual | 4 | 4 | Yes | YES | Moderate | 10% to 20% | No | Moderate | Balanced (80% - 90%) | Some Information but still need further details | No | Well Managed | Continuous Epic Grooming | Sprint Closure/review | Backlog & CS bugs prioritisation | Change in Due date and QA Sign off Date restrictions | Reduced over commit | Modifications on Approved Tech designs | More Than 5% but less than 10% |  | YES | NA |  |  | Yes | CoPilot, GitHub AI review | 10% or below | No
2025-05-20 10:59 | Diksha Khatri | SWATANTRA ROUT | Dev & Scrum Master | Iota | 5 | No |  | Yes | Balanced | 3 | 5 | 5 | 5 | Yes | 4 | 4 | Scrum Team | 5 | 3 | Yes | YES | Moderate | Less than 10% | Yes | None | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Release Kick Off | Sprint Planning | Ad-hoc requests prioritisation and acceptance | Blocking Scope change | Better & transparent commitments | Modifications on Approved Tech designs | My role involves process improvement and enablement (EM's, SM's & Other folks responsible for process streamlining) | No | YES | NA | NA |  | Yes | ChatGPT, CoPilot, GitHub AI review | 10% to 20% | Yes
2025-05-20 10:59 | Mujtaba Ahmad | Ranjith Kumar M | Dev | Zeta | 3 | Yes | Faster Pr reviews | Yes | Balanced | 4 | 4 | 3 | 4 | Yes | 4 | 4 | Scrum Team | 4 | 3 | Yes | YES | Moderate | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Some Information but still need further details | Yes | Well Managed | Committed Epic Prioritisation | Sprint Closure/review | Ad-hoc requests prioritisation and acceptance | Blocking Scope change | Better Estimations & Epic Breakdown | Ad-hoc Tasks & improper prioritisation | More Than 5% but less than 10% |  | YES | More clear Prioritisation of tasks |  |  | Yes | ChatGPT, CoPilot | 10% to 20% | Yes
2025-05-20 11:11 | Diksha Khatri | SWATANTRA ROUT | Dev & Scrum Master | Iota | 5 | Yes | Epic and story/bug tracking and moving it to the right status We are doing regular epic status updates to make sure the trackers are in the right state. Bugs and other trackers we are validating the trackers during DSU. | Yes | Balanced | 5 | 4 | 4 | 4 | Yes | 5 | 4 | Individual | 4 | 4 | Yes | YES | Multiple | Less than 10% | Yes | None | Balanced (80% - 90%) | Some Information but still need further details | Yes | Well Managed | Monitoring and Controlling Progress | Sprint Planning | CI/CD, Testing & Continuous planning | Risk call out during Weekly SoS | Better & transparent commitments | Ad-hoc Tasks & improper prioritisation | Less than 5% |  | YES | NA |  |  | Yes | ChatGPT, CoPilot, GitHub AI review | 10% to 20% | Yes
2025-05-20 11:14 | Diksha Khatri | Diksha Khatri | Dev & Scrum Master | Iota | 4 | Yes | Mid Sprint review should be done without fail. It was actively done and JIRA reprioritised thereby saving spillovers. | Yes | Balanced | 3 | 4 | 4 | 4 | Yes | 3 | 4 | Scrum Team | 4 | 3 | Yes | Moderately | None | 10% to 20% | Yes | Moderate | Over Utilised (90% and Above) | Some Information but still need further details | Yes | Average | Continuous Epic Grooming | Sprint Closure/review | KT and recording repository | Risk call out during Weekly SoS | Work allocation with sufficient capacity reserve | Ad-hoc Tasks & improper prioritisation | More Than 5% but less than 10% |  | YES | Dashboard for Release progression would. make the whole process transparent and smooth | Use of worklog is not utilised properly |  | Yes | ChatGPT, CoPilot, Gemini, GitHub AI review | 10% to 20% | Yes
2025-05-20 11:16 | Mujtaba Ahmad | Priya Vanteru | Dev | Falcon | 5 | Yes | Better sprint planning and backlog grooming. | Yes | Well Managed | 4 | 4 | 5 | 5 | Yes |  | 5 | Scrum Team | 5 | 5 | Yes | YES | Moderate | 10% to 20% | Yes | Moderate | Over Utilised (90% and Above) | Optimal information available | Yes | Average | Committed Epic Prioritisation | Sprint Closure/review | Backlog & CS bugs prioritisation | Blocking Scope change | Release Planning, Strategy & Schedule (Proper Checkpoint and dates on jira tickets) | Delayed Response on open Queries, need multiple followups | Less than 5% |  | YES | N/A | N/A |  | Yes | ChatGPT, CoPilot | 10% or below | Yes
2025-05-20 11:22 | Mohammed Fayaz | Mohammed Fayaz | QA | Dynamos | 5 | Yes | Code review delay is addressed. | Yes | Balanced | 5 | 5 | 5 | 5 | Yes | 5 | 5 | Scrum Team | 5 | 5 | Yes | YES | Moderate | 10% to 20% | Yes | None | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Monitoring and Controlling Progress | Sprint Closure/review | Non Release Activity Identification & capacity reserve | Blocking Scope change | Better Estimations & Epic Breakdown | Partial or missing details on Jira Trackers Description | Less than 5% |  | YES | Can we add environment unavailability also. |  |  | Yes | ChatGPT | 10% to 20% | Yes
2025-05-20 11:25 | Jegadeesh Santhana Krishnan | Anusha Badveeti | Dev | Dynamos | 5 | Yes | NA | Yes | Balanced | 4 | 4 | 5 | 5 | Yes | 4 | 5 | Scrum Team | 4 | 4 | Yes | YES | Multiple | Less than 10% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Code Freeze Milestones and hardening phase | Sprint Closure/review | Tech Design | Change in Due date and QA Sign off Date restrictions | None | PR Merges | Less than 5% |  | YES | NA |  |  | Yes | ChatGPT, CoPilot | 10% or below | Yes
2025-05-20 11:26 | Jegadeesh Santhana Krishnan | Anusha Badveeti | Dev | Dynamos | 4 | Yes | NA | Yes | Balanced | 4 | 5 | 5 | 4 | Yes | 4 | 5 | Individual | 4 | 3 | Yes | Moderately | Moderate | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Some Information but still need further details | Yes | Well Managed | Monitoring and Controlling Progress | Sprint Planning | Intra Team Collaboration - Dependency linking on Jira by Individual owners | Blocking Scope change | None | PR Merges | More Than 5% but less than 10% |  | YES | NA |  |  | Yes | CoPilot, Gemini | 10% to 20% | Yes
2025-05-20 11:30 | Jegadeesh Santhana Krishnan | Anusha Badveeti | Dev | Dynamos | 4 | Yes | There wasn't an action item for the scrum team as such. | Yes | Balanced | 4 | 4 | 4 | 4 | Yes | 4 | 4 | Scrum Team | 4 | 4 | Yes | YES | Moderate | 10% to 20% | Yes | None | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Committed Epic Prioritisation | Sprint Planning | Non Release Activity Identification & capacity reserve | Blocking Scope change | Sprint Planning Structure | Reviews | More Than 5% but less than 10% |  | YES | -NA- |  |  | Yes | ChatGPT | 10% to 20% | Yes
2025-05-20 11:56 | Jegadeesh Santhana Krishnan | Jegadeesh Santhana Krishnan | EM |  |  |  |  | Yes | Well Managed | 5 | 5 | 5 | 5 | Yes | 5 | 5 | Scrum Team | 5 | 4 | Yes | YES | Moderate | Less than 10% | Yes | Moderate | Balanced (80% - 90%) | Some Information but still need further details | Yes | Well Managed | Code Freeze Milestones and hardening phase | Sprint Planning | KT and recording repository | Change in Due date and QA Sign off Date restrictions | Release Planning, Strategy & Schedule (Proper Checkpoint and dates on jira tickets) | PR Merges | My role involves process improvement and enablement (EM's, SM's & Other folks responsible for process streamlining) | . | YES | . | . |  | Yes | ChatGPT, Gemini | 10% to 20% | Yes
2025-05-20 12:07 | Mohammed Fayaz | Mohammed Fayaz | EM |  |  |  |  | Yes | Chaotic | 4 | 5 | 5 | 5 | Yes | 4 | 4 | Scrum Team | 5 | 4 | Yes | YES | Moderate | Less than 10% | Yes | Moderate | Over Utilised (90% and Above) | Optimal information available | Yes | Not Well | Code Freeze Milestones and hardening phase | Sprint Planning | Ad-hoc requests prioritisation and acceptance | Strict Bug SLA's | Risk call out (Release Confluence Page) | Improper Epic Breakdown & Estimations - Missing Sprint Backlog | My role involves process improvement and enablement (EM's, SM's & Other folks responsible for process streamlining) |  | YES | NA |  |  | Yes | ChatGPT, CoPilot, Gemini | 10% or below | Yes
2025-05-20 12:10 | Diksha Khatri | SWATANTRA ROUT | QA | Nexus | 4 | Yes | Handling execution of suites effectively | Yes | Balanced | 3 | 3 | 4 | 4 | Yes | 4 | 4 | Scrum Team | 4 | 3 | Yes | NO | Moderate | Less than 10% | Yes | Moderate | Balanced (80% - 90%) | Some Information but still need further details | Not aware and did not find any significant change in the release coordination among teams | Average | Epic Breakdown | Sprint Planning | Jira Details - Epic breakdown, DoD, Exit criteria, CS Bugs | Strict Bug SLA's | Sprint Planning Structure | Improper Epic Breakdown & Estimations - Missing Sprint Backlog | More Than 5% but less than 10% |  | YES | NA |  |  | Yes | ChatGPT, CoPilot, Gemini | 10% to 20% | No
2025-05-20 12:11 | Mohammed Fayaz | Prasad Deverakonda | QA | Iota | 5 | Yes | . | Yes | Balanced | 5 | 5 | 5 | 5 | Yes | 4 | 5 | Individual | 5 | 5 | Yes | YES | None | Less than 10% | No | Moderate | Balanced (80% - 90%) | Optimal information available | Not aware and did not find any significant change in the release coordination among teams | Average | Code Freeze Milestones and hardening phase | Sprint Closure/review | Test Design | Blocking Scope change | Effective communication | Intra team collaboration | Less than 5% | If there is a platform bug and its not blocker for our IA customers as they are completely migrated to the MicroServices, we signed off the release from IA side, but the platform team and release coordinator didn’t stop the release before it was deployed in staging | YES | There shouldn’t be any P1 S1 bug identified during the hardening phase. | . |  | Yes | ChatGPT | 10% to 20% | Yes
2025-05-20 12:39 | Mujtaba Ahmad | Ranjith Kumar M | Dev & Scrum Master | Zeta | 3 | Yes | PR meeting time was blocked | Yes | Balanced | 3 | 3 | 3 | 3 | Yes | 3 | 3 | Scrum Team | 3 | 3 | No | YES | Moderate | 10% to 20% | No | Multiple | Balanced (80% - 90%) | Some Information but still need further details | Yes | Average | Release Kick Off | Sprint Retrospective | Jira Details - Epic breakdown, DoD, Exit criteria, CS Bugs | Strict Bug SLA's | Efficient Jira Usage (New Fields such as - Due date, QA Lead, QA Involvement, QA Signoff date) | PR Merges | More than 10% but Less than 20% |  | YES | NA |  |  | Yes | ChatGPT, CoPilot, Perplexity, Gemini, Claude | 30% and Above | Yes
2025-05-20 12:57 | Mohammed Fayaz | Varun Batra | QA | Echo | 5 | Yes | na | Yes | Well Managed | 5 | 5 | 5 | 5 | Yes | 5 | 5 | Individual | 5 | 5 | Yes | YES | Multiple | 20% to 30% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Committed Epic Prioritisation | Sprint Closure/review | CI/CD, Testing & Continuous planning | Strict Bug SLA's | Better & transparent commitments | Non Release Activities | More Than 5% but less than 10% |  | YES | na |  |  | Yes | ChatGPT, CoPilot, Gemini | 10% or below | Yes
2025-05-20 14:35 | Mujtaba Ahmad | Priya Vanteru | Dev | Falcon | 3 | No |  | Yes | Balanced | 4 | 4 | 4 | 4 | Partially/Incomplete | 4 | 4 | Scrum Team | 4 | 2 | Yes | Moderately | Moderate | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Some Information but still need further details | Not aware of any such initiative. Though the release coordination among teams was better than previous releases among teams | Average | Committed Epic Prioritisation | Sprint Planning | CI/CD, Testing & Continuous planning | Change in Due date and QA Sign off Date restrictions | Better Estimations & Epic Breakdown | Delayed Response on open Queries, need multiple followups | Less than 5% |  | YES | No |  |  | Yes | ChatGPT | 20% to 30% | Yes
2025-05-20 15:13 | Diksha Khatri | SWATANTRA ROUT | Dev | Nexus | 4 | Yes | Locally setting up the IAs for IA Automation is an action item and its resolved | No | [32 empty] | COmpletely dedicated to IA Automation | No | ChatGPT, CoPilot | Just started using AI, need time to quantify | Yes
2025-05-20 15:13 | Diksha Khatri | SWATANTRA ROUT | Dev | Nexus | 4 | Yes | Environment files were not available to all the team members, and now it's available in a drive format. | No | [33 empty] | Yes | ChatGPT, CoPilot | 10% or below | Yes
2025-05-20 15:15 | Jegadeesh Santhana Krishnan | Ankur Sachdeva | Dev & Scrum Master | Echo | 5 | No |  | Yes | Well Managed | 5 | 5 | 5 | 5 | Yes | 4 | 4 | Scrum Team | 5 | 5 | Yes | YES | Multiple | 10% to 20% | No | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Code Freeze Milestones and hardening phase | Sprint Closure/review | Ad-hoc requests prioritisation and acceptance | Blocking Scope change | Release Planning, Strategy & Schedule (Proper Checkpoint and dates on jira tickets) | Ad-hoc Tasks & improper prioritisation | Less than 5% |  | YES | better prioritisation of trackers/bugs |  |  | Yes | ChatGPT, CoPilot, GitHub AI review | 20% to 30% | Yes
2025-05-20 15:17 | Jegadeesh Santhana Krishnan | Ankur Sachdeva | Dev & Scrum Master | Chipmuks | 5 | Yes | action items: bugs, resolution: effective discussion and prioritisation. | Yes | Balanced | 5 | 5 | 5 | 5 | Yes | 4 | 5 | Scrum Team | 5 | 5 | Yes | YES | Moderate | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Committed Epic Prioritisation | Sprint Planning | Jira Details - Epic breakdown, DoD, Exit criteria, CS Bugs | Blocking Scope change | Better & transparent commitments | Ad-hoc Tasks & improper prioritisation | More Than 5% but less than 10% |  | YES | none |  |  | Yes | ChatGPT, CoPilot, GitHub AI review | 20% to 30% | Yes
2025-05-20 15:22 | Jegadeesh Santhana Krishnan | Ankur Sachdeva | Dev | Chipmuks | 5 | Yes | tickets should be moved by sprint end and new tickets should be ready before sprint start | Yes | Balanced | 5 | 5 | 5 | 5 | Yes |  | 5 | Individual | 5 | 5 | Yes | YES | Multiple | Less than 10% | Yes | None | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Continuous Epic Grooming | Sprint Planning | KT and recording repository | Risk call out during Weekly SoS | Release Planning, Strategy & Schedule (Proper Checkpoint and dates on jira tickets) | Ad-hoc Tasks & improper prioritisation | Less than 5% |  | YES | - |  |  | Yes | ChatGPT, CoPilot | Just started using AI, need time to quantify | Yes
2025-05-20 15:29 | Diksha Khatri | Diksha Khatri | Dev | Astra | 5 | No |  | Yes | Well Managed | 5 | 5 | 5 | 5 | Yes | 5 | 5 | Scrum Team | 5 | 5 | Yes | YES | Moderate | 10% to 20% | Yes | None | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Committed Epic Prioritisation | Sprint DSU's | Test Design | Change in Due date and QA Sign off Date restrictions | None | PR Merges | More than 10% but Less than 20% |  | YES | - |  |  | Yes | ChatGPT, CoPilot, GitHub AI review | 20% to 30% | Yes
2025-05-20 15:32 | Diksha Khatri | SWATANTRA ROUT | Dev | Nexus | 5 | Yes | - | Yes | Balanced | 5 | 4 | 5 | 5 | Yes | 4 | 5 | Individual | 5 | 5 | Yes | YES | Moderate | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Not aware of any such initiative. Though the release coordination among teams was better than previous releases among teams | Well Managed | Epic Breakdown | Sprint Closure/review | KT and recording repository | Blocking Scope change | Effective communication | Improper Epic Breakdown & Estimations - Missing Sprint Backlog | More than 10% but Less than 20% |  | YES | - |  |  | Yes | ChatGPT | 10% to 20% | Yes
2025-05-20 15:41 | Diksha Khatri | Diksha Khatri | Dev | Astra | 4 | Yes | Couldn't answer as today is first retro | Yes | Balanced | 4 | 4 | 4 | 4 | Yes | 4 | 5 | Scrum Team | 5 | 5 | Yes | YES | Moderate | Less than 10% | Yes | None | Over Utilised (90% and Above) | Optimal information available | Yes | Average | Monitoring and Controlling Progress | Sprint DSU's | Jira Automation | Risk call out during Weekly SoS | Release Planning, Strategy & Schedule (Proper Checkpoint and dates on jira tickets) | Non Release Activities | More than 10% but Less than 20% |  | YES | no |  |  | Yes | ChatGPT, CoPilot, GitHub AI review | 10% to 20% | Yes
2025-05-20 15:59 | Jegadeesh Santhana Krishnan | Jegadeesh Santhana Krishnan | EM |  |  |  |  | Yes | Well Managed | 5 | 5 | 5 | 5 | Yes | 5 | 5 | Scrum Team | 5 | 5 | Yes | YES | Moderate | 20% to 30% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Code Freeze Milestones and hardening phase | Sprint Retrospective | CI/CD, Testing & Continuous planning | Risk call out during Weekly SoS | Reduced over commit | Delay in commitments from dependant team | My role involves process improvement and enablement (EM's, SM's & Other folks responsible for process streamlining) | Multiple last min changes went into adapter repos, which had cascading impact on all services. | YES | Multiple last min changes went into adapter repos, which had cascading impact on all services. | NA |  | Yes | ChatGPT, CoPilot | 10% to 20% | Yes
2025-05-20 17:01 | Jegadeesh Santhana Krishnan | Ashok Kumar Dantham | Dev | Aurora | 5 | Yes | There was a small gap regarding requirements comingup which were not part of an epic's FRD. In this release we had discussions before hand regarding this kind of use cases | Yes | Well Managed | 5 | 5 | 5 | 5 | Yes | 5 | 5 | Individual | 5 | 4 | Yes | YES | Multiple | 20% to 30% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Continuous Epic Grooming | Sprint Retrospective | Intra Team Collaboration - Dependency linking on Jira by Individual owners | Blocking Scope change | Sprint Planning Structure | Delay in commitments from dependant team | Less than 5% |  | YES | We can try to speed up UX requirements a bit, for epics of higher priority |  |  | Yes | ChatGPT, CoPilot, Perplexity, Gemini, GitHub AI review, Claude | 20% to 30% | Yes
2025-05-20 17:29 | Mujtaba Ahmad | Ranjith Kumar M | Dev | Zeta | 5 | Yes | Better JIRA fields usage, Sprint planning | Yes | Well Managed | 5 | 5 | 4 | 5 | Yes | 4 | 4 | Individual | 5 | 4 | Yes | YES | None | 10% to 20% | Yes | Moderate | Over Utilised (90% and Above) | Some Information but still need further details | Not aware of any such initiative. Though the release coordination among teams was better than previous releases among teams | Average | Continuous Epic Grooming | Sprint Closure/review | Bugs Management & Deferring | Blocking Scope change | Better & transparent commitments | Modifications on Approved Tech designs | More Than 5% but less than 10% |  | YES | no |  |  | Yes | ChatGPT, CoPilot | 10% to 20% | Yes
2025-05-20 17:32 | Mohammed Fayaz | Prasad Deverakonda | QA | Tetris | 5 | Yes | Early FRD reviews | Yes | Well Managed | 5 | 5 | 5 | 5 | Yes | 5 | 5 | Individual | 5 | 5 | Yes | YES | Moderate | 20% to 30% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Monitoring and Controlling Progress | Sprint Closure/review | Backlog & CS bugs prioritisation | Strict Bug SLA's | Risk call out (Release Confluence Page) | Missing SLA's for Bugs, Trackers on Jira | Less than 5% |  | YES | no | no |  | Yes | ChatGPT | Just started using AI, need time to quantify | Yes
2025-05-20 19:16 | Krishna Kishore Mothukuri | Ajitkumar kaller | Dev & Scrum Master | Velocity | 5 | Yes | We have started including PM for the planning and demo meeting | Yes | Balanced | 4 | 4 | 5 | 5 | Partially/Incomplete | 4 | 5 | Scrum Team | 5 | 4 | Yes | YES | Multiple | Less than 10% | Yes | Moderate | Over Utilised (90% and Above) | Optimal information available | Yes | Average | Continuous Epic Grooming | Sprint Planning | Tech Design | Change in Due date and QA Sign off Date restrictions | Reduced over commit | Non Release Activities | Less than 5% | N/A | YES | n/a | n/a |  | Yes | ChatGPT, CoPilot, Langchain | 30% and Above | Yes
2025-05-20 19:20 | Krishna Kishore Mothukuri | Krishna Kishore Mothukuri | Architect/Individual Contributors |  |  |  |  | No | [32 empty] | Research on forward looking items and POCs | Yes | ChatGPT, CoPilot | 30% and Above | Yes
2025-05-20 21:23 | Jegadeesh Santhana Krishnan | Subhan Ansari | Dev | Skywalker | 4 | Yes | To reduce spillovers. Precise sprint planning. | Yes | Balanced |  |  |  |  | Yes |  |  | Individual |  |  | Yes | YES | Moderate | Less than 10% | Yes |  |  | Some Information but still need further details | Yes |  | Code Freeze Milestones and hardening phase | Sprint Planning | Backlog & CS bugs prioritisation | Blocking Scope change | Reduced over commit | Communication gap b/w dependent teams | Less than 5% |  | YES | Nope. |  |  | Yes | ChatGPT, CoPilot | 10% or below | Yes
2025-05-20 21:39 | Mujtaba Ahmad | Priya Vanteru | Dev & Scrum Master | Indus | 4 | Yes | Action item was to enter next release with better estimation of trackers , so to resolve this we started grooming trackers regularly. | Yes | Balanced | 4 | 5 | 4 | 5 | Yes | 5 | 5 | Scrum Team | 4 | 4 | Yes | YES | Moderate | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Some Information but still need further details | Yes | Well Managed | Continuous Epic Grooming | Sprint Retrospective | Backlog & CS bugs prioritisation | Risk call out during Weekly SoS | Better Estimations & Epic Breakdown | Ad-hoc Tasks & improper prioritisation | Less than 5% |  | YES | None |  |  | Yes | ChatGPT, CoPilot | 10% to 20% | Yes
2025-05-20 22:10 | Jegadeesh Santhana Krishnan | Ashok Kumar Dantham | Dev & Scrum Master | Aurora | 5 | Yes | There is gap between FRD and UX mocks - Developer need to find out the gaps and reach out to the PM and UX team | Yes | Well Managed | 5 | 5 | 5 | 5 | Yes | 5 | 5 | Individual | 5 | 5 | Yes | YES | Multiple | 10% to 20% | Yes | None | Under Utilisation (80% Below) | Optimal information available | Yes | Well Managed | Continuous Epic Grooming | Sprint Planning | KT and recording repository | Change in Due date and QA Sign off Date restrictions | Effective communication | Communication gap b/w dependent teams | My role involves process improvement and enablement (EM's, SM's & Other folks responsible for process streamlining) |  | YES | - |  |  | Yes | ChatGPT, CoPilot | 10% to 20% | Yes
2025-05-21 06:55 | Mujtaba Ahmad | Mujtaba Ahmad | EM |  |  |  |  | Yes | Well Managed | 5 | 5 | 5 | 5 | Yes | 4 | 4 | SME/Epic Owner/EM/QM (Pre Defined Efforts Estimates) | 5 | 5 | Yes | YES | Multiple | Less than 10% | Yes | Moderate |  | Optimal information available | Yes | Well Managed | Continuous Epic Grooming | Sprint Retrospective | Ad-hoc requests prioritisation and acceptance | Strict Bug SLA's | Dependency management | CS Bugs higher than the reserved Capacity | My role involves process improvement and enablement (EM's, SM's & Other folks responsible for process streamlining) |  | YES | NA |  |  | Yes | ChatGPT | 20% to 30% | Yes
2025-05-21 10:15 | Jegadeesh Santhana Krishnan | Ramakrishna Grandhi | Dev | Tintin | 4 | Yes | NA | Yes | Balanced | 4 | 4 | 4 | 4 | Partially/Incomplete | 4 | 4 | Individual | 4 | 4 | Yes | YES | Moderate | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Some Information but still need further details | Not aware of any such initiative. Though the release coordination among teams was better than previous releases among teams | Average | Epic Breakdown | Sprint Planning | KT and recording repository | Blocking Scope change | Sprint Planning Structure | Partial or missing details on Jira Trackers Description | More Than 5% but less than 10% |  | YES | no | no |  | Yes | CoPilot | 10% or below | Yes
2025-05-21 10:40 | Jegadeesh Santhana Krishnan | Ramakrishna Grandhi | Dev | Tintin | 4 | No |  | Yes | Balanced | 4 | 5 | 5 | 5 | Yes | 5 | 4 | Scrum Team | 5 | 3 | Yes | YES | Moderate | 20% to 30% | Yes | None | Balanced (80% - 90%) | Optimal information available | Not aware and did not find any significant change in the release coordination among teams | Average | Monitoring and Controlling Progress | Sprint Closure/review | KT and recording repository | Change in Due date and QA Sign off Date restrictions | Work allocation with sufficient capacity reserve | Communication gap b/w dependent teams | Less than 5% |  | YES | No | No |  | Yes | ChatGPT, CoPilot | 10% or below | Yes
2025-05-21 10:50 | Jegadeesh Santhana Krishnan | Ramakrishna Grandhi | Dev | Avengers | 3 | No |  | No | [32 empty] | NA | Yes | ChatGPT | 10% to 20% | Yes
2025-05-21 12:44 | Jegadeesh Santhana Krishnan | Ankur Sachdeva | Dev | Chipmuks | 4 | Yes | task prioritization | Yes | Balanced | 4 | 4 | 4 | 4 | Yes | 4 | 4 | Scrum Team | 4 | 4 | Yes | YES | Multiple | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Committed Epic Prioritisation | Sprint Planning | KT and recording repository | Blocking Scope change | Better & transparent commitments | Ad-hoc Tasks & improper prioritisation | Less than 5% |  | YES | - |  |  | Yes | ChatGPT, CoPilot, Claude | 20% to 30% | Yes
2025-05-21 12:49 | Krishna Kishore Mothukuri | Ajitkumar kaller | Dev & Scrum Master | Velocity | 5 | Yes | We are progressing towards having the analysis, Technical Designs (TDs) and POCs ready by the start of the next release, as we have begun working on them in the last (hardening) sprint. | Yes | Balanced | 5 | 5 | 5 | 5 | Partially/Incomplete | 4 | 5 | Scrum Team | 5 | 5 | Yes | YES | Moderate | Less than 10% | Yes | Moderate | Over Utilised (90% and Above) | Some Information but still need further details | Yes | Well Managed | Continuous Epic Grooming | Sprint Planning | Tech Design | Change in Due date and QA Sign off Date restrictions | Risk call out (Release Confluence Page) | Delayed Test Designs | My role involves process improvement and enablement (EM's, SM's & Other folks responsible for process streamlining) |  | YES | no |  |  | Yes | ChatGPT, CoPilot, Gemini | 30% and Above | Yes
2025-05-21 12:52 | Mujtaba Ahmad | Priya Vanteru | Dev | Indus | 4 | Yes | Reserving bandwidth for predictable ad hoc tasks | Yes | Balanced | 4 | 5 | 5 | 4 | Yes | 4 | 4 | Individual | 4 | 4 | Yes | Moderately | Moderate | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Average | Continuous Epic Grooming | Sprint Closure/review | CI/CD, Testing & Continuous planning | Risk call out during Weekly SoS | Release Planning, Strategy & Schedule (Proper Checkpoint and dates on jira tickets) | Communication gap b/w dependent teams | More Than 5% but less than 10% |  | YES | NA |  |  | Yes | ChatGPT, CoPilot | 10% to 20% | Yes
2025-05-21 13:15 | Jegadeesh Santhana Krishnan | Subhan Ansari | Dev | Aliens | 2 | No |  | Yes | Chaotic | 4 | 5 | 2 | 5 | Partially/Incomplete | 4 | 3 | Individual | 4 | 3 | Yes | YES | Moderate | Less than 10% | No | Multiple | Over Utilised (90% and Above) | Optimal information available | Yes | Well Managed | Monitoring and Controlling Progress | Sprint Planning | KT and recording repository | Blocking Scope change | None | PR Merges | More Than 5% but less than 10% |  | YES | we should not pickup moretasks than available bandwidth |  |  | Yes | ChatGPT | 10% or below | Yes
2025-05-21 13:27 | Jegadeesh Santhana Krishnan | Ashok Kumar Dantham | Dev | Iris | 5 | Yes | Action item was to start backlog grooming at the end of sprint and pick up the spike related task in hardening sprint and New automation test cases added in the suites should be reviewed and fixed by Author. So we started checking on these points and followed backlog grooming at the end of sprint 2 and picked up spike related task. | Yes | Well Managed | 5 | 5 | 5 | 5 | Yes | 5 | 5 | Individual | 5 | 5 | Yes | YES | Moderate | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Some Information but still need further details | Yes | Well Managed | Monitoring and Controlling Progress | Sprint Planning | Intra Team Collaboration - Dependency linking on Jira by Individual owners | Blocking Scope change | Effective communication | Delay in commitments from dependant team | Less than 5% |  | YES |  |  |  | Yes | ChatGPT, CoPilot | 10% to 20% | Yes
2025-05-21 14:01 | Jegadeesh Santhana Krishnan | Subhan Ansari | Dev | Aliens | 4 | Yes | na | Yes | Balanced | 4 | 4 | 5 | 4 | Yes | 4 | 4 | Individual | 5 | 4 | Yes | YES | Moderate | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Some Information but still need further details | Yes | Well Managed | Epic Breakdown | Sprint Planning | Tech Design | Risk call out during Weekly SoS | Effective communication | Improper Epic Breakdown & Estimations - Missing Sprint Backlog | More Than 5% but less than 10% |  | YES | na |  |  | Yes | ChatGPT, CoPilot, Perplexity, Gemini, GitHub AI review | 20% to 30% | Yes
2025-05-21 16:26 | Mohammed Fayaz | Varun Batra | QA | Tranformers | 4 | Yes | - | Yes | Well Managed | 5 | 5 | 4 | 4 | Yes | 5 | 4 | Scrum Team | 4 | 4 | Yes | YES | Moderate | Less than 10% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Epic Breakdown | Sprint Planning | CI/CD, Testing & Continuous planning | Blocking Scope change | Better & transparent commitments | Ad-hoc Tasks & improper prioritisation | More Than 5% but less than 10% | - | YES | - |  |  | Yes | ChatGPT | 10% or below | Yes
2025-05-21 16:41 | Mohammed Fayaz | Varun Batra | QA | Skywalker | 5 | Yes | No action item was added | Yes | Balanced | 5 | 5 | 5 | 5 | Yes | 5 | 5 | Scrum Team | 5 | 5 | Yes | YES | Moderate | Less than 10% | Yes | Moderate | Over Utilised (90% and Above) | Optimal information available | Yes | Well Managed | Committed Epic Prioritisation | Sprint Planning | Ad-hoc requests prioritisation and acceptance | Strict Bug SLA's | Better Estimations & Epic Breakdown | CS Bugs higher than the reserved Capacity | Less than 5% |  | YES | no |  |  | Yes | ChatGPT | 10% to 20% | Yes
2025-05-21 16:52 | Mohammed Fayaz | Varun Batra | QA | Sharks | 5 | Yes | Update story point before sprint starts. | Yes | Balanced | 5 | 5 | 5 | 5 | Yes |  | 5 | Individual | 5 |  | Yes | YES | Moderate | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Epic Breakdown | Sprint Planning | Backlog & CS bugs prioritisation | Strict Bug SLA's | None | Non Release Activities | More Than 5% but less than 10% |  | YES | NO |  |  | Yes | ChatGPT | 10% or below | Yes
2025-05-21 18:16 | Mohammed Fayaz | Komal Varma | QA | Aurora | 4 | Yes | na | Yes | Balanced | 4 | 4 | 4 | 4 | Yes | 4 | 3 | Individual | 4 | 4 | Yes | YES | Moderate | Less than 10% | Yes | Moderate | Balanced (80% - 90%) | Some Information but still need further details | Not aware of any such initiative. Though the release coordination among teams was better than previous releases among teams | Average | Code Freeze Milestones and hardening phase | Sprint Planning | Non Release Activity Identification & capacity reserve | Change in Due date and QA Sign off Date restrictions | Release Planning, Strategy & Schedule (Proper Checkpoint and dates on jira tickets) | Delay in commitments from dependant team | Less than 5% |  | YES | na |  |  | Yes | ChatGPT, CoPilot | 10% to 20% | Yes
2025-05-21 18:23 | Mohammed Fayaz | Komal Varma | QA | Eirene | 3 | No |  | Yes | Balanced | 4 | 5 | 5 | 5 | Yes | 4 | 4 | Individual | 4 | 4 | Yes | YES | Moderate | Less than 10% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Committed Epic Prioritisation | Sprint Closure/review | Jira Details - Epic breakdown, DoD, Exit criteria, CS Bugs | Change in Due date and QA Sign off Date restrictions | Better Estimations & Epic Breakdown | Delayed Response on open Queries, need multiple followups | Less than 5% |  | YES | NO |  |  | Yes | ChatGPT, CoPilot | 10% or below | Yes
2025-05-21 18:26 | Mohammed Fayaz | Tharuni Sai Idupulapati | QA | Apollo | 4 | Yes | updating the dates of the trackers, team are updating post dsu's | Yes | Balanced | 4 | 4 | 5 | 4 | Yes | 5 | 4 | Scrum Team | 5 | 4 | Yes | Moderately | Moderate | Less than 10% | Yes | Multiple | Over Utilised (90% and Above) | Some Information but still need further details | Not aware of any such initiative. Though the release coordination among teams was better than previous releases among teams | Average | Epic Breakdown | Sprint Planning | Ad-hoc requests prioritisation and acceptance | Change in Due date and QA Sign off Date restrictions | Effective communication | Ad-hoc Tasks & improper prioritisation | Less than 5% |  | YES | NA |  |  | Yes | ChatGPT, CoPilot, Gemini | 10% to 20% | Yes
2025-05-21 18:30 | Mohammed Fayaz | SathishKumar D | QA | Optimus | 4 | Yes | NA | No | [32 empty] | Automation framework changes and developments | Yes | ChatGPT, CoPilot | 20% to 30% | Yes
2025-05-21 18:36 | Mohammed Fayaz | Komal Varma | QA | Helios | 5 | Yes | Add stories before sprint planning and no stories has been added post planning and all the trackers were closed before sprint closure | Yes | Chaotic | 4 | 3 | 3 | 5 | Yes | 3 | 4 | Scrum Team | 5 | 5 | Yes | YES | Moderate | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Some Information but still need further details | Yes | Well Managed | Code Freeze Milestones and hardening phase | Sprint Closure/review | Ad-hoc requests prioritisation and acceptance | Risk call out during Weekly SoS | Efficient Jira Usage (New Fields such as - Due date, QA Lead, QA Involvement, QA Signoff date) | Ad-hoc Tasks & improper prioritisation | More than 20% | NA | YES | NA | NA |  | Yes | ChatGPT | 10% or below | Yes
2025-05-21 19:25 | Mohammed Fayaz | Komal Varma | QA & Scrum Master | Iris | 4 | Yes | Implement internal feature freeze one week before code freeze so that QA will get enough time for testing and dev will get time for automation and bugs | Yes | Well Managed | 4 | 4 | 5 | 4 | Yes | 4 | 4 | Individual | 5 | 4 | Yes | YES | Moderate | 10% to 20% | Yes | Moderate | Over Utilised (90% and Above) | Some Information but still need further details | Yes | Well Managed | Continuous Epic Grooming | Sprint Closure/review | Non Release Activity Identification & capacity reserve | Blocking Scope change | Sprint Planning Structure | Delayed Response on open Queries, need multiple followups | More Than 5% but less than 10% | As compared to prev release it went well | YES | "To further enhance and streamline the release process, it is recommended that scope changes during an active sprint be avoided or minimized to maintain focus, efficiency, and timely delivery." |  |  | Yes | ChatGPT | 10% to 20% | Yes
2025-05-21 20:21 | Krishna Kishore Mothukuri | Krishna Kishore Mothukuri | EM |  |  |  |  | Yes | Well Managed | 5 | 5 | 5 | 5 | Partially/Incomplete | 5 | 5 | Scrum Team | 5 | 4 | Yes | YES | Moderate | Less than 10% | Yes | None | Balanced (80% - 90%) | Some Information but still need further details | Yes | Well Managed | Continuous Epic Grooming | Sprint Planning | Jira Details - Epic breakdown, DoD, Exit criteria, CS Bugs | Strict Bug SLA's | Effective communication | Communication gap b/w dependent teams | My role involves process improvement and enablement (EM's, SM's & Other folks responsible for process streamlining) | No | YES | No | There were some confusion on closing bugs type, this was brought up with JIRA admin. |  | Yes | ChatGPT | 10% to 20% | Yes
2025-05-21 20:22 | Mohammed Fayaz | Komal Varma | QA | Pheonix | 5 | Yes | adhering to in-sprint story closure | Yes | Balanced | 5 | 5 | 5 | 5 | Yes | 5 | 5 | Individual | 5 | 5 | Yes | YES | Multiple | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Committed Epic Prioritisation | Sprint Planning | Ad-hoc requests prioritisation and acceptance | Risk call out during Weekly SoS | Sprint Planning Structure | Ad-hoc Tasks & improper prioritisation | More than 10% but Less than 20% | NA | YES | NA | NA |  | Yes | ChatGPT, Gemini | 10% or below | Yes
2025-05-21 20:38 | Mohammed Fayaz | Komal Varma | QA | Helios | 4 | Yes | The tasks will be created on the sprint planning day and closed within the sprint mostly | Yes | Balanced | 4 | 4 | 4 | 5 | Yes | 4 | 4 | SME/Epic Owner/EM/QM (Pre Defined Efforts Estimates) | 4 | 4 | Yes | YES | Moderate | More than 30% | Yes | None | Balanced (80% - 90%) | Optimal information available | Yes | Average | Committed Epic Prioritisation | Sprint Retrospective | Backlog & CS bugs prioritisation | Risk call out during Weekly SoS | Work allocation with sufficient capacity reserve | Modifications on Approved Tech designs | More than 10% but Less than 20% |  | Not Efficiently | No |  |  | Yes | ChatGPT, CoPilot | 10% to 20% | Yes
2025-05-21 20:45 | Umesh Radhakrishna | Umesh Radhakrishna | Architect/Individual Contributors |  |  |  |  | No | [33 empty] | Yes | ChatGPT | 10% to 20% | Yes
2025-05-21 21:00 | Mohammed Fayaz | Mohammed Fayaz | QA | Individual Capacity, Not Associated with any particular team | 1 | Yes | Individual contributor not associated with any team | Yes | Well Managed | 5 | 5 | 5 | 5 | Yes | 5 | 5 | Scrum Team | 5 | 5 | Yes | YES | Multiple | 10% to 20% | Yes | None | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Monitoring and Controlling Progress | Sprint Planning | Test Design | Strict Bug SLA's | Release Planning, Strategy & Schedule (Proper Checkpoint and dates on jira tickets) | Intra team collaboration | My role involves process improvement and enablement (EM's, SM's & Other folks responsible for process streamlining) |  | YES | No |  |  | Yes | ChatGPT | 20% to 30% | Yes
2025-05-21 21:15 | Mohammed Fayaz | Komal Varma | QA | Velocity | 4 | Yes | updating the delay in tickets for discussing in Retrospective | Yes | Well Managed | 4 | 4 | 4 | 4 | Yes | 4 | 3 | Scrum Team | 4 | 4 | Yes | YES | Moderate | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Some Information but still need further details | Yes | Well Managed | Continuous Epic Grooming | Sprint Planning | Intra Team Collaboration - Dependency linking on Jira by Individual owners | Blocking Scope change | Work allocation with sufficient capacity reserve | Intra team collaboration | More Than 5% but less than 10% |  | YES | Incremental builds from the initial days of the sprints |  |  | Yes | ChatGPT | 10% to 20% | Yes
2025-05-21 22:50 | Mohammed Fayaz | Komal Varma | QA | Helios | 5 | Yes | maintaining proper story points | Yes | Balanced | 5 | 5 | 5 | 5 | Yes | 5 | 5 | SME/Epic Owner/EM/QM (Pre Defined Efforts Estimates) | 5 | 5 | No | YES | Moderate | Less than 10% | No | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Average | Code Freeze Milestones and hardening phase | Sprint Retrospective | Non Release Activity Identification & capacity reserve | Risk call out during Weekly SoS | Sprint Planning Structure | CS Bugs higher than the reserved Capacity | More than 10% but Less than 20% |  | YES | no |  |  | Yes | ChatGPT | 10% or below | Yes
2025-05-21 23:11 | Mohammed Fayaz | Komal Varma | QA | Chloris | 4 | Yes | scope/requirement changes till code freeze date, this was resolved this release | Yes | Balanced | 4 | 4 | 4 | 5 | Yes | 4 | 4 | Scrum Team | 4 | 4 | Yes | YES | Multiple | 20% to 30% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Continuous Epic Grooming | Sprint Planning | Ad-hoc requests prioritisation and acceptance | Blocking Scope change | Reduced over commit | Non Release Activities | More than 20% |  | YES | Adhoc tasks planning |  |  | Yes | ChatGPT | 10% to 20% | Yes
2025-05-22 08:51 | Mujtaba Ahmad | Mujtaba Ahmad | EM |  |  |  |  | Yes | Balanced | 5 | 5 | 5 | 5 | Yes | 5 | 5 | Scrum Team | 5 | 5 | Yes | YES | Moderate | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Committed Epic Prioritisation | Sprint Planning | CI/CD, Testing & Continuous planning | Blocking Scope change | Better & transparent commitments | PR Merges | My role involves process improvement and enablement (EM's, SM's & Other folks responsible for process streamlining) |  | YES | Optimise CI and build time | None |  | Yes | ChatGPT | 10% to 20% | Yes
2025-05-22 09:15 | Mujtaba Ahmad | Mujtaba Ahmad | Dev | Ganges | 4 | Yes | Continuous RMS Test failures are being addressed | Yes | Well Managed | 5 | 3 | 3 | 5 | Yes | 4 | 4 | Scrum Team | 5 | 4 | Yes | YES | Moderate | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Release Kick Off | Sprint Closure/review | KT and recording repository | Risk call out during Weekly SoS | Efficient Jira Usage (New Fields such as - Due date, QA Lead, QA Involvement, QA Signoff date) | Intra team collaboration | Less than 5% |  | YES | No |  |  | Yes | ChatGPT, CoPilot, GitHub AI review | 10% to 20% | Yes
2025-05-22 09:33 | Mohammed Fayaz | Tharuni Sai Idupulapati | QA | Stark | 4 | Yes | sign-off delays should callout earlier | Yes | Balanced | 4 | 4 | 4 | 4 | Yes | 4 | 4 | Scrum Team | 4 | 4 | Yes | YES | Moderate | Less than 10% | No | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Monitoring and Controlling Progress | Sprint DSU's | Ad-hoc requests prioritisation and acceptance | Change in Due date and QA Sign off Date restrictions | Reduced over commit | Delayed Response on open Queries, need multiple followups | Less than 5% |  | YES | - |  |  | Yes | ChatGPT, CoPilot | 10% or below | Yes
2025-05-22 09:47 | Jegadeesh Santhana Krishnan | Chandra Sekhar Kusupati | EM |  |  |  |  | Yes | Well Managed | 5 | 5 | 5 | 5 | Yes | 5 | 5 | SME/Epic Owner/EM/QM (Pre Defined Efforts Estimates) | 5 | 5 | Yes | YES | Multiple | 10% to 20% | Yes | None | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Monitoring and Controlling Progress | Sprint Planning | Intra Team Collaboration - Dependency linking on Jira by Individual owners | Blocking Scope change | None | Delay in commitments from dependant team | My role involves process improvement and enablement (EM's, SM's & Other folks responsible for process streamlining) |  | YES | . |  |  | Yes | ChatGPT | 30% and Above | Yes
2025-05-22 10:06 | Mujtaba Ahmad | Raman Soni | Dev | Apollo | 5 | Yes | update the dates on Jira board on time | Yes | Balanced | 4 | 4 | 4 | 5 | Yes | 4 | 3 | Scrum Team | 3 | 3 | Yes | YES | Moderate | Less than 10% | No | Moderate | Balanced (80% - 90%) | Some Information but still need further details | Yes | Average | Epic Breakdown | Sprint Planning | Intra Team Collaboration - Dependency linking on Jira by Individual owners | Blocking Scope change | Work allocation with sufficient capacity reserve | Modifications on Approved Tech designs | Less than 5% |  | YES | Everything should be mentioned properly on Jira tracker. In zepher also when QA upload the test case they should check whether it is uploading everthing properly or not. This will reduce the time of the person who is automating those and to those who are fixing the test cases |  |  | Yes | ChatGPT | Just started using AI, need time to quantify | Yes
2025-05-22 10:13 | Mujtaba Ahmad | Raman Soni | Dev & Scrum Master | Ganges | 4 | Yes | Team had to improve on JIRA guidelines. Team is improving day by day | Yes | Well Managed | 4 | 5 | 5 | 5 | Yes | 5 | 4 | Scrum Team | 4 | 4 | Yes | YES | Moderate | Less than 10% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Not aware of any such initiative. Though the release coordination among teams was better than previous releases among teams | Well Managed | Code Freeze Milestones and hardening phase | Sprint Closure/review | CI/CD, Testing & Continuous planning | Risk call out during Weekly SoS | Efficient Jira Usage (New Fields such as - Due date, QA Lead, QA Involvement, QA Signoff date) | Ad-hoc Tasks & improper prioritisation | More Than 5% but less than 10% |  | YES | NO |  |  | Yes | CoPilot | 10% to 20% | Yes
2025-05-22 10:18 | Krishna Kishore Mothukuri | Ajitkumar kaller | Dev | Velocity | 5 | Yes | Updating the JIRA timely with update | Yes | Balanced | 4 | 4 | 4 | 4 | Yes | 4 | 4 | Scrum Team | 5 | 5 | Yes | YES | Moderate | 10% to 20% | Yes | None | Balanced (80% - 90%) | Some Information but still need further details | Yes | Average | Committed Epic Prioritisation | Sprint Planning | Backlog & CS bugs prioritisation | Blocking Scope change | Better Estimations & Epic Breakdown | Ad-hoc Tasks & improper prioritisation | More Than 5% but less than 10% | NO | YES | NO | NO |  | Yes | ChatGPT, CoPilot, Langchain | 10% to 20% | Yes
2025-05-22 10:22 | Mohammed Fayaz | Varun Batra | QA | Chipmuks | 5 | Yes | NA | Yes | Well Managed | 5 | 5 | 4 | 5 | Yes | 5 | 5 | Scrum Team | 5 | 4 | Yes | YES | Moderate | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Some Information but still need further details | Yes | Average | Committed Epic Prioritisation | Sprint Retrospective | Jira Details - Epic breakdown, DoD, Exit criteria, CS Bugs | Blocking Scope change | None | Ad-hoc Tasks & improper prioritisation | More Than 5% but less than 10% | NA | YES | NA | NA |  | Yes | ChatGPT, CoPilot | Just started using AI, need time to quantify | Yes
2025-05-22 10:26 | Mohammed Fayaz | Tharuni Sai Idupulapati | QA | Ganges | 4 | Yes | Documenting devops trackers for env variable changes | Yes | Balanced | 4 | 4 | 4 | 4 | Partially/Incomplete | 4 | 4 | Scrum Team | 4 | 4 | Yes | YES | Moderate | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Some Information but still need further details | Yes | Average | Monitoring and Controlling Progress | Sprint Planning | Jira Details - Epic breakdown, DoD, Exit criteria, CS Bugs | Strict Bug SLA's | Effective communication | Communication gap b/w dependent teams | More Than 5% but less than 10% |  | YES | No |  |  | Yes | ChatGPT, CoPilot | 10% to 20% | Yes
2025-05-22 10:27 | Jegadeesh Santhana Krishnan | Ashok Kumar Dantham | Dev | Iris | 5 | Yes | Implement internal feature freeze one week before code freeze so that QA wil get enought time for testing and dev will get time for automation and bugs. | Yes | Balanced | 5 | 5 | 4 | 5 | Yes | 5 | 5 | Individual | 5 | 5 | Yes | YES | Moderate | Less than 10% | Yes | Moderate | Balanced (80% - 90%) | Some Information but still need further details | Yes | Well Managed | Epic Breakdown | Sprint Planning | Intra Team Collaboration - Dependency linking on Jira by Individual owners | Blocking Scope change | Work allocation with sufficient capacity reserve | Communication gap b/w dependent teams | More Than 5% but less than 10% |  | YES | This seems good |  |  | Yes | ChatGPT, CoPilot, GitHub AI review | 10% to 20% | Yes
2025-05-22 10:28 | Mujtaba Ahmad | Priya Vanteru | Dev | Indus | 4 | Yes | Continous grooming | Yes | Balanced | 4 | 4 | 4 | 4 | Yes | 4 | 4 | Individual | 4 | 4 | Yes | YES | Moderate | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Continuous Epic Grooming | Sprint Planning | Jira Details - Epic breakdown, DoD, Exit criteria, CS Bugs | Strict Bug SLA's | Better Estimations & Epic Breakdown | Ad-hoc Tasks & improper prioritisation | Less than 5% |  | YES | no |  |  | Yes | ChatGPT, CoPilot, GitHub AI review | 20% to 30% | Yes
2025-05-22 10:33 | Jegadeesh Santhana Krishnan | Ankur Sachdeva | Dev | Echo | 3 | Yes | N/A | Yes | Balanced | 3 | 3 | 3 | 3 | Yes | 3 | 3 | Individual | 3 | 3 | Yes | YES | Multiple | More than 30% | No | Multiple | Balanced (80% - 90%) | Some Information but still need further details | Not aware of any such initiative. Though the release coordination among teams was better than previous releases among teams | Average | Epic Breakdown | Sprint DSU's | Tech Design | Risk call out during Weekly SoS | Better & transparent commitments | Ad-hoc Tasks & improper prioritisation | More than 20% |  | YES | N/A |  |  | Yes | ChatGPT, CoPilot, Claude | 30% and Above | Yes
2025-05-22 10:36 | Jegadeesh Santhana Krishnan | Anusha Badveeti | Dev & Scrum Master | Tranformers | 5 | Yes | The issues were regarding the change in ticket priority order during the sprint. But after an internal team meeting it is decided to keep team level adhoc task quota and once if there is no p0 priority item the existing priority ticket won't be changed | Yes | Balanced | 5 | 4 | 4 | 4 | Yes | 4 | 5 | Scrum Team | 5 | 5 | Yes | YES | Moderate | 10% to 20% | Yes | Multiple | Balanced (80% - 90%) | Some Information but still need further details | Yes | Average | Monitoring and Controlling Progress | Sprint Retrospective | Intra Team Collaboration - Dependency linking on Jira by Individual owners | Blocking Scope change | Release Planning, Strategy & Schedule (Proper Checkpoint and dates on jira tickets) | Ad-hoc Tasks & improper prioritisation | My role involves process improvement and enablement (EM's, SM's & Other folks responsible for process streamlining) |  | YES | none |  |  | Yes | ChatGPT, CoPilot, Gemini | 10% to 20% | Yes
2025-05-22 10:38 | Mujtaba Ahmad | Mujtaba Ahmad | EM |  |  |  |  | No | [32 empty] | Managing team | No | ChatGPT, Gemini | Just started using AI, need time to quantify | Yes
2025-05-22 10:41 | Krishna Kishore Mothukuri | Krishna Kishore Mothukuri | Dev | Inceris | 2 | No |  | No | [32 empty] | Localsetup Framework Development | Yes | ChatGPT, CoPilot, Gemini | 30% and Above | Yes
2025-05-22 10:44 | Jegadeesh Santhana Krishnan | Rajesh Subramani | Dev | Hercules | 4 | Yes | Complete the committed epics | Yes | Balanced | 4 | 4 | 4 | 4 | Yes | 4 | 4 | Individual | 4 | 4 | Yes | Moderately | Moderate | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Some Information but still need further details | Yes | Average | Continuous Epic Grooming | Sprint Planning | Tech Design | Blocking Scope change | Better Estimations & Epic Breakdown | Ad-hoc Tasks & improper prioritisation | More than 10% but Less than 20% |  | YES | NA |  |  | Yes | ChatGPT, CoPilot | 10% to 20% | Yes
2025-05-22 10:49 | Jegadeesh Santhana Krishnan | Jegadeesh Santhana Krishnan | EM |  |  |  |  | Yes | Well Managed | 4 | 5 | 5 | 5 | Yes | 5 | 4 | Individual | 4 | 4 | Yes | YES | Moderate | 10% to 20% | Yes | None | Balanced (80% - 90%) | Some Information but still need further details | Yes | Average | Continuous Epic Grooming | Sprint DSU's | Jira Details - Epic breakdown, DoD, Exit criteria, CS Bugs | Change in Due date and QA Sign off Date restrictions | Sprint Planning Structure | Delay in commitments from dependant team | My role involves process improvement and enablement (EM's, SM's & Other folks responsible for process streamlining) |  | YES | Continuous backlog grooming should be enforced for better planning |  |  | Yes | CoPilot, GitHub AI review | 10% or below | Yes
2025-05-22 10:57 | Jegadeesh Santhana Krishnan | Selvakumar Thiyagarajan | Dev | Pheonix | 5 | Yes | Mainly bugs and engineering epics. | Yes | Well Managed | 5 | 5 | 5 | 5 | Yes | 5 | 5 | Scrum Team | 5 | 5 | Yes | YES | Multiple | Less than 10% | Yes | None | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Continuous Epic Grooming | Sprint Closure/review | Jira Automation | Risk call out during Weekly SoS | Release Planning, Strategy & Schedule (Proper Checkpoint and dates on jira tickets) | Delay in commitments from dependant team | Less than 5% |  | YES | NA |  |  | Yes | CoPilot | 30% and Above | Yes
2025-05-22 10:57 | Jegadeesh Santhana Krishnan | Selvakumar Thiyagarajan | Dev & Scrum Master | Chloris | 4 | Yes | Dependency on other teams and getting delayed | Yes | Well Managed | 5 | 5 | 5 | 5 | Yes | 5 | 5 | Individual | 5 | 5 | Yes | YES | Moderate | Less than 10% | Yes | None | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Code Freeze Milestones and hardening phase | Sprint Planning | Intra Team Collaboration - Dependency linking on Jira by Individual owners | Change in Due date and QA Sign off Date restrictions | Sprint Planning Structure | Delay in commitments from dependant team | My role involves process improvement and enablement (EM's, SM's & Other folks responsible for process streamlining) |  | YES | NIL |  |  | Yes | CoPilot | 10% to 20% | Yes
2025-05-22 11:01 | Jegadeesh Santhana Krishnan | Rajesh Subramani | Dev | Helios | 5 | Yes | sp and time allocation was done properly | Yes | Balanced | 5 | 5 | 4 | 5 | Yes | 5 | 5 | Individual | 5 | 5 | Yes | YES | Moderate | 20% to 30% | Yes | Moderate | Over Utilised (90% and Above) | Optimal information available | Yes | Well Managed | Committed Epic Prioritisation | Sprint Planning | CI/CD, Testing & Continuous planning | Strict Bug SLA's | Work allocation with sufficient capacity reserve | CS Bugs higher than the reserved Capacity | More than 20% |  | YES | No |  |  | Yes | ChatGPT, CoPilot | 10% to 20% | Yes
2025-05-22 11:05 | Jegadeesh Santhana Krishnan | Chandra Sekhar Kusupati | Dev | Eirene | 5 | No |  | Yes | Well Managed | 5 | 5 | 5 | 5 | Yes | 5 | 5 | Individual | 5 | 5 | Yes | YES | Moderate | Less than 10% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Monitoring and Controlling Progress | Sprint Closure/review | Intra Team Collaboration - Dependency linking on Jira by Individual owners | Blocking Scope change | Release Planning, Strategy & Schedule (Proper Checkpoint and dates on jira tickets) | Intra team collaboration | Less than 5% |  | YES | No |  |  | Yes | ChatGPT, CoPilot, GitHub AI review | 10% or below | Yes
2025-05-22 11:44 | Jegadeesh Santhana Krishnan | Ramakrishna Grandhi | Dev & Scrum Master | Tintin | 4 | No |  | Yes | Balanced | 4 | 4 | 5 | 5 | Yes | 4 | 4 | Individual | 4 | 4 | Yes | YES | Moderate | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Monitoring and Controlling Progress | Sprint Planning | Jira Details - Epic breakdown, DoD, Exit criteria, CS Bugs | Risk call out during Weekly SoS | Better Estimations & Epic Breakdown | Ad-hoc Tasks & improper prioritisation | More Than 5% but less than 10% |  | YES | na | na |  | Yes | ChatGPT | 10% to 20% | Yes
2025-05-22 11:46 | Jegadeesh Santhana Krishnan | Anusha Badveeti | Dev | Dynamos | 5 | Yes | Proper planning of upcoming Releases | Yes | Well Managed | 5 | 5 | 5 | 5 | Yes | 5 | 5 | Scrum Team | 5 | 5 | Yes | YES | Moderate | Less than 10% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | No | Well Managed | Committed Epic Prioritisation | Sprint Closure/review | Ad-hoc requests prioritisation and acceptance | Risk call out during Weekly SoS | Better & transparent commitments | PR Merges | Less than 5% |  | YES | NA |  |  | Yes | CoPilot, Gemini | Just started using AI, need time to quantify | Yes
2025-05-22 11:47 | Jegadeesh Santhana Krishnan | Subhan Ansari | Dev | Skywalker | 5 | Yes | Prepare Backlog/epics for the release | Yes | Balanced | 4 | 4 | 4 | 4 | Yes | 4 | 4 | Scrum Team | 4 | 4 | Yes | YES | Moderate | Less than 10% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Continuous Epic Grooming | Sprint Planning | Backlog & CS bugs prioritisation | Blocking Scope change | Better Estimations & Epic Breakdown | Ad-hoc Tasks & improper prioritisation | Less than 5% |  | YES | NA |  |  | Yes | ChatGPT | 10% or below | Yes
2025-05-22 11:50 | Jegadeesh Santhana Krishnan | Ramakrishna Grandhi | Dev & Scrum Master | Sharks | 5 | Yes | na | Yes | Balanced | 4 | 4 | 4 | 4 | Yes | 5 | 5 | Scrum Team | 5 | 5 | Yes | YES | Multiple | 20% to 30% | Yes | None | Over Utilised (90% and Above) | Optimal information available | Yes | Well Managed | Code Freeze Milestones and hardening phase | Sprint Closure/review | Ad-hoc requests prioritisation and acceptance | Risk call out during Weekly SoS | None | Intra team collaboration | My role involves process improvement and enablement (EM's, SM's & Other folks responsible for process streamlining) |  | YES | na | na |  | Yes | ChatGPT, CoPilot, Gemini | 10% or below | Yes
2025-05-22 11:51 | Jegadeesh Santhana Krishnan | Subhan Ansari | Dev | Skywalker | 4 | No |  | Yes | Balanced | 4 | 4 | 4 | 4 | Yes | 4 | 4 | Scrum Team | 4 | 4 | Yes | YES | Moderate | 20% to 30% | Yes | Moderate | Balanced (80% - 90%) | Some Information but still need further details | Yes | Well Managed | Epic Breakdown | Sprint Planning | KT and recording repository | Change in Due date and QA Sign off Date restrictions | Effective communication | Communication gap b/w dependent teams | More Than 5% but less than 10% |  | YES | None |  |  | Yes | CoPilot | 10% to 20% | Yes
2025-05-22 11:53 | Jegadeesh Santhana Krishnan | Ankur Sachdeva | Dev | Echo | 4 | No |  | Yes | Balanced | 3 | 4 | 5 | 5 | Yes | 4 | 4 | Scrum Team | 4 | 4 | Yes | Moderately | Multiple | Less than 10% | Yes | Moderate | Balanced (80% - 90%) | Some Information but still need further details | Yes | Average | Monitoring and Controlling Progress | Sprint Planning | Ad-hoc requests prioritisation and acceptance | Blocking Scope change | Work allocation with sufficient capacity reserve | Communication gap b/w dependent teams | Less than 5% |  | YES | NA |  |  | Yes | ChatGPT, CoPilot, GitHub AI review | 10% to 20% | Yes
2025-05-22 11:56 | Jegadeesh Santhana Krishnan | Ankur Sachdeva | Dev | Echo | 4 | Yes | Less parallel work, i was able to get it reduced the last 1.5 sprints | Yes | Balanced | 4 | 4 | 4 | 4 | Yes | 4 | 4 | Individual | 4 | 4 | Yes | YES | Moderate | Less than 10% | Yes | Moderate | Over Utilised (90% and Above) | Optimal information available | Not aware and did not find any significant change in the release coordination among teams | Average | Monitoring and Controlling Progress | Sprint Closure/review | KT and recording repository | Blocking Scope change | None | Delayed Response on open Queries, need multiple followups | Less than 5% |  | YES | no |  |  | Yes | ChatGPT | 10% or below | Yes
2025-05-22 12:06 | Jegadeesh Santhana Krishnan | Selvakumar Thiyagarajan | Dev | Sharks | 4 | Yes | NA | Yes | Balanced | 4 | 4 | 4 | 4 | Yes |  | 4 | Individual | 4 | 4 | Yes | YES | Moderate | Less than 10% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Not aware of any such initiative. Though the release coordination among teams was better than previous releases among teams | Average | Code Freeze Milestones and hardening phase | Sprint Planning | Ad-hoc requests prioritisation and acceptance | Blocking Scope change | Effective communication | Reviews | Less than 5% |  | YES | NA |  |  | Yes | CoPilot | 10% or below | Yes
2025-05-22 12:08 | Jegadeesh Santhana Krishnan | Ankur Sachdeva | Dev | Chipmuks | 5 | Yes | Bette planning | Yes | Balanced | 4 | 4 | 4 | 4 | Partially/Incomplete | 4 | 5 | Scrum Team | 5 | 5 | Yes | YES | Moderate | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Some Information but still need further details | Not aware of any such initiative. Though the release coordination among teams was better than previous releases among teams | Average | Committed Epic Prioritisation | Sprint Planning | Bugs Management & Deferring | Risk call out during Weekly SoS | Sprint Planning Structure | PR Merges | More Than 5% but less than 10% |  | YES | No | No |  | Yes | ChatGPT, CoPilot, Gemini | 20% to 30% | Yes
2025-05-22 12:08 | Jegadeesh Santhana Krishnan | Rajesh Subramani | Dev | Hercules | 5 | No |  | Yes | Balanced | 5 | 5 | 4 | 5 | Yes | 5 | 5 | Individual | 4 | 5 | Yes | YES | Moderate | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Continuous Epic Grooming | Sprint Planning | KT and recording repository | Blocking Scope change | Better & transparent commitments | Ad-hoc Tasks & improper prioritisation | More Than 5% but less than 10% |  | YES | Nil |  |  | Yes | ChatGPT, CoPilot | 10% to 20% | Yes
2025-05-22 12:10 | Jegadeesh Santhana Krishnan | Ramakrishna Grandhi | Dev | Sharks | 5 | Yes | Mandatory jira details better understanding of the ticket | Yes | Well Managed | 5 | 5 | 5 | 5 | Yes | 5 | 5 | Scrum Team | 5 | 5 | Yes | YES | Multiple | 10% to 20% | Yes | Moderate | Over Utilised (90% and Above) | Optimal information available | Yes | Well Managed | Epic Breakdown | Sprint Planning | Jira Details - Epic breakdown, DoD, Exit criteria, CS Bugs | Strict Bug SLA's | Sprint Planning Structure | Partial or missing details on Jira Trackers Description | More than 10% but Less than 20% |  | YES | Hardening should be strictly followed |  |  | Yes | ChatGPT, CoPilot, Gemini, GitHub AI review | 10% to 20% | Yes
2025-05-22 12:19 | Jegadeesh Santhana Krishnan | Ramakrishna Grandhi | Dev | Avengers | 5 | Yes | Better deadlines and planning | Yes | Well Managed | 5 | 5 | 5 | 5 | Yes | 5 | 5 | Scrum Team | 5 | 5 | Yes | YES | Multiple | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Monitoring and Controlling Progress | Sprint Planning | Jira Details - Epic breakdown, DoD, Exit criteria, CS Bugs | Change in Due date and QA Sign off Date restrictions | Release Planning, Strategy & Schedule (Proper Checkpoint and dates on jira tickets) | Improper Epic Breakdown & Estimations - Missing Sprint Backlog | More Than 5% but less than 10% |  | YES | N/A | N/A |  | Yes | ChatGPT | 30% and Above | Yes
2025-05-22 12:19 | Jegadeesh Santhana Krishnan | Ramakrishna Grandhi | Dev | Avengers | 4 | No |  | Yes | Chaotic | 4 | 5 | 2 | 4 | Yes | 4 | 4 | Individual | 5 | 4 | Yes | YES | Moderate | More than 30% | No | Multiple | Over Utilised (90% and Above) | Some Information but still need further details | Not aware of any such initiative. Though the release coordination among teams was better than previous releases among teams | Average | Committed Epic Prioritisation | Sprint Planning | Ad-hoc requests prioritisation and acceptance | Strict Bug SLA's | None | PR Merges | More Than 5% but less than 10% |  | YES | NA |  |  | Yes | CoPilot, Gemini | 10% or below | Yes
2025-05-22 12:33 | Jegadeesh Santhana Krishnan | Anusha Badveeti | Dev | Dynamos | 5 | No |  | Yes | Well Managed | 5 | 5 | 4 | 5 | Yes | 5 | 5 | Scrum Team | 5 | 5 | Yes | YES | Moderate | Less than 10% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Epic Breakdown | Sprint Closure/review | Jira Details - Epic breakdown, DoD, Exit criteria, CS Bugs | Risk call out during Weekly SoS | Release Planning, Strategy & Schedule (Proper Checkpoint and dates on jira tickets) | Modifications on Approved Tech designs | Less than 5% |  | YES | NA |  |  | Yes | ChatGPT, CoPilot | 10% to 20% | Yes
2025-05-22 12:42 | Jegadeesh Santhana Krishnan | Jegadeesh Santhana Krishnan | Architect/Individual Contributors |  |  |  |  | Yes | Balanced | 2 | 4 | 4 | 4 | Yes | 3 | 2 | Individual | 4 | 2 | Yes | Moderately | Moderate | 10% to 20% | Yes | None | Over Utilised (90% and Above) | Some Information but still need further details | Yes | Average | Epic Breakdown | Sprint Planning | Jira Details - Epic breakdown, DoD, Exit criteria, CS Bugs | Change in Due date and QA Sign off Date restrictions | Sprint Planning Structure | Reviews | My role involves process improvement and enablement (EM's, SM's & Other folks responsible for process streamlining) |  | YES | Adapting better techniques for Story sizing, Better methodologies for estimation and subtasking |  |  | Yes | ChatGPT, CoPilot, GitHub AI review | 10% or below | Yes
2025-05-22 12:56 | Mujtaba Ahmad | Mujtaba Ahmad | EM |  |  |  |  | No | [32 empty] | Managing and Planning for roadmap | Yes | ChatGPT, Gemini | 10% to 20% | Yes
2025-05-22 12:59 | Mohammed Fayaz | Mohammed Fayaz | EM |  |  |  |  | Yes | Balanced | 4 | 4 | 5 | 5 | Partially/Incomplete | 4 | 4 | Scrum Team | 4 | 4 | Yes | YES | Moderate | 10% to 20% | Yes | Moderate | Over Utilised (90% and Above) | Some Information but still need further details | Yes | Well Managed | Epic Breakdown | Sprint Planning | Jira Details - Epic breakdown, DoD, Exit criteria, CS Bugs | Change in Due date and QA Sign off Date restrictions | Effective communication | Missing SLA's for Bugs, Trackers on Jira | My role involves process improvement and enablement (EM's, SM's & Other folks responsible for process streamlining) |  | YES | Better Planning and efforts estimations. Before committing the Epic, complete the Work breakdown and efforts estimations | DueDate and QA sign-off slippages and better tracking |  | Yes | ChatGPT, Gemini | 20% to 30% | Yes
2025-05-22 13:10 | Diksha Khatri | Diksha Khatri | Dev | Titans | 5 | Yes | NA | Yes | Balanced | 5 | 5 | 5 | 5 | Yes | 5 | 5 | Scrum Team | 5 | 5 | Yes | YES | Moderate | 10% to 20% | Yes | Moderate | Over Utilised (90% and Above) | Optimal information available | Yes | Well Managed | Code Freeze Milestones and hardening phase | Sprint Closure/review | KT and recording repository | Risk call out during Weekly SoS | Work allocation with sufficient capacity reserve | Non Release Activities | Less than 5% |  | YES | NA |  |  | Yes | ChatGPT, CoPilot | 20% to 30% | Yes
2025-05-22 13:10 | Mohammed Fayaz | Anusha Jharupula | QA | Enigma | 4 | Yes | Providing clear acceptance criteria for QA to test | Yes | Balanced | 4 | 4 | 4 | 4 | Partially/Incomplete | 4 | 4 | Individual | 4 | 4 | Yes | YES | Moderate | Less than 10% | No | Moderate | Balanced (80% - 90%) | Optimal information available | Not aware of any such initiative. Though the release coordination among teams was better than previous releases among teams | Well Managed | Monitoring and Controlling Progress | Sprint Closure/review | Ad-hoc requests prioritisation and acceptance | Blocking Scope change | Effective communication | Delayed Response on open Queries, need multiple followups | Less than 5% | NA | YES | NA | NA |  | No | ChatGPT | Just started using AI, need time to quantify | No
2025-05-22 13:12 | Mujtaba Ahmad | Priya Vanteru | Dev & Scrum Master | Enigma | 4 | Yes | Working on the action item from the last retro, we have started including more detailed acceptance criteria in stories. | Yes | Balanced | 4 | 5 | 5 | 5 | Yes | 4 | 4 | Scrum Team | 5 | 4 | Yes | YES | Moderate | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Some Information but still need further details | Yes | Well Managed | Committed Epic Prioritisation | Sprint Planning | KT and recording repository | Blocking Scope change | Efficient Jira Usage (New Fields such as - Due date, QA Lead, QA Involvement, QA Signoff date) | Modifications on Approved Tech designs | My role involves process improvement and enablement (EM's, SM's & Other folks responsible for process streamlining) | We need more knowledge transfer sessions among team members to improve at writing technical designs and estimating story points. | YES | We need more knowledge transfer sessions among team members to improve at writing technical designs and estimating story points. | NA |  | Yes | ChatGPT, CoPilot | 10% or below | Yes
2025-05-22 13:30 | Mujtaba Ahmad | Raman Soni | Dev & Scrum Master | Stark | 4 | Yes | Main items generally are related to running test suites/inter team dependency management to catch any corner case bug which lands into prod | Yes | Balanced | 4 | 5 | 4 | 5 | Yes | 4 | 4 | Individual | 4 | 3 | Yes | YES | Moderate | Less than 10% | No | Moderate | Balanced (80% - 90%) | Some Information but still need further details | Yes | Well Managed | Monitoring and Controlling Progress | Sprint Planning | Backlog & CS bugs prioritisation | Risk call out during Weekly SoS | Release Planning, Strategy & Schedule (Proper Checkpoint and dates on jira tickets) | Ad-hoc Tasks & improper prioritisation | My role involves process improvement and enablement (EM's, SM's & Other folks responsible for process streamlining) |  | YES | No | No |  | Yes | ChatGPT, CoPilot | 10% or below | Yes
2025-05-22 13:48 | Mujtaba Ahmad | Mujtaba Ahmad | Dev | Titans | 5 | Yes | Netsuite Training | No | [33 empty] | Yes | CoPilot | 10% or below | Yes
2025-05-22 14:07 | Jegadeesh Santhana Krishnan | Chandra Sekhar Kusupati | Dev | Eirene | 5 | No |  | Yes | Well Managed | 4 | 5 | 5 | 5 | Yes | 5 | 5 | Individual | 5 | 5 | Yes | YES | Multiple | 10% to 20% | Yes | None | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Continuous Epic Grooming | Sprint Closure/review | Jira Details - Epic breakdown, DoD, Exit criteria, CS Bugs | Risk call out during Weekly SoS | Sprint Planning Structure | Ad-hoc Tasks & improper prioritisation | Less than 5% |  | YES | NA |  |  | Yes | ChatGPT, CoPilot, Gemini | 30% and Above | Yes
2025-05-22 14:13 | Jegadeesh Santhana Krishnan | Subhan Ansari | Dev & Scrum Master | Skywalker | 5 | Yes | Action item was to help new members with their first tasks | Yes | Balanced | 4 | 4 | 4 | 4 | Yes | 4 | 4 | SME/Epic Owner/EM/QM (Pre Defined Efforts Estimates) | 4 | 4 | Yes | YES | Moderate | 20% to 30% | Yes | Moderate | Balanced (80% - 90%) | Some Information but still need further details | Yes | Well Managed | Continuous Epic Grooming | Sprint Planning | Ad-hoc requests prioritisation and acceptance | Change in Due date and QA Sign off Date restrictions | Efficient Jira Usage (New Fields such as - Due date, QA Lead, QA Involvement, QA Signoff date) | Ad-hoc Tasks & improper prioritisation | More than 10% but Less than 20% |  | YES | Avoid frequent updates to integrator-adaptor |  |  | Yes | ChatGPT, CoPilot | 10% to 20% | Yes
2025-05-22 14:33 | Jegadeesh Santhana Krishnan | Jegadeesh Santhana Krishnan | EM |  |  |  |  | Yes | Well Managed | 5 | 5 | 5 | 5 | Yes | 5 | 5 | Scrum Team | 4 | 5 | Yes | YES | Multiple | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Code Freeze Milestones and hardening phase | Sprint Retrospective | KT and recording repository | Risk call out during Weekly SoS | Better Estimations & Epic Breakdown | CS Bugs higher than the reserved Capacity | My role involves process improvement and enablement (EM's, SM's & Other folks responsible for process streamlining) |  | YES | NA |  |  | Yes | ChatGPT | 30% and Above | Yes
2025-05-22 14:35 | Jegadeesh Santhana Krishnan | Jegadeesh Santhana Krishnan | EM |  |  |  |  | Yes | Well Managed | 5 | 5 | 5 | 5 | Yes | 5 | 5 | Scrum Team | 5 | 5 | Yes | YES | Moderate | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Release Kick Off | Sprint Closure/review | Bugs Management & Deferring | Blocking Scope change | Better Estimations & Epic Breakdown | Non Release Activities | My role involves process improvement and enablement (EM's, SM's & Other folks responsible for process streamlining) |  | YES | NA | NA |  | Yes | ChatGPT, Gemini | 10% to 20% | Yes
2025-05-22 14:35 | Jegadeesh Santhana Krishnan | Ashok Kumar Dantham | Dev | Aurora | 4 | Yes | better planning so no new tasks come mid-sprint | Yes | Well Managed | 4 | 5 | 4 | 5 | Yes | 5 | 4 | Scrum Team | 5 | 4 | Yes | YES | Moderate | Less than 10% | Yes | None | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Committed Epic Prioritisation | Sprint Planning | Intra Team Collaboration - Dependency linking on Jira by Individual owners | Blocking Scope change | Better Estimations & Epic Breakdown | Delay in commitments from dependant team | Less than 5% |  | YES | Fixed dates by dependent teams |  |  | Yes | ChatGPT, CoPilot, Gemini, GitHub AI review | 20% to 30% | Yes
2025-05-22 14:36 | Jegadeesh Santhana Krishnan | Anusha Badveeti | Dev | Tranformers | 4 | Yes | Better planning from last sprint | Yes | Balanced | 4 | 4 | 4 | 4 | Yes | 4 | 4 | Scrum Team | 4 | 4 | Yes | Moderately | Moderate | Less than 10% | No | Moderate | Over Utilised (90% and Above) | Optimal information available | Not aware of any such initiative. Though the release coordination among teams was better than previous releases among teams | Well Managed | Continuous Epic Grooming | Sprint Planning | KT and recording repository | Blocking Scope change | Sprint Planning Structure | Ad-hoc Tasks & improper prioritisation | More Than 5% but less than 10% |  | YES | no |  |  | Yes | ChatGPT, CoPilot | 10% or below | Yes
2025-05-22 14:38 | Jegadeesh Santhana Krishnan | Ankur Sachdeva | Dev | Echo | 3 | No |  | No | [32 empty] | Training | Yes | ChatGPT | Just started using AI, need time to quantify | Yes
2025-05-22 14:41 | Mujtaba Ahmad | Priya Vanteru | Dev | Enigma | 4 | Yes | - | Yes | Balanced | 4 | 4 | 4 | 4 | Yes | 4 | 4 | Scrum Team | 4 | 4 | Yes | YES | Moderate | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Average | Code Freeze Milestones and hardening phase | Sprint Planning | KT and recording repository | Risk call out during Weekly SoS | None | PR Merges | More than 10% but Less than 20% |  | YES | - |  |  | Yes | ChatGPT, CoPilot | 10% to 20% | Yes
2025-05-22 14:46 | Jegadeesh Santhana Krishnan | Anusha Badveeti | Dev | Tranformers | 5 | Yes | A considerable time was going in adhoc tasks, so moving forward a team level bandwidth for adhoc tasks is kept so that anyone can pick up these tasks. | Yes | Balanced | 5 | 5 | 5 | 5 | Yes | 5 | 5 | Individual | 5 | 5 | Yes | YES | Moderate | 10% to 20% | Yes | None | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Epic Breakdown | Sprint Closure/review | KT and recording repository | Blocking Scope change | Better Estimations & Epic Breakdown | PR Merges | Less than 5% |  | YES | Well managed |  |  | Yes | ChatGPT | Just started using AI, need time to quantify | Yes
2025-05-22 14:48 | Mujtaba Ahmad | Priya Vanteru | Dev & Scrum Master | Titans | 5 | Yes | review process was improved and people focused on closing the prs faster | Yes | Well Managed | 5 | 5 | 5 | 5 | Yes | 5 | 5 | Scrum Team | 5 | 5 | Yes | YES | Moderate | 10% to 20% | Yes | Multiple | Over Utilised (90% and Above) | Optimal information available | Yes | Well Managed | Release Kick Off | Sprint Closure/review | Ad-hoc requests prioritisation and acceptance | Risk call out during Weekly SoS | Release Planning, Strategy & Schedule (Proper Checkpoint and dates on jira tickets) | Delay in commitments from dependant team | My role involves process improvement and enablement (EM's, SM's & Other folks responsible for process streamlining) |  | YES | NA |  |  | Yes | ChatGPT, CoPilot | 10% to 20% | Yes
2025-05-22 16:03 | Mohammed Fayaz | Anusha Jharupula | QA | Titans | 5 | Yes | NA | Yes | Well Managed | 4 | 4 | 5 | 5 | Yes | 5 | 5 | Scrum Team | 5 | 5 | Yes | YES | Moderate | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Epic Breakdown | Sprint Closure/review | Ad-hoc requests prioritisation and acceptance | Risk call out during Weekly SoS | Better Estimations & Epic Breakdown | Non Release Activities | Less than 5% |  | YES | no |  |  | Yes | ChatGPT, CoPilot, Gemini | 10% to 20% | Yes
2025-05-22 16:25 | Jegadeesh Santhana Krishnan | Selvakumar Thiyagarajan | Dev | Pheonix | 4 | Yes | Yes communication between cross teams(for Ex BE) is much better now which helps in delivering bugs or epics on time . | Yes | Balanced | 4 | 4 | 4 | 4 | Yes | 4 | 4 | Individual | 4 | 4 | Yes | YES | Moderate | Less than 10% | Yes | None | Balanced (80% - 90%) | Some Information but still need further details | Not aware of any such initiative. Though the release coordination among teams was better than previous releases among teams | Average | Monitoring and Controlling Progress | Sprint DSU's | Intra Team Collaboration - Dependency linking on Jira by Individual owners | Blocking Scope change | Effective communication | Communication gap b/w dependent teams | More Than 5% but less than 10% |  | YES | N/A | N/A |  | Yes | ChatGPT, CoPilot, GitHub AI review | 30% and Above | Yes
2025-05-22 19:41 | Mohammed Fayaz | Komal Varma | Architect/Individual Contributors |  |  |  |  | No | [32 empty] | Working as floating staff and involved in team management and adhoc tasks from Managers | Yes | ChatGPT | 20% to 30% | Yes
2025-05-22 20:00 | Jegadeesh Santhana Krishnan | Selvakumar Thiyagarajan | Dev | Aurora | 5 | No |  | No | [33 empty] | Yes | ChatGPT, CoPilot, GitHub AI review, Claude | 30% and Above | Yes
2025-05-22 20:49 | Jegadeesh Santhana Krishnan | Rajesh Subramani | Dev | Hercules | 5 | Yes | We discussed about grooming items in advance to the sprint so that all the team members can have better visibility and can analyse them beforehand to make sure they properly plan it during the sprint. It worked, we are following early grooming now for better sprint velocity. | No | [32 empty] | Working on release epics. | Yes | ChatGPT, CoPilot | 30% and Above | Yes
2025-05-22 21:34 | Jegadeesh Santhana Krishnan | Chandra Sekhar Kusupati | Dev | Eirene | 4 | Yes | Enable team to have better automation success by standardizing connection.js file | Yes | Balanced | 4 | 4 | 4 | 4 | Yes | 4 | 4 | Scrum Team | 4 | 4 | No | YES | Moderate | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Some Information but still need further details | Yes | Average | Code Freeze Milestones and hardening phase | Sprint Retrospective | Jira Details - Epic breakdown, DoD, Exit criteria, CS Bugs | Risk call out during Weekly SoS | Release Planning, Strategy & Schedule (Proper Checkpoint and dates on jira tickets) | Delayed Response on open Queries, need multiple followups | Less than 5% |  | YES | None | All details should be available in jira rather than needing follow up on missing |  | Yes | ChatGPT, CoPilot | 10% or below | Yes
2025-05-22 21:39 | Jegadeesh Santhana Krishnan | Chandra Sekhar Kusupati | Dev & Scrum Master | Helios | 4 | Yes | We were adding sprint items in middle of sprint because of planning gaps ,that is addressed now | Yes | Well Managed | 5 | 4 | 4 | 4 | Yes | 4 | 4 | Individual | 4 | 4 | Yes | YES | Moderate | 10% to 20% | Yes | None | Balanced (80% - 90%) | Some Information but still need further details | Yes | Well Managed | Continuous Epic Grooming | Sprint Planning | Intra Team Collaboration - Dependency linking on Jira by Individual owners | Change in Due date and QA Sign off Date restrictions | Sprint Planning Structure | Intra team collaboration | More Than 5% but less than 10% |  | YES | NA |  |  | Yes | ChatGPT, CoPilot, Gemini | 30% and Above | Yes
2025-05-22 21:41 | Jegadeesh Santhana Krishnan | Rajesh Subramani | Dev & Scrum Master | Hercules | 4 | No |  | Yes | Balanced | 4 | 4 | 4 | 4 | Yes | 4 | 4 | Individual | 4 | 4 | Yes | YES | Moderate | Less than 10% | Yes | None | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Continuous Epic Grooming | Sprint Closure/review | Jira Details - Epic breakdown, DoD, Exit criteria, CS Bugs | Strict Bug SLA's | Release Planning, Strategy & Schedule (Proper Checkpoint and dates on jira tickets) | Improper Epic Breakdown & Estimations - Missing Sprint Backlog | My role involves process improvement and enablement (EM's, SM's & Other folks responsible for process streamlining) |  | YES | Nil |  |  | Yes | ChatGPT, CoPilot, GitHub AI review | 10% to 20% | Yes
2025-05-22 22:10 | Jegadeesh Santhana Krishnan | Selvakumar Thiyagarajan | Dev | Chloris | 5 | No |  | Yes | Chaotic | 3 | 5 | 3 | 4 | Partially/Incomplete | 3 | 4 | Individual | 5 | 5 | Yes | YES | None | Less than 10% | No | Multiple | Over Utilised (90% and Above) | Some Information but still need further details | Not aware of any such initiative. Though the release coordination among teams was better than previous releases among teams | Average | Code Freeze Milestones and hardening phase | Sprint Closure/review | Ad-hoc requests prioritisation and acceptance | Blocking Scope change | Efficient Jira Usage (New Fields such as - Due date, QA Lead, QA Involvement, QA Signoff date) | Ad-hoc Tasks & improper prioritisation | Less than 5% |  | YES | None |  |  | Yes | ChatGPT, CoPilot | 10% or below | Yes
2025-05-22 22:19 | Jegadeesh Santhana Krishnan | Chandra Sekhar Kusupati | DevOps | [38 empty] | Yes | ChatGPT, CoPilot, Gemini | 10% or below | Yes
2025-05-22 22:37 | Jegadeesh Santhana Krishnan | Selvakumar Thiyagarajan | Dev & Scrum Master | Pheonix | 3 | Yes | One of my team member not able to update sprint in Jira. raised a ticket | Yes | Well Managed | 5 | 5 | 5 | 5 | Yes | 5 | 5 | Scrum Team | 5 | 4 | Yes | YES | Moderate | Less than 10% | Yes | None | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Continuous Epic Grooming | Sprint Closure/review | Intra Team Collaboration - Dependency linking on Jira by Individual owners | Strict Bug SLA's | Better Estimations & Epic Breakdown | Intra team collaboration | My role involves process improvement and enablement (EM's, SM's & Other folks responsible for process streamlining) |  | YES | NA |  |  | Yes | ChatGPT, CoPilot | 10% to 20% | Yes
2025-05-22 22:45 | Jegadeesh Santhana Krishnan | Selvakumar Thiyagarajan | EM |  |  |  |  | Yes | Well Managed | 5 | 5 | 5 | 5 | Yes | 5 | 5 | Scrum Team | 5 | 5 | Yes | YES | Multiple | Less than 10% | Yes | None | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Continuous Epic Grooming | Sprint Planning | Intra Team Collaboration - Dependency linking on Jira by Individual owners | Change in Due date and QA Sign off Date restrictions | Better & transparent commitments | Communication gap b/w dependent teams | My role involves process improvement and enablement (EM's, SM's & Other folks responsible for process streamlining) |  | YES | NO |  |  | Yes | ChatGPT | 10% or below | Yes
2025-05-22 23:14 | Jegadeesh Santhana Krishnan | Selvakumar Thiyagarajan | Dev | Iris | 4 | Yes | BE dependency on Epics improved | Yes | Balanced | 5 | 5 | 5 | 5 | Yes | 4 | 4 | Individual | 4 | 4 | Yes | Moderately | Moderate | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Monitoring and Controlling Progress | Sprint Closure/review | Tech Design | Blocking Scope change | Dependency management | Partial or missing details on Jira Trackers Description | More Than 5% but less than 10% |  | YES | Nil |  |  | Yes | ChatGPT, CoPilot, GitHub AI review | 30% and Above | Yes
2025-05-22 23:31 | Jegadeesh Santhana Krishnan | Rajesh Subramani | Dev | Helios | 4 | Yes | Proper alignment of tasks so as to call out any forseen risk that could occur, and executing everything in systematic manner. | Yes | Balanced | 4 | 4 | 1 | 5 | Yes | 5 | 5 | Individual | 5 | 5 | Yes | YES | Multiple | Less than 10% | No | None | Over Utilised (90% and Above) | Optimal information available | Yes | Well Managed | Code Freeze Milestones and hardening phase | Sprint Planning | Jira Details - Epic breakdown, DoD, Exit criteria, CS Bugs | Risk call out during Weekly SoS | Effective communication | Communication gap b/w dependent teams | More Than 5% but less than 10% |  | YES | Risk callout of an item should also mention the impacted areas that will be affected | JIRA should not allow to add STORY points at STORY LEVEL(PARENTS LEVEL), if its going to reset them once we add the child/Sub tasks. The Burndown captures wrong data points |  | Yes | ChatGPT, CoPilot | 20% to 30% | Yes
2025-05-23 07:16 | Jegadeesh Santhana Krishnan | Chandra Sekhar Kusupati | Dev & Scrum Master | Eirene | 4 | No |  | Yes | Balanced | 4 | 4 | 4 | 4 | Yes | 4 | 4 | Scrum Team | 4 | 4 | Yes | YES | Moderate | 10% to 20% | Yes | None | Balanced (80% - 90%) | Some Information but still need further details | Yes | Average | Epic Breakdown | Sprint Planning | Jira Details - Epic breakdown, DoD, Exit criteria, CS Bugs | Blocking Scope change | Better & transparent commitments | Communication gap b/w dependent teams | My role involves process improvement and enablement (EM's, SM's & Other folks responsible for process streamlining) |  | YES | na |  |  | Yes | ChatGPT, CoPilot | 20% to 30% | Yes
2025-05-23 10:17 | Mohammed Fayaz | Anusha Jharupula | QA | Indus | 5 | Yes | Handled adhoc tasks efficiently. | Yes | Well Managed | 5 | 5 | 5 | 5 | Yes | 5 | 5 | Scrum Team | 5 | 5 | Yes | YES | Multiple | Less than 10% | Yes | Moderate | Over Utilised (90% and Above) | Optimal information available | Yes | Well Managed | Monitoring and Controlling Progress | Sprint Closure/review | Ad-hoc requests prioritisation and acceptance | Change in Due date and QA Sign off Date restrictions | Release Planning, Strategy & Schedule (Proper Checkpoint and dates on jira tickets) | Ad-hoc Tasks & improper prioritisation | More Than 5% but less than 10% |  | YES | NO |  |  | Yes | ChatGPT | 10% to 20% | Yes
2025-05-23 10:19 | Jegadeesh Santhana Krishnan | Ashok Kumar Dantham | Dev | Iris | 5 | Yes | scope fix | Yes | Well Managed | 5 | 5 | 5 | 5 | Yes | 5 | 5 | Scrum Team | 4 | 5 | Yes | YES | Moderate | 10% to 20% | Yes | None | Over Utilised (90% and Above) | Optimal information available | Yes | Well Managed | Continuous Epic Grooming | Sprint Closure/review | Non Release Activity Identification & capacity reserve | Risk call out during Weekly SoS | Better & transparent commitments | Delayed Response on open Queries, need multiple followups | Less than 5% |  | YES | NA |  |  | Yes | ChatGPT, CoPilot, Gemini, GitHub AI review | 10% to 20% | Yes
2025-05-23 10:24 | Jegadeesh Santhana Krishnan | Anusha Badveeti | Dev | Tranformers | 5 | Yes | - | Yes | Balanced | 4 | 4 | 4 | 4 | Yes | 4 | 4 | Scrum Team | 4 | 4 | Yes | Moderately | Moderate | Less than 10% | No | Moderate | Over Utilised (90% and Above) | Optimal information available | Yes | Well Managed | Committed Epic Prioritisation | Sprint Planning | Ad-hoc requests prioritisation and acceptance | Blocking Scope change | Release Planning, Strategy & Schedule (Proper Checkpoint and dates on jira tickets) | Ad-hoc Tasks & improper prioritisation | Less than 5% |  | YES | - |  |  | Yes | ChatGPT, CoPilot | 10% to 20% | Yes
2025-05-23 10:33 | Mohammed Fayaz | Tharuni Sai Idupulapati | QA | Apollo | 4 | Yes | Meeting time optimisation | Yes | Balanced | 4 | 4 | 4 | 4 | Yes | 4 | 5 | Scrum Team | 4 | 4 | Yes | YES | Multiple | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Code Freeze Milestones and hardening phase | Sprint Retrospective | Jira Automation | Change in Due date and QA Sign off Date restrictions | Sprint Planning Structure | Missing SLA's for Bugs, Trackers on Jira | More Than 5% but less than 10% |  | YES | Following the strict SLA's on bug trackers and not changing the due and sign-off dates |  |  | Yes | ChatGPT, CoPilot | 20% to 30% | Yes
2025-05-23 10:50 | Mohammed Fayaz | SathishKumar D | QA | Optimus | 4 | Yes | NA | No | [32 empty] | Automation Enhancements | Yes | ChatGPT, CoPilot, Gemini | 10% or below | Yes
2025-05-23 10:51 | Mohammed Fayaz | SathishKumar D | QA | Optimus | 5 | Yes | Fixing Automation failures | No | [32 empty] | Fixing Automation issues | Yes | ChatGPT, CoPilot | 10% to 20% | Yes
2025-05-23 10:55 | Mohammed Fayaz | SathishKumar D | QA | Optimus | 5 | Yes | As members of the QA Core Team, we were not directly involved in executing specific test cases for this release, but we played a crucial supporting role throughout the process. Our primary responsibility was to monitor the overall quality and stability of the release from a quality assurance perspective. During the release, if any issues or test failures were observed on the QA side, our team was the first line of investigation and resolution. We proactively analyzed the root cause of failures, coordinated with respective QA owners or developers, and ensured that issues were addressed promptly without blocking the release timeline. Our role was to maintain oversight and provide quick resolutions, thereby upholding the reliability and standards expected from the QA function in every release cycle. | No | [32 empty] | During the release process, our QA Core Team served as the initial point of contact for any issues or test failures related to quality assurance. Although we were not directly executing test cases, we played a key oversight role. Whenever a QA-related failure occurred, we immediately took ownership by investigating the root cause, collaborating with the relevant QA engineers or developers, and facilitating a swift resolution. This ensured that such issues did not delay the release. Our involvement was essential in maintaining the quality benchmarks and ensuring a smooth and timely deployment. | Yes | ChatGPT, CoPilot | 20% to 30% | Yes
2025-05-23 10:58 | Mujtaba Ahmad | Hemant Agrawal | Dev | Enigma | 5 | No |  | Yes | Balanced | 5 | 5 | 5 | 5 | Yes | 4 | 4 | Scrum Team | 5 | 5 | Yes | YES | Moderate | 10% to 20% | No | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Continuous Epic Grooming | Sprint Closure/review | KT and recording repository | Change in Due date and QA Sign off Date restrictions | Better Estimations & Epic Breakdown | Non Release Activities | More Than 5% but less than 10% |  | YES | No |  |  | Yes | ChatGPT, CoPilot | Just started using AI, need time to quantify | Yes
2025-05-23 10:59 | Jegadeesh Santhana Krishnan | Rajesh Subramani | Dev | Hercules | 4 | No |  | Yes | Well Managed | 4 | 4 | 4 | 4 | Yes | 5 | 5 | Individual | 5 | 4 | Yes | Moderately | Moderate | 10% to 20% | No | None | Over Utilised (90% and Above) | Optimal information available | Not aware of any such initiative. Though the release coordination among teams was better than previous releases among teams | Well Managed | Code Freeze Milestones and hardening phase | Sprint Closure/review | Jira Details - Epic breakdown, DoD, Exit criteria, CS Bugs | Change in Due date and QA Sign off Date restrictions | Better Estimations & Epic Breakdown | Intra team collaboration | More Than 5% but less than 10% |  | YES | Nil | Nil |  | Yes | ChatGPT, CoPilot | 20% to 30% | Yes
2025-05-23 11:01 | Mohammed Fayaz | SathishKumar D | QA | Optimus | 4 | Yes | All conducted in respective manner | No | [32 empty] | Testing new release codes | No | ChatGPT | 20% to 30% | Yes
2025-05-23 11:02 | Mohammed Fayaz | SathishKumar D | QA | Optimus | 5 | Yes | - | No | [32 empty] | - | Yes | ChatGPT | Just started using AI, need time to quantify | Yes
2025-05-23 11:25 | Mohammed Fayaz | SathishKumar D | QA | Optimus | 5 | Yes | We are part of the automation team, we are not involved in release activities. | No | [32 empty] | we are part of automation team so whatever the QA/Dev would face issue in testing at framework level, we would resolve that | Yes | ChatGPT | 20% to 30% | Yes
2025-05-23 11:26 | Mohammed Fayaz | SathishKumar D | QA | Optmius | 4 | No |  | No | [32 empty] | Automation and QA ops | Yes | ChatGPT, CoPilot | 20% to 30% | Yes
2025-05-23 11:39 | Mohammed Fayaz | SathishKumar D | QA | Optimus | 4 | Yes | healthchecks for different services | No | [32 empty] | engagement area was on different service healthchecks | Yes | ChatGPT | 20% to 30% | Yes
2025-05-23 11:49 | Mujtaba Ahmad | Raman Soni | Dev | Stark | 4 | No |  | Yes | Well Managed | 4 | 4 | 4 | 4 | Yes | 4 | 4 | Individual | 4 | 4 | Yes | YES | Moderate | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Some Information but still need further details | Yes | Average | Committed Epic Prioritisation | Sprint Planning | Jira Details - Epic breakdown, DoD, Exit criteria, CS Bugs | Change in Due date and QA Sign off Date restrictions | Better Estimations & Epic Breakdown | PR Merges | More than 10% but Less than 20% |  | YES | NA |  |  | Yes | ChatGPT, CoPilot, Perplexity, Gemini, GitHub AI review | 20% to 30% | Yes
2025-05-23 11:50 | Jegadeesh Santhana Krishnan | Jegadeesh Santhana Krishnan | Architect/Individual Contributors |  |  |  |  | No | [33 empty] | Yes | ChatGPT, CoPilot | 30% and Above | Yes
2025-05-23 11:50 | Jegadeesh Santhana Krishnan | Jegadeesh Santhana Krishnan | Architect/Individual Contributors |  |  |  |  | No | [33 empty] | Yes | ChatGPT | 20% to 30% | Yes
2025-05-23 12:06 | Mujtaba Ahmad | Raman Soni | Dev | Apollo | 4 | Yes | One of the action item was going through the retro items during mid sprint as we were alway s doing end to end reflection which was not very effective | Yes | Balanced | 4 | 4 | 4 | 5 | Yes | 4 | 4 | Scrum Team | 5 | 3 | Yes | YES | Moderate | Less than 10% | Yes | Multiple | Over Utilised (90% and Above) | Some Information but still need further details | Yes | Well Managed | Committed Epic Prioritisation | Sprint Planning | Non Release Activity Identification & capacity reserve | Risk call out during Weekly SoS | Dependency management | Ad-hoc Tasks & improper prioritisation | Less than 5% |  | YES | I think adhoc meetings/discussions should be captured better to have better velocity | JIRA workflows should be made simpler with hooks and approvals and currently sometimes we are not aware of whom should we reach to update certain statuses |  | Yes | ChatGPT, CoPilot | 10% to 20% | Yes
2025-05-23 12:12 | Mujtaba Ahmad | Hemant Agrawal | Dev | Enigma | 4 | Yes |  | No | [33 empty] | Yes | ChatGPT, Gemini | 10% to 20% | Yes
2025-05-23 12:22 | Mujtaba Ahmad | Raman Soni | Dev | Stark | 5 | No |  | Yes | Balanced | 5 | 5 | 5 | 5 | Yes | 5 | 5 | Scrum Team | 5 | 5 | Yes | YES | Multiple | Less than 10% | Yes | Moderate | Over Utilised (90% and Above) | Optimal information available | Yes | Well Managed | Committed Epic Prioritisation | Sprint Closure/review | Ad-hoc requests prioritisation and acceptance | Strict Bug SLA's | Efficient Jira Usage (New Fields such as - Due date, QA Lead, QA Involvement, QA Signoff date) | Ad-hoc Tasks & improper prioritisation | Less than 5% |  | YES | N/A |  |  | Yes | ChatGPT, CoPilot | 10% to 20% | Yes
2025-05-23 13:26 | Mohammed Fayaz | Tharuni Sai Idupulapati | QA | Apollo | 5 | Yes | NA | Yes | Balanced | 4 | 4 | 4 | 5 | Yes | 4 | 4 | Individual | 4 | 4 | Yes | YES | Moderate | 10% to 20% | Yes | None | Over Utilised (90% and Above) | Optimal information available | Not aware of any such initiative. Though the release coordination among teams was better than previous releases among teams | Average | Code Freeze Milestones and hardening phase | Sprint Retrospective | CI/CD, Testing & Continuous planning | Strict Bug SLA's | None | Intra team collaboration | Less than 5% | NA | YES | NA |  |  | Yes | ChatGPT | Just started using AI, need time to quantify | Yes
2025-05-23 13:49 | Mujtaba Ahmad | Raman Soni | Dev | Stark | 5 | Yes | Maintain proper JIRA trackers | Yes | Well Managed | 5 | 5 | 5 | 5 | Yes | 5 | 5 | Scrum Team | 5 | 5 | Yes | YES | Multiple | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Committed Epic Prioritisation | Sprint Planning | Ad-hoc requests prioritisation and acceptance | Strict Bug SLA's | Release Planning, Strategy & Schedule (Proper Checkpoint and dates on jira tickets) | Ad-hoc Tasks & improper prioritisation | Less than 5% |  | YES | NA |  |  | Yes | ChatGPT, CoPilot | 10% to 20% | Yes
2025-05-23 13:58 | Krishna Kishore Mothukuri | Ajitkumar kaller | Dev | Velocity | 5 | Yes | regular grooming of trackers was needed which was done | Yes | Well Managed | 5 | 5 | 5 | 5 | Yes | 5 | 5 | Scrum Team | 5 | 5 | Yes | YES | Moderate | Less than 10% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Committed Epic Prioritisation | Sprint DSU's | Backlog & CS bugs prioritisation | Change in Due date and QA Sign off Date restrictions | None | Communication gap b/w dependent teams | Less than 5% |  | YES | N/A |  |  | Yes | ChatGPT, CoPilot, GitHub AI review | 20% to 30% | Yes
2025-05-23 14:18 | Mujtaba Ahmad | Raman Soni | Dev & Scrum Master | Apollo | 4 | Yes | Meetings were made as concise as possible and we checked the retrospective items in the mid-sprint to make sure that they're being followed. | Yes | Balanced | 4 | 4 | 5 | 5 | Yes | 4 | 4 | Scrum Team | 4 | 4 | Yes | YES | Multiple | Less than 10% | Yes | Moderate | Balanced (80% - 90%) | Some Information but still need further details | Yes | Average | Continuous Epic Grooming | Sprint Closure/review | Jira Details - Epic breakdown, DoD, Exit criteria, CS Bugs | Blocking Scope change | Better & transparent commitments | Improper Epic Breakdown & Estimations - Missing Sprint Backlog | Less than 5% |  | YES | NA |  |  | Yes | ChatGPT, GitHub AI review | 10% to 20% | Yes
2025-05-23 15:21 | Mujtaba Ahmad | Raman Soni | Dev | Apollo | 5 | Yes | Action item - revisit prev retro Resolved by setting up a dedicated meeting with mid sprint review to go through the retro and improve. | Yes | Well Managed | 5 | 4 | 4 | 5 | Yes | 4 | 4 | Scrum Team | 5 | 4 | Yes | YES | Moderate | Less than 10% | Yes | Moderate | Under Utilisation (80% Below) | Some Information but still need further details | Yes | Well Managed | Code Freeze Milestones and hardening phase | Sprint Planning | Backlog & CS bugs prioritisation | Blocking Scope change | Effective communication | Ad-hoc Tasks & improper prioritisation | More Than 5% but less than 10% |  | YES | NA |  |  | Yes | ChatGPT, CoPilot | 10% to 20% | Yes
2025-05-23 17:03 | Mohammed Fayaz | Varun Batra | QA | Chipmuks | 5 | Yes | NA | Yes | Balanced | 5 | 5 | 5 | 5 | Yes | 5 | 5 | Scrum Team | 5 | 5 | Yes | YES | Moderate | Less than 10% | Yes | None | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Committed Epic Prioritisation | Sprint Planning | Jira Details - Epic breakdown, DoD, Exit criteria, CS Bugs | Risk call out during Weekly SoS | Better & transparent commitments | Modifications on Approved Tech designs | Less than 5% |  | YES | NA |  |  | Yes | ChatGPT | Just started using AI, need time to quantify | Yes
2025-05-23 17:14 | Mujtaba Ahmad | Hemant Agrawal | Dev | Titans | 5 | No |  | Yes | Well Managed | 5 | 5 | 5 | 5 | Yes | 5 | 4 | Individual | 5 | 5 | Yes | YES | Moderate | 20% to 30% | Yes | Multiple | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Continuous Epic Grooming | Sprint Planning | Jira Details - Epic breakdown, DoD, Exit criteria, CS Bugs | Risk call out during Weekly SoS | Better & transparent commitments | Ad-hoc Tasks & improper prioritisation | Less than 5% |  | YES | na |  |  | Yes | ChatGPT, CoPilot, Gemini | 10% to 20% | Yes
2025-05-23 17:27 | Jegadeesh Santhana Krishnan | Selvakumar Thiyagarajan | Dev | Chloris | 4 | Yes | - | Yes | Balanced | 4 | 4 | 4 | 5 | Yes | 5 | 4 | Scrum Team | 4 | 4 | No | YES | Moderate | Less than 10% | Yes | Moderate | Over Utilised (90% and Above) | Optimal information available | Yes | Average | Committed Epic Prioritisation | Sprint Planning | KT and recording repository | Risk call out during Weekly SoS | Effective communication | Ad-hoc Tasks & improper prioritisation | Less than 5% | - | YES | - | - |  | Yes | ChatGPT, CoPilot | 10% to 20% | Yes
2025-05-24 01:17 | Mohammed Fayaz | Tharuni Sai Idupulapati | QA | Ganges | 5 | Yes | No slippages in QA ready dates | Yes | Balanced | 5 | 4 | 5 | 5 | Yes | 5 | 5 | Scrum Team | 5 | 5 | Yes | YES | Moderate | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Monitoring and Controlling Progress | Sprint Closure/review | Test Design | Blocking Scope change | Sprint Planning Structure | Delayed Test Designs | More Than 5% but less than 10% |  | YES | Nothing |  |  | Yes | ChatGPT, CoPilot, Gemini | 20% to 30% | Yes
2025-05-24 23:36 | Mujtaba Ahmad | Ranjith Kumar M | Dev | Gryffindor | 4 | No |  | Yes | Balanced | 4 | 4 | 4 | 4 | Partially/Incomplete | 4 | 4 | Scrum Team | 4 | 4 | No | Moderately | Moderate | 20% to 30% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Average | Committed Epic Prioritisation | Sprint Retrospective | Bugs Management & Deferring | Risk call out during Weekly SoS | None | Improper Epic Breakdown & Estimations - Missing Sprint Backlog | Less than 5% |  | YES | NA |  |  | Yes | ChatGPT, CoPilot | 10% to 20% | Yes