## Form Responses 1
Timestamp | You are part of which of the following directors org | What's your primary role? | Enter the Team/Scrum team that you are mostly associated with during the release. (Select Only One) | Are you using AI for efficiency improvement in your day to day Dev/QA activity? | Which Tool are you using for your AI tasks | With the usage of AI what has been increase in your productivity? | Are you getting the required support and guidance within Engineering to explore and increase efficiency using AI? | Are you directly involved in the Release Deliverables for current release items or items planned and in progress for future releases? | How would you rate Release Overall (Individual Perspective) ? | How would you rate the release planning in comparison to previous release plannings? (1-Poor, 5- Improved) | How well were you as an individual aware of your teams commitments and scope of work prior to release implementation start ? (1-Not Aware, 5- Aware) | What was your involvement in Release planning and the selection of commitments? (1-Not Involved, 5- Fully Involved) | Were you as an individual aware of the Release timelines and your tasks in hand for the Release ? (1-Somewhat Aware, 5- Fully Aware) | Detailed Epic Breakdown with estimates and scrum team ownership were done for your trackers parent epic prior to Release Implementation Initiation. | How confident were you in terms of your teams commitments and deliverables? (1-Not Confident, 5- Full Confidence) | How would you rate effectiveness the Sprint Planning Meetings ? (1-Not Effective, 5- Effective) | Individual items efforts estimate for completion of the task is done by whom ? (Desired state is by scrum team) | How would you rate effectiveness of the Daily Standup connect to understand and analyse your tasks in hand ? (1-Not Effective, 5- Effective) | How would you rate effectiveness of the Sprint Closure / review meetings ? (1-Not Effective, 5- Effective) | Was Sprint retrospective Conducted for your Team at the end of each Sprint | Sprint Retrospective Effectiveness | Do you as an individual get sufficient opportunity to raise risk or concerns during agile ceremonies? | Do you get opportunity to learn new things in accordance to your role release over release? | What percentage of your capacity in the sprint was reserved for Items such as CS Support Bugs/Requests which cannot be estimated but as a team you reserve some bandwidth, as per history you are aware of such requests and your team reserves capacity for it ?(individual capacity reserved) | Is your reserved capacity for the Historical support activities such as CS Bugs/Support tickets and others, sufficient during the release. | How much Adhoc requests (Request for which no bandwidth was reserved during Release/Sprint Planning) were received post sprint planning. | How was your available capacity utilised during the Release i.e. your workload. (1-Under Utilisation, 5- Over Utilisation) | Do you have sufficient details available on Jira to successfully and independently complete your assigned tasks | Was the Release Coordination Group initiated with representatives from each directors org, helpful and more efficient in managing the Release checkpoints and ensuring the key asks were routed better to the respective team/people? | How well were dependencies managed in the Release. | Check the Release Ceremony where there is need to spend more efforts to make the release more effective. | Check the Sprint Ceremony where there is need to spend more efforts to make the release more effective. | What is the top improvement area in the below list you would suggest to improve for a smoother release? | What do we need to improve in Release Implementation | Anything that you would like to call out which improved in this release as compared to the previous releases. | What is the most probable reason that deviates the planned timelines? | Applicable only for pure DEV or QA Resources - What percent of your available capacity is impacted by process changes and new processes enablement on regular tasks not the other cleanup activities from previous releases (Not Applicable to EM's, SM's & Other Folks responsible for process streamlining) | Any other thought you would like to share related to the releases. | In Your individual opinion are we considering the release Delivery Timelines and milestones while we are planning and delivering our assigned tasks | Do you have any suggestion for improving and streamlining the release further?
2024-11-05 11:15 | Krishna Kishore Mothukuri | Dev | Hercules | Yes | Copilot | 20% to 30% | Yes | No
2024-11-05 11:19 | Mujtaba Ahmad | Dev | Stark | Yes | copilot , perplexity | 10% or below | Yes | Yes | Balanced | 4 | 5 | 4 | 4 | Yes | 4 | 4 | Individual | 4 | 3 | Yes | 4 | YES | Moderate | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Committed Epic Prioritisation | Sprint Retrospective | Backlog & CS bugs prioritisation | Blocking Scope change | Dependency management | Ad-hoc Tasks & improper prioritisation | More Than 5% but less than 10% |  | YES | NA
2024-11-05 11:19 | Mohammed Fayaz | EM | Chipmuks | Yes | ChatGPT | 10% or below | Yes | Yes | Well Managed | 4 | 4 | 5 | 5 | Partially/Incomplete | 5 | 3 | Scrum Team | 4 | 4 | Yes | 3 | YES | Moderate | 10% to 20% | Yes | None | Balanced (80% - 90%) | Some Information but still need further details | Yes | Well Managed | Continuous Epic Grooming | Sprint Planning | Jira Details - Epic breakdown, DoD, Exit criteria, CS Bugs | Strict Bug SLA's | Release Planning, Strategy & Schedule (Proper Checkpoint and dates on jira tickets) | Improper Epic Breakdown & Estimations - Missing Sprint Backlog | My role involves process improvement and enablement (EM's, SM's & Other folks responsible for process streamlining) |  | YES | NA
2024-11-05 11:21 | Jegadeesh Santhana Krishnan | Dev & Scrum Master | Aurora | Yes | chatgpt | 10% to 20% | Yes | No
2024-11-05 11:21 | Mujtaba Ahmad | Dev | Ganges | Yes | copilot | 10% to 20% | Yes | Yes | Balanced | 3 | 3 | 5 | 4 | Yes | 5 | 4 | Scrum Team | 4 | 4 | Yes | 4 | YES | Multiple | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Not aware of any such initiative. Though the release coordination among teams was better than previous releases among teams | Well Managed | Committed Epic Prioritisation | Sprint Planning | Ad-hoc requests prioritisation and acceptance | Change in Due date and QA Sign off Date restrictions | Reduced over commit | Ad-hoc Tasks & improper prioritisation | More Than 5% but less than 10% |  | YES | not for now
2024-11-05 11:22 | Jegadeesh Santhana Krishnan | EM | Hercules | No |  |  |  | Yes | Well Managed | 5 | 5 | 5 | 5 | Yes | 5 | 5 | Individual | 5 | 5 | Yes | 5 | YES | Multiple | Less than 10% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Code Freeze Milestones and hardening phase | Sprint Closure/review | Intra Team Collaboration - Dependency linking on Jira by Individual owners | Blocking Scope change | None | Reviews | My role involves process improvement and enablement (EM's, SM's & Other folks responsible for process streamlining) |  | YES | -
2024-11-05 11:29 | Mohammed Fayaz | QA | Zeta | Yes | chatgpt | 10% to 20% | Yes | Yes | Well Managed | 4 | 4 | 4 | 4 | Yes | 4 | 4 | Scrum Team | 4 | 4 | Yes | 4 | YES | Moderate | Less than 10% | Yes | Moderate | Balanced (80% - 90%) | Some Information but still need further details | Yes | Average | Committed Epic Prioritisation | Sprint Planning | Jira Details - Epic breakdown, DoD, Exit criteria, CS Bugs | Change in Due date and QA Sign off Date restrictions | Dependency management | Ad-hoc Tasks & improper prioritisation | Less than 5% |  | YES | No
2024-11-05 11:32 | Sandeep Kumar | Dev & Scrum Master | Dynamos | Yes | copilot | 10% or below | Yes | Yes | Balanced | 4 | 4 | 5 | 5 | Yes | 5 | 4 | Scrum Team | 4 | 4 | Yes | 3 | YES | Moderate | Less than 10% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Epic Breakdown | Sprint Closure/review | Jira Details - Epic breakdown, DoD, Exit criteria, CS Bugs | Change in Due date and QA Sign off Date restrictions | None | PR Merges | Less than 5% |  | YES | NA
2024-11-05 11:33 | Mujtaba Ahmad | Dev | Ganges | No |  |  |  | Yes | Well Managed | 5 | 3 | 4 | 4 | Yes | 5 | 5 | Scrum Team | 5 | 5 | Yes | 5 | YES | Multiple | More than 30% | Yes | Moderate | Balanced (80% - 90%) | Some Information but still need further details | Yes | Well Managed | Continuous Epic Grooming | Sprint Closure/review | KT and recording repository | Change in Due date and QA Sign off Date restrictions | Reduced over commit | PR Merges | Less than 5% |  | YES | None
2024-11-05 11:34 | Jegadeesh Santhana Krishnan | Dev | Helios | Yes | Github copilot | 10% to 20% | Yes | Yes | Well Managed | 5 | 5 | 4 | 5 | Yes | 5 | 5 | Individual | 5 | 5 | Yes | 5 | YES | Moderate | Less than 10% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Not aware of any such initiative. Though the release coordination among teams was better than previous releases among teams | Average | Epic Breakdown | Sprint Planning | Jira Details - Epic breakdown, DoD, Exit criteria, CS Bugs | Change in Due date and QA Sign off Date restrictions | Better Estimations & Epic Breakdown | Improper Epic Breakdown & Estimations - Missing Sprint Backlog | More Than 5% but less than 10% |  | YES | NA
2024-11-05 11:34 | Jegadeesh Santhana Krishnan | Dev | Sharks | Yes | github copilot, chatgpt | 10% to 20% | Yes | No
2024-11-05 11:36 | Sandeep Kumar | Dev | Omega | Yes | OpenAI | 30% and Above | Yes | Yes | Balanced | 3 | 3 | 4 | 4 | Yes | 4 | 4 | Scrum Team | 4 | 4 | Yes | 4 | Moderately | None | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Epic Breakdown | Sprint Planning | KT and recording repository | Change in Due date and QA Sign off Date restrictions | Efficient Jira Usage (New Fields such as - Due date, QA Lead, QA Involvement, QA Signoff date) | Improper Epic Breakdown & Estimations - Missing Sprint Backlog | More Than 5% but less than 10% |  | YES | Better communication regarding deliverables of the release and the processes
2024-11-05 11:38 | Sandeep Kumar | QA | Phi | No |  |  |  | Yes | Balanced | 3 | 3 | 3 | 4 | Partially/Incomplete | 4 | 4 | Scrum Team | 4 | 4 | Yes | 4 | Moderately | Moderate | Less than 10% | No | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Average | Monitoring and Controlling Progress | Sprint Planning | Ad-hoc requests prioritisation and acceptance | Strict Bug SLA's | Better Estimations & Epic Breakdown | Ad-hoc Tasks & improper prioritisation | More than 10% but Less than 20% |  | YES | NA
2024-11-05 11:39 | Mujtaba Ahmad | Dev | Stark | Yes | copilot and chatgpt | 10% to 20% | No | Yes | Balanced | 3 | 5 | 5 | 5 | Yes | 5 | 4 | Scrum Team | 4 | 4 | Yes | 5 | YES | Moderate | 10% to 20% | Yes | Multiple | Over Utilised (90% and Above) | Optimal information available | Yes | Average | Monitoring and Controlling Progress | Sprint Planning | Ad-hoc requests prioritisation and acceptance | Risk call out during Weekly SoS | Effective communication | Ad-hoc Tasks & improper prioritisation | More Than 5% but less than 10% | N/A | YES | N/A
2024-11-05 11:39 | Sandeep Kumar | Dev | Phi | Yes | Chat-GPT | 10% or below | No | Yes | Balanced | 4 | 3 | 4 | 5 | Partially/Incomplete | 4 | 4 | Individual | 4 | 4 | Yes | 5 | Moderately | None | Less than 10% | No | Multiple | Over Utilised (90% and Above) | Some Information but still need further details | Yes | Well Managed | Committed Epic Prioritisation | Sprint Planning | Backlog & CS bugs prioritisation | Blocking Scope change | None | PR Merges | Less than 5% |  | YES | NA
2024-11-05 11:40 | Jegadeesh Santhana Krishnan | Dev | Hercules | Yes | Copilot and chatgpt | 10% to 20% | Yes | Yes | Well Managed | 5 | 5 | 4 | 4 | Yes | 4 | 4 | Scrum Team | 5 | 5 | Yes | 5 | YES | Moderate | 10% to 20% | Yes | Moderate | Over Utilised (90% and Above) | Optimal information available | Yes | Well Managed | Release Kick Off | Sprint Closure/review | Intra Team Collaboration - Dependency linking on Jira by Individual owners | Blocking Scope change | Efficient Jira Usage (New Fields such as - Due date, QA Lead, QA Involvement, QA Signoff date) | Intra team collaboration | Less than 5% |  | YES | No
2024-11-05 11:44 | Sandeep Kumar | Dev | Phi | Yes | langchain, TP FDR utility, scrapper utility | 30% and Above | Yes | Yes | Balanced | 4 | 4 | 4 | 5 | Yes | 5 | 4 | Scrum Team | 4 | 4 | Yes | 4 | Moderately | None | Less than 10% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Epic Breakdown | Sprint Planning | Ad-hoc requests prioritisation and acceptance | Blocking Scope change | Better & transparent commitments | Ad-hoc Tasks & improper prioritisation | Less than 5% |  | YES | NA
2024-11-05 11:48 | Mohammed Fayaz | QA | Gryffindor | Yes | Chatgpt | 20% to 30% | Yes | Yes | Well Managed | 4 | 5 | 4 | 5 | Yes | 5 | 5 | Individual | 5 | 5 | Yes | 5 | YES | Moderate | Less than 10% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Code Freeze Milestones and hardening phase | Sprint Closure/review | Ad-hoc requests prioritisation and acceptance | Change in Due date and QA Sign off Date restrictions | Release Planning, Strategy & Schedule (Proper Checkpoint and dates on jira tickets) | PR Merges | More than 10% but Less than 20% | NA | YES | Overall process was handled very perfectly with the team
2024-11-05 11:51 | Mujtaba Ahmad | Dev | Enigma | Yes | Co-Pilot and chatgpt | 10% to 20% | Yes | Yes | Balanced | 5 | 5 | 5 | 5 | Partially/Incomplete | 4 | 4 | Scrum Team | 5 | 4 | Yes | 4 | YES | Multiple | 20% to 30% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Committed Epic Prioritisation | Sprint Planning | Ad-hoc requests prioritisation and acceptance | Blocking Scope change | Reduced over commit | Delay in commitments from dependant team | Less than 5% |  | YES | NA
2024-11-05 12:02 | Mohammed Fayaz | QA | Iota | Yes | ChatGpt | 10% or below | Yes | Yes | Balanced | 4 | 4 | 4 | 4 | Yes | 4 | 4 | Scrum Team | 4 | 4 | Yes | 4 | YES | Moderate | Less than 10% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Continuous Epic Grooming | Sprint Planning | KT and recording repository | Strict Bug SLA's | Effective communication | Improper Epic Breakdown & Estimations - Missing Sprint Backlog | Less than 5% | NA | YES | NA
2024-11-05 12:10 | Jegadeesh Santhana Krishnan | Others | Individual Capacity, Not Associated with any particular team | Yes | ChatGPT | 20% to 30% | Yes | No
2024-11-05 12:11 | Sandeep Kumar | Dev & Scrum Master | Gryffindor | Yes | Github copilot | 10% to 20% | Yes | Yes | Chaotic | 4 | 5 | 5 | 5 | Yes | 4 | 5 | Scrum Team | 5 | 3 | Yes | 5 | YES | None | 10% to 20% | Yes | Multiple | Over Utilised (90% and Above) | Some Information but still need further details | Yes | Average | Committed Epic Prioritisation | Sprint Closure/review | Ad-hoc requests prioritisation and acceptance | Blocking Scope change | Effective communication | Ad-hoc Tasks & improper prioritisation | More than 10% but Less than 20% |  | YES | NA
2024-11-05 12:11 | Jegadeesh Santhana Krishnan | Dev | Echo | Yes | GPT & Copilot | 20% to 30% | Yes | Yes | Well Managed |  |  |  |  | Yes | 4 |  | Scrum Team |  |  | Yes | 4 | YES | Multiple | Less than 10% | No | Multiple | Balanced (80% - 90%) | Optimal information available | Yes |  | Committed Epic Prioritisation | Sprint Planning | Ad-hoc requests prioritisation and acceptance | Risk call out during Weekly SoS | Effective communication | Ad-hoc Tasks & improper prioritisation | Less than 5% |  | YES | NA
2024-11-05 12:19 | Mohammed Fayaz | QA | Chipmuks | Yes | chatGPT | Just started using AI, need time to quantify | Yes | Yes | Balanced | 3 | 4 | 3 | 3 | Partially/Incomplete | 4 | 3 | Scrum Team | 3 | 3 | Yes | 3 | YES | Moderate | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Some Information but still need further details | Yes | Average | Committed Epic Prioritisation | Sprint Planning | Jira Details - Epic breakdown, DoD, Exit criteria, CS Bugs | Blocking Scope change | Reduced over commit | Improper Epic Breakdown & Estimations - Missing Sprint Backlog | Less than 5% | NA | YES | Better identify the interdependancy between the trackers
2024-11-05 12:28 | Mohammed Fayaz | QA | Chipmuks | Yes | CHATGPT | 10% or below | Yes | Yes | Balanced | 4 | 4 | 4 | 4 | Yes | 4 | 4 | Scrum Team | 4 | 4 | Yes | 4 | YES | Moderate | Less than 10% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Average | Code Freeze Milestones and hardening phase | Sprint Closure/review | Non Release Activity Identification & capacity reserve | Blocking Scope change | Work allocation with sufficient capacity reserve | Modifications on Approved Tech designs | Less than 5% |  | YES | NA
2024-11-05 12:43 | Mohammed Fayaz | QA | Iota | Yes |  | 10% or below | No | No
2024-11-05 12:48 | Mujtaba Ahmad | EM | Falcon and Indus | No |  |  |  | Yes | Balanced | 4 | 4 | 5 | 5 | Partially/Incomplete | 4 | 4 | Scrum Team | 4 | 4 | Yes | 4 | YES | Multiple | Less than 10% | Yes | Moderate | Balanced (80% - 90%) | Some Information but still need further details | Yes | Well Managed | Continuous Epic Grooming | Sprint Planning | Backlog & CS bugs prioritisation | Strict Bug SLA's | Release Planning, Strategy & Schedule (Proper Checkpoint and dates on jira tickets) | Improper Epic Breakdown & Estimations - Missing Sprint Backlog | My role involves process improvement and enablement (EM's, SM's & Other folks responsible for process streamlining) |  | YES | NA
2024-11-05 12:58 | Mohammed Fayaz | QA | Stark | Yes | Github copilot | Just started using AI, need time to quantify | Yes | Yes | Well Managed | 5 | 5 | 5 | 4 | Yes | 5 | 5 | Individual | 5 | 4 | Yes | 5 | YES | Multiple | 10% to 20% | No | Multiple | Over Utilised (90% and Above) | Optimal information available | Yes | Average | Committed Epic Prioritisation | Sprint Planning | Ad-hoc requests prioritisation and acceptance | Change in Due date and QA Sign off Date restrictions | Effective communication | Ad-hoc Tasks & improper prioritisation | More than 10% but Less than 20% |  | YES | Adhoc tasks needs to be prioritized earlier and overloading with adhoc tasks
2024-11-05 13:22 | Mohammed Fayaz | QA & Scrum Master | Indus | Yes | chatGPT and GitHub copilot | 10% to 20% | Yes | Yes | Balanced | 2 | 3 | 5 | 4 | Partially/Incomplete | 4 | 5 | Scrum Team | 5 | 5 | Yes | 5 | Moderately | Multiple | 10% to 20% | No | Moderate | Over Utilised (90% and Above) | Some Information but still need further details | Yes | Average | Committed Epic Prioritisation | Sprint Planning | Backlog & CS bugs prioritisation | Change in Due date and QA Sign off Date restrictions | Work allocation with sufficient capacity reserve | CS Bugs higher than the reserved Capacity | More Than 5% but less than 10% |  | YES | Managers should be more involved in release activities; they should be aware of challenges and provide solutions instead of asking questions at the last moment.
2024-11-05 15:07 | Jegadeesh Santhana Krishnan | Dev | Eirene | Yes | Copilot | 10% to 20% | Yes | Yes | Well Managed | 5 | 5 | 5 | 5 | Yes | 4 | 5 | Individual | 5 | 5 | Yes | 4 | YES | Multiple | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Some Information but still need further details | Yes | Well Managed | Release Kick Off | Sprint Planning | Jira Details - Epic breakdown, DoD, Exit criteria, CS Bugs | Change in Due date and QA Sign off Date restrictions | Efficient Jira Usage (New Fields such as - Due date, QA Lead, QA Involvement, QA Signoff date) | Partial or missing details on Jira Trackers Description | Less than 5% |  | YES | nil
2024-11-05 15:30 | Mujtaba Ahmad | Dev | Stark | Yes | Copilot, chatGPT | 10% to 20% | Yes | Yes | Balanced | 4 | 4 | 4 | 4 | Yes | 4 | 4 | Individual | 4 | 4 | No |  | Moderately | Moderate | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Epic Breakdown | Sprint Planning | Tech Design | Blocking Scope change | Better Estimations & Epic Breakdown | Ad-hoc Tasks & improper prioritisation | More than 10% but Less than 20% |  | YES | NA
2024-11-05 15:59 | Jegadeesh Santhana Krishnan | Dev | Echo | Yes | copilot | 20% to 30% | Yes | Yes | Well Managed | 5 | 5 | 5 | 5 | Yes | 5 | 4 | Individual | 5 | 5 | Yes | 5 | YES | Multiple | 10% to 20% | Yes | Multiple | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Code Freeze Milestones and hardening phase | Sprint Planning | Ad-hoc requests prioritisation and acceptance | Blocking Scope change | Effective communication | Ad-hoc Tasks & improper prioritisation | More Than 5% but less than 10% |  | YES | .
2024-11-05 16:00 | Sandeep Kumar | Dev | Iota | Yes | GitHub Copilot, OpenAI reviews GitHub | 10% to 20% | Yes | Yes | Balanced | 4 | 3 | 5 | 4 | Partially/Incomplete | 3 | 4 | SME/Epic Owner/EM/QM (Pre Defined Efforts Estimates) | 4 | 3 | Yes | 4 | YES | Multiple | 20% to 30% | No | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Epic Breakdown | Sprint Closure/review | Non Release Activity Identification & capacity reserve | Risk call out during Weekly SoS | Better Estimations & Epic Breakdown | Ad-hoc Tasks & improper prioritisation | Less than 5% |  | YES | NA
2024-11-05 17:36 | Jegadeesh Santhana Krishnan | Dev | Chloris | Yes | Copilot | 10% or below | Yes | Yes | Balanced | 4 | 5 | 5 | 4 | No | 4 | 4 | Individual | 3 | 2 | Yes | 4 | YES | None | 10% to 20% | Yes | Moderate | Over Utilised (90% and Above) | Some Information but still need further details | Not aware and did not find any significant change in the release coordination among teams | Well Managed | Epic Breakdown | Sprint Retrospective | KT and recording repository | Blocking Scope change | Efficient Jira Usage (New Fields such as - Due date, QA Lead, QA Involvement, QA Signoff date) | Ad-hoc Tasks & improper prioritisation | More Than 5% but less than 10% |  | Not Efficiently | NA
2024-11-05 18:01 | Krishna Kishore Mothukuri | Dev & Scrum Master | Velocity | Yes | Chatgpt | 20% to 30% | Yes | Yes | Balanced | 4 | 4 | 4 | 5 | Partially/Incomplete | 4 | 5 | Individual | 4 | 4 | Yes | 5 | YES | Multiple | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Some Information but still need further details | Yes | Well Managed | Epic Breakdown | Sprint Planning | Jira Details - Epic breakdown, DoD, Exit criteria, CS Bugs | Blocking Scope change | Effective communication | Improper Epic Breakdown & Estimations - Missing Sprint Backlog | More Than 5% but less than 10% |  | YES | Proper Epic Breakdown
2024-11-05 19:37 | Jegadeesh Santhana Krishnan | Dev | Pheonix | Yes | Copilot | 10% to 20% | Yes | No
2024-11-05 20:07 | Mujtaba Ahmad | Dev | Indus | Yes | Copilot chatgpt | 20% to 30% | Yes | Yes | Balanced | 5 | 5 | 5 | 5 | Yes | 5 | 5 | Scrum Team | 5 | 5 | Yes | 5 | YES | Multiple | More than 30% | Yes | Multiple | Over Utilised (90% and Above) | Optimal information available | Yes | Well Managed | Code Freeze Milestones and hardening phase | Sprint Retrospective | Jira Automation | Risk call out during Weekly SoS | Effective communication | CS Bugs higher than the reserved Capacity | Less than 5% | NA | YES | NA
2024-11-06 10:31 | Jegadeesh Santhana Krishnan | Dev | Chipmuks | Yes | copilot | 20% to 30% | Yes | No
2024-11-06 10:45 | Jegadeesh Santhana Krishnan | Dev | Chipmuks | Yes | github copilot | 10% to 20% | Yes | Yes | Balanced | 5 | 5 | 4 | 5 | Yes | 4 | 4 | Scrum Team | 4 | 4 | Yes | 4 | YES | Multiple | Less than 10% | Yes | Moderate | Balanced (80% - 90%) | Some Information but still need further details | Not aware of any such initiative. Though the release coordination among teams was better than previous releases among teams | Well Managed | Monitoring and Controlling Progress | Sprint Closure/review | KT and recording repository | Blocking Scope change | Better Estimations & Epic Breakdown | Reviews | Less than 5% |  | YES | -
2024-11-06 11:16 | Mohammed Fayaz | QA | Skywalker | Yes | chatgpt | 10% or below | Yes | Yes | Balanced | 4 | 4 | 5 | 4 | Yes | 5 | 4 | Individual | 5 | 5 | Yes | 5 | YES | Moderate | Less than 10% | Yes | Multiple | Over Utilised (90% and Above) | Optimal information available | Not aware of any such initiative. Though the release coordination among teams was better than previous releases among teams | Well Managed | Continuous Epic Grooming | Sprint Planning | Tech Design | Blocking Scope change | Reduced over commit | Improper Epic Breakdown & Estimations - Missing Sprint Backlog | Less than 5% |  | YES | No
2024-11-06 11:21 | Mujtaba Ahmad | Dev & Scrum Master | Titans | Yes | Chat GPT, co pilot | 10% to 20% | Yes | Yes | Balanced | 5 | 5 | 5 | 5 | Yes | 5 | 5 | Scrum Team | 5 | 5 | Yes | 5 | YES | Moderate | 10% to 20% | Yes | Moderate | Over Utilised (90% and Above) | Optimal information available | Yes | Average | Release Kick Off | Sprint Closure/review | Jira Automation | Risk call out during Weekly SoS | Better & transparent commitments | Delay in commitments from dependant team | My role involves process improvement and enablement (EM's, SM's & Other folks responsible for process streamlining) |  | YES | Patch and Hotfix process should be well defined and should be conveyed to everyone before hand including any updated steps.
2024-11-06 11:22 | Mujtaba Ahmad | Dev | Titans | Yes | co-pilot, chatgpt | 10% or below | Yes | Yes | Balanced | 5 | 4 | 4 | 4 | Yes | 5 | 5 | Individual | 5 | 5 | Yes | 5 | YES | Moderate | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Release Kick Off | Sprint Closure/review | Jira Automation | Risk call out during Weekly SoS | Release Planning, Strategy & Schedule (Proper Checkpoint and dates on jira tickets) | Delay in commitments from dependant team | More Than 5% but less than 10% |  | YES | There should be a well defined and documented process for Patch and hotfix release, so that the process is consistent and stream lined.
2024-11-06 11:43 | Jegadeesh Santhana Krishnan | Dev & Scrum Master | Tintin | Yes | Copilot | 10% to 20% | Yes | Yes | Chaotic | 4 | 2 | 1 | 3 | Partially/Incomplete | 3 | 3 | Individual | 5 | 2 | No |  | YES | Moderate | Less than 10% | Yes | Moderate | Over Utilised (90% and Above) | Some Information but still need further details | Yes | Well Managed | Committed Epic Prioritisation | Sprint Planning | CI/CD, Testing & Continuous planning | Blocking Scope change | Release Planning, Strategy & Schedule (Proper Checkpoint and dates on jira tickets) | Improper Epic Breakdown & Estimations - Missing Sprint Backlog | My role involves process improvement and enablement (EM's, SM's & Other folks responsible for process streamlining) |  | YES | Better Epic prioritization
2024-11-06 12:09 | Mohammed Fayaz | QA | Dynamos | Yes | chatGPT | 10% to 20% | Yes | Yes | Well Managed | 5 | 5 | 5 | 4 | Yes | 5 | 5 | Scrum Team | 5 | 4 | Yes | 4 | YES | Moderate | Less than 10% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Continuous Epic Grooming | Sprint Retrospective | Non Release Activity Identification & capacity reserve | Blocking Scope change | Release Planning, Strategy & Schedule (Proper Checkpoint and dates on jira tickets) | Modifications on Approved Tech designs | Less than 5% |  | YES | -
2024-11-06 12:22 | Mujtaba Ahmad | Dev | Titans | No |  |  |  | No
2024-11-06 12:26 | Mujtaba Ahmad | Dev & Scrum Master | Apollo | Yes | Github Copilot | 10% or below | No | Yes | Balanced | 4 | 4 | 4 | 4 | Yes | 4 | 4 | Individual | 4 | 4 | Yes | 3 | Moderately | Multiple | Less than 10% | Yes | Multiple | Over Utilised (90% and Above) | Some Information but still need further details | Yes | Average | Continuous Epic Grooming | Sprint Retrospective | Tech Design | Blocking Scope change | None | Intra team collaboration | My role involves process improvement and enablement (EM's, SM's & Other folks responsible for process streamlining) |  | YES | na
2024-11-06 12:31 | Mujtaba Ahmad | Dev | Apollo | Yes | Chatgpt and copilot | 10% to 20% | Yes | Yes | Balanced | 3 | 2 | 4 | 4 | Yes | 3 | 3 | Scrum Team | 4 | 3 | Yes | 3 | YES | Moderate | 10% to 20% | Yes | Moderate | Over Utilised (90% and Above) | Some Information but still need further details | Yes | Average | Committed Epic Prioritisation | Sprint Planning | Jira Details - Epic breakdown, DoD, Exit criteria, CS Bugs | Change in Due date and QA Sign off Date restrictions | Work allocation with sufficient capacity reserve | Ad-hoc Tasks & improper prioritisation | More than 10% but Less than 20% |  | Not Efficiently | Sprint planning effectiveness does not have any metrics for scrum team.
2024-11-06 12:32 | Mohammed Fayaz | QA | Hercules | Yes | Chatgpt | 10% to 20% | Yes | Yes | Well Managed | 4 | 4 | 4 | 4 | Yes | 5 | 3 | Scrum Team | 4 | 4 | Yes | 5 | YES | Moderate | 20% to 30% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Code Freeze Milestones and hardening phase | Sprint Planning | Ad-hoc requests prioritisation and acceptance | Blocking Scope change | Better Estimations & Epic Breakdown | Ad-hoc Tasks & improper prioritisation | Less than 5% | NA | YES | NA
2024-11-06 12:33 | Sandeep Kumar | Dev | Sudo | Yes | copilot | 10% to 20% | No | Yes | Balanced | 4 | 3 | 3 | 4 | Yes | 4 | 4 | Scrum Team | 4 | 4 | Yes | 4 | YES | Multiple | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Epic Breakdown | Sprint DSU's | Tech Design | Strict Bug SLA's | Better & transparent commitments | Ad-hoc Tasks & improper prioritisation | More than 10% but Less than 20% |  | YES | NA
2024-11-06 12:35 | Others | Dev | Dexter | Yes | ChatGPT | Just started using AI, need time to quantify | No | Yes | Well Managed | 4 | 3 | 4 | 5 | Yes | 3 | 5 | Scrum Team | 5 | 5 | Yes | 4 | Moderately | Multiple | Less than 10% | No | None | Balanced (80% - 90%) | Some Information but still need further details | Not aware of any such initiative. Though the release coordination among teams was better than previous releases among teams | Well Managed | Monitoring and Controlling Progress | Sprint Closure/review | KT and recording repository | Change in Due date and QA Sign off Date restrictions | None | Non Release Activities | Less than 5% |  | Not Efficiently | N
2024-11-06 12:35 | Jegadeesh Santhana Krishnan | Dev | Tintin | Yes | copilot | 10% or below | Yes | Yes | Well Managed |  |  |  |  | Yes |  |  | Individual |  |  | Yes | 4 | YES | Moderate | 10% to 20% | Yes |  |  | Some Information but still need further details | Yes | Well Managed | Monitoring and Controlling Progress | Sprint Planning | Jira Details - Epic breakdown, DoD, Exit criteria, CS Bugs | Strict Bug SLA's | Release Planning, Strategy & Schedule (Proper Checkpoint and dates on jira tickets) | Delayed Response on open Queries, need multiple followups | Less than 5% |  | YES | No
2024-11-06 12:37 | Sandeep Kumar | Dev | Zeta | Yes | copilot and chatgpt | 10% to 20% | Yes | Yes | Balanced | 5 | 5 | 4 | 5 | Partially/Incomplete | 5 | 5 | Scrum Team | 5 | 5 | Yes | 5 | YES | Moderate | Less than 10% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Code Freeze Milestones and hardening phase | Sprint Closure/review | Tech Design | Change in Due date and QA Sign off Date restrictions | None | Ad-hoc Tasks & improper prioritisation | More Than 5% but less than 10% |  | YES | No
2024-11-06 12:44 | Mujtaba Ahmad | Dev | Falcon | Yes | ChatGPT | 30% and Above | Yes | Yes | Balanced | 4 | 4 | 4 | 3 | Partially/Incomplete | 4 | 4 | Scrum Team | 4 | 3 | Yes | 3 | YES | Moderate | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Some Information but still need further details | Not aware of any such initiative. Though the release coordination among teams was better than previous releases among teams | Well Managed | Code Freeze Milestones and hardening phase | Sprint Retrospective | CI/CD, Testing & Continuous planning | Blocking Scope change | Better & transparent commitments | Partial or missing details on Jira Trackers Description | Less than 5% |  | YES | No
2024-11-06 12:45 | Sandeep Kumar | Dev | Zeta | Yes | Copilot, ChatGPT | 10% to 20% | No | Yes | Well Managed | 5 | 5 | 3 | 5 | Yes | 4 | 5 | Individual | 5 | 5 | Yes | 5 | YES | Moderate | 10% to 20% | Yes | Moderate | Over Utilised (90% and Above) | Optimal information available | Not aware of any such initiative. Though the release coordination among teams was better than previous releases among teams | Well Managed | Committed Epic Prioritisation | Sprint Planning | Bugs Management & Deferring | Blocking Scope change | Efficient Jira Usage (New Fields such as - Due date, QA Lead, QA Involvement, QA Signoff date) | Ad-hoc Tasks & improper prioritisation | More than 10% but Less than 20% |  | YES | NA
2024-11-06 12:47 | Jegadeesh Santhana Krishnan | Dev | Pheonix | Yes | Github copilot | 30% and Above | Yes | Yes | Well Managed | 5 | 5 | 5 | 5 | Yes | 5 | 5 | Individual | 5 | 5 | Yes | 5 | YES | Multiple | Less than 10% | Yes | None | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Monitoring and Controlling Progress | Sprint Planning | Ad-hoc requests prioritisation and acceptance | Risk call out during Weekly SoS | Efficient Jira Usage (New Fields such as - Due date, QA Lead, QA Involvement, QA Signoff date) | Delayed Response on open Queries, need multiple followups | Less than 5% |  | YES | NA
2024-11-06 12:47 | Mujtaba Ahmad | Dev | Apollo | Yes | ChatGPT/Gemini | 10% to 20% | Yes | Yes | Balanced | 4 | 4 | 4 | 5 | Yes | 4 | 4 | Scrum Team | 5 | 5 | Yes | 5 | YES | Multiple | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Not aware of any such initiative. Though the release coordination among teams was better than previous releases among teams | Well Managed | Committed Epic Prioritisation | Sprint Planning | Non Release Activity Identification & capacity reserve | Risk call out during Weekly SoS | Sprint Planning Structure | Non Release Activities | Less than 5% |  | YES | NA
2024-11-06 12:58 | Mujtaba Ahmad | Dev | Apollo | Yes | chatgpt | Just started using AI, need time to quantify | Yes | Yes | Balanced | 4 | 5 | 5 | 5 | Yes | 4 | 3 | Scrum Team | 3 | 3 | Yes | 4 | Moderately | Moderate | Less than 10% | Yes | Moderate | Over Utilised (90% and Above) | Some Information but still need further details | Yes | Average | Continuous Epic Grooming | Sprint Planning | Non Release Activity Identification & capacity reserve | Risk call out during Weekly SoS | Sprint Planning Structure | Intra team collaboration | Less than 5% |  | YES | no
2024-11-06 13:04 | Mohammed Fayaz | QA | Tintin | Yes | Gemini | 10% to 20% | Yes | Yes | Balanced | 3 | 4 | 4 | 4 | Yes | 5 | 5 | Individual | 5 | 5 | No |  | Moderately | Multiple | Less than 10% | No | Moderate | Over Utilised (90% and Above) | Some Information but still need further details | Yes | Well Managed | Code Freeze Milestones and hardening phase | Sprint Planning | Intra Team Collaboration - Dependency linking on Jira by Individual owners | Change in Due date and QA Sign off Date restrictions | Effective communication | Delayed Response on open Queries, need multiple followups | More Than 5% but less than 10% |  | YES | Please include the crucial epics at the starting of the release
2024-11-06 13:11 | Mohammed Fayaz | QA | Sudo | No |  |  |  | Yes | Balanced | 5 | 5 | 5 | 5 | Yes | 5 | 5 | Individual | 5 | 5 | Yes | 5 | YES | Moderate | Less than 10% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Code Freeze Milestones and hardening phase | Sprint Closure/review | CI/CD, Testing & Continuous planning | Strict Bug SLA's | Release Planning, Strategy & Schedule (Proper Checkpoint and dates on jira tickets) | Missing SLA's for Bugs, Trackers on Jira | Less than 5% |  | YES | NO
2024-11-06 13:28 | Sandeep Kumar | Dev | Dynamos | Yes | copilot, chatGPT | 20% to 30% | Yes | Yes | Balanced | 4 | 4 | 3 | 4 | Partially/Incomplete | 4 | 5 | Individual | 4 | 3 | Yes | 3 | Moderately | Moderate | 10% to 20% | Yes | None | Balanced (80% - 90%) | Some Information but still need further details | Not aware of any such initiative. Though the release coordination among teams was better than previous releases among teams | Well Managed | Epic Breakdown | Sprint Closure/review | Jira Details - Epic breakdown, DoD, Exit criteria, CS Bugs | Blocking Scope change | Sprint Planning Structure | Reviews | More Than 5% but less than 10% |  | YES | No
2024-11-06 13:33 | Jegadeesh Santhana Krishnan | Dev & Scrum Master | Hercules | Yes | Github Copilot | 10% to 20% | Yes | Yes | Balanced | 4 | 4 | 4 | 5 | Yes | 4 | 4 | Individual | 4 | 4 | Yes | 3 | YES | Moderate | Less than 10% | Yes | None | Over Utilised (90% and Above) | Optimal information available | Yes | Well Managed | Release Kick Off | Sprint Closure/review | Jira Details - Epic breakdown, DoD, Exit criteria, CS Bugs | Strict Bug SLA's | Effective communication | Improper Epic Breakdown & Estimations - Missing Sprint Backlog | My role involves process improvement and enablement (EM's, SM's & Other folks responsible for process streamlining) |  | YES | N/A
2024-11-06 13:48 | Mohammed Fayaz | QA | Apollo | Yes | Chat GPT,Gemini | 20% to 30% | Yes | Yes | Balanced | 4 | 4 | 4 |  | Yes | 4 | 4 | Scrum Team | 5 | 5 | Yes | 5 | YES | Moderate | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Average | Code Freeze Milestones and hardening phase | Sprint Planning | KT and recording repository | Change in Due date and QA Sign off Date restrictions | None | Ad-hoc Tasks & improper prioritisation | More Than 5% but less than 10% |  | YES | N/A
2024-11-06 13:56 | Mohammed Fayaz | QA | Sharks | Yes | Chatgpt | 10% or below | Yes | Yes | Well Managed | 5 | 5 | 5 | 5 | Yes | 5 | 5 | Scrum Team | 5 | 5 | Yes | 5 | YES | Multiple | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Epic Breakdown | Sprint Planning | Backlog & CS bugs prioritisation | Risk call out during Weekly SoS | Effective communication | Reviews | Less than 5% | NO | YES | NA
2024-11-06 14:44 | Sandeep Kumar | Dev & Scrum Master | Sudo | Yes | Github copilot, Claude, Chat-Gpt | 20% to 30% | Yes | Yes | Balanced | 4 | 4 | 4 | 4 | Yes | 4 | 4 | SME/Epic Owner/EM/QM (Pre Defined Efforts Estimates) | 4 | 4 | Yes | 4 | YES | Moderate | 20% to 30% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Committed Epic Prioritisation | Sprint Planning | KT and recording repository | Blocking Scope change | Better & transparent commitments | Modifications on Approved Tech designs | More than 10% but Less than 20% |  | YES | NA
2024-11-06 14:54 | Mohammed Fayaz | QA | Skywalker | No |  |  |  | Yes | Balanced | 4 | 3 | 4 | 3 | Yes | 4 | 4 | Scrum Team | 3 | 3 | Yes | 3 | Moderately | Moderate | 10% to 20% | No | Moderate | Balanced (80% - 90%) | Some Information but still need further details | Yes | Average | Epic Breakdown | Sprint DSU's | KT and recording repository | Risk call out during Weekly SoS | Effective communication | Ad-hoc Tasks & improper prioritisation | More Than 5% but less than 10% |  | YES | no
2024-11-06 15:18 | Mujtaba Ahmad | Dev & Scrum Master | Indus | Yes | CoPilot, ChatGPT | 10% to 20% | Yes | Yes | Balanced | 4 | 4 | 4 | 5 | Yes | 5 | 4 | Scrum Team | 3 | 4 | Yes | 3 | YES | Moderate | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Monitoring and Controlling Progress | Sprint Closure/review | Ad-hoc requests prioritisation and acceptance | Risk call out during Weekly SoS | Release Planning, Strategy & Schedule (Proper Checkpoint and dates on jira tickets) | Reviews | Less than 5% |  | YES | No
2024-11-06 19:44 | Mujtaba Ahmad | Dev & Scrum Master | Falcon | Yes | Copilot and Chatgpt | 10% to 20% | Yes | Yes | Balanced | 4 | 4 | 4 | 4 | Yes | 4 | 4 | Scrum Team | 4 | 4 | Yes | 5 | YES | Moderate | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Some Information but still need further details | Yes | Average | Epic Breakdown | Sprint Planning | KT and recording repository | Blocking Scope change | Reduced over commit | Ad-hoc Tasks & improper prioritisation | More than 10% but Less than 20% |  | YES | Epic grooming and breakdown is necessary.
2024-11-06 19:51 | Mohammed Fayaz | QA | Falcon | No |  |  |  | Yes | Balanced | 5 | 4 | 4 | 4 | Yes | 5 | 5 | Scrum Team | 5 | 5 | Yes | 5 | YES | Moderate | 10% to 20% | Yes | Moderate | Over Utilised (90% and Above) | Optimal information available | Yes | Well Managed | Continuous Epic Grooming | Sprint Retrospective | Jira Details - Epic breakdown, DoD, Exit criteria, CS Bugs | Change in Due date and QA Sign off Date restrictions | Work allocation with sufficient capacity reserve | Partial or missing details on Jira Trackers Description | More Than 5% but less than 10% | NA | YES | Concern: Applicable to Dev, Please add the tracker description n required details on the each jira tickets and also please make sure to add Devloper notes to QA for all trackers on jira
2024-11-06 20:02 | Mohammed Fayaz | QA | Iris | No |  |  |  | Yes | Well Managed | 5 | 5 | 5 | 5 | Yes | 5 | 5 | Individual | 5 | 5 | Yes | 5 | YES | Multiple | 10% to 20% | Yes | Moderate | Over Utilised (90% and Above) | Optimal information available | Yes | Well Managed | Continuous Epic Grooming | Sprint Closure/review | Non Release Activity Identification & capacity reserve | Risk call out during Weekly SoS | Better & transparent commitments | Non Release Activities | More Than 5% but less than 10% |  | YES | no
2024-11-06 20:07 | Jegadeesh Santhana Krishnan | Dev | Hercules | Yes | Github Copilot | 10% to 20% | Yes | Yes | Balanced | 4 | 4 | 3 | 4 | Yes | 4 | 4 | Individual | 4 | 4 | Yes | 4 | YES | Moderate | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Some Information but still need further details | Yes | Average | Epic Breakdown | Sprint DSU's | Tech Design | Blocking Scope change | Release Planning, Strategy & Schedule (Proper Checkpoint and dates on jira tickets) | Ad-hoc Tasks & improper prioritisation | More Than 5% but less than 10% |  | YES | Current process is efficient
2024-11-07 10:52 | Jegadeesh Santhana Krishnan | Dev & Scrum Master | Dexter | Yes | Copilot, GPT | 10% or below | Yes | Yes | Well Managed | 5 | 5 | 5 | 4 | Yes | 4 | 4 | Individual | 5 | 5 | Yes | 4 | YES | Moderate | Less than 10% | No | Multiple | Balanced (80% - 90%) | Some Information but still need further details | Yes | Well Managed | Monitoring and Controlling Progress | Sprint DSU's | KT and recording repository | Risk call out during Weekly SoS | Sprint Planning Structure | Ad-hoc Tasks & improper prioritisation | My role involves process improvement and enablement (EM's, SM's & Other folks responsible for process streamlining) |  | YES | -
2024-11-07 11:02 | Jegadeesh Santhana Krishnan | Dev | Dexter | No |  |  |  | Yes | Balanced | 5 | 5 | 4 | 4 | Yes | 4 | 5 | Scrum Team | 5 | 4 | Yes | 5 | YES | Multiple | 10% to 20% | Yes | Moderate | Over Utilised (90% and Above) | Some Information but still need further details | Yes | Well Managed | Release Kick Off | Sprint Closure/review | Ad-hoc requests prioritisation and acceptance | Risk call out during Weekly SoS | Effective communication | Improper Epic Breakdown & Estimations - Missing Sprint Backlog | More Than 5% but less than 10% |  | YES | Keeping a check on processes from the Program Management side would be beneficial in order to limit the non-dev work engineers have to do.
2024-11-07 11:08 | Jegadeesh Santhana Krishnan | Dev & Scrum Master | Chipmuks | Yes | Git co-pilot | 10% to 20% | Yes | Yes | Balanced | 5 | 5 | 5 | 5 | Yes | 5 | 5 | Scrum Team | 5 | 5 | Yes | 5 | YES | Moderate | 20% to 30% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Not aware of any such initiative. Though the release coordination among teams was better than previous releases among teams | Well Managed | Continuous Epic Grooming | Sprint Retrospective | Backlog & CS bugs prioritisation | Blocking Scope change | Work allocation with sufficient capacity reserve | CS Bugs higher than the reserved Capacity | More Than 5% but less than 10% |  | YES | nil
2024-11-07 12:07 | Krishna Kishore Mothukuri | Dev | Pathfinders | Yes | Github Copilot, Chat GPT Enterprise | 30% and Above | Yes | Yes | Balanced | 5 | 5 | 4 | 5 | Yes | 5 | 4 | Individual | 4 | 4 | Yes | 4 | YES | Multiple | Less than 10% | Yes | None | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Continuous Epic Grooming | Sprint Planning | Test Design | Change in Due date and QA Sign off Date restrictions | None | Ad-hoc Tasks & improper prioritisation | Less than 5% |  | YES | None
2024-11-07 12:20 | Mohammed Fayaz | QA | Tranformers | Yes | ChatGPT | 20% to 30% | Yes | No
2024-11-07 12:22 | Jegadeesh Santhana Krishnan | Dev | Skywalker | Yes | copilot | 10% to 20% | Yes | No
2024-11-07 12:23 | Jegadeesh Santhana Krishnan | Dev | Chipmuks | Yes | chatgpt, github copilot | 10% or below | Yes | Yes | Chaotic | 4 | 4 | 5 | 5 | Yes | 5 | 4 | Scrum Team | 4 | 4 | Yes | 4 | YES | Moderate | 10% to 20% | No | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Average | Continuous Epic Grooming | Sprint Planning | Backlog & CS bugs prioritisation | Strict Bug SLA's | Better Estimations & Epic Breakdown | Delay in commitments from dependant team | More Than 5% but less than 10% |  | YES | Nothing as of now.
2024-11-07 12:27 | Jegadeesh Santhana Krishnan | Dev | Helios | Yes | copilot autosuggest and chat (part of vscode ext)) | 20% to 30% | Yes | Yes | Well Managed | 3 | 3 | 2 | 4 | Partially/Incomplete | 3 | 4 | Individual | 4 | 4 | Yes | 4 | YES | Moderate | 20% to 30% | Yes | None | Under Utilisation (80% Below) | Optimal information available | Yes | Average | Epic Breakdown | Sprint Planning | Jira Details - Epic breakdown, DoD, Exit criteria, CS Bugs | Risk call out during Weekly SoS | Effective communication | Improper Epic Breakdown & Estimations - Missing Sprint Backlog | Less than 5% |  | YES | N.A
2024-11-07 12:30 | Mujtaba Ahmad | Dev | Falcon | Yes | Copilot and ChatGPT | 10% or below | Yes | Yes | Balanced | 4 | 4 | 4 | 4 | Yes | 4 | 4 | Scrum Team | 4 | 4 | Yes | 4 | YES | Moderate | 10% to 20% | Yes | Moderate | Over Utilised (90% and Above) | Some Information but still need further details | Yes | Average | Monitoring and Controlling Progress | Sprint Closure/review | Non Release Activity Identification & capacity reserve | Change in Due date and QA Sign off Date restrictions | Efficient Jira Usage (New Fields such as - Due date, QA Lead, QA Involvement, QA Signoff date) | PR Merges | More Than 5% but less than 10% | N/A | YES | N/A
2024-11-07 12:31 | Krishna Kishore Mothukuri | Dev | Velocity | Yes | Co pilot, claude | 20% to 30% | Yes | No
2024-11-07 12:33 | Sandeep Kumar | Others | Phi | Yes | Chat GPT | 20% to 30% | Yes | Yes | Chaotic | 3 | 4 | 4 | 4 | Yes | 4 | 4 | Scrum Team | 3 | 3 | Yes | 4 | YES | None | Less than 10% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Average | Committed Epic Prioritisation | Sprint Planning | Jira Details - Epic breakdown, DoD, Exit criteria, CS Bugs | Blocking Scope change | Release Planning, Strategy & Schedule (Proper Checkpoint and dates on jira tickets) | Improper Epic Breakdown & Estimations - Missing Sprint Backlog | My role involves process improvement and enablement (EM's, SM's & Other folks responsible for process streamlining) |  | YES | No
2024-11-07 12:39 | Mohammed Fayaz | QA | Iota | Yes | Chatgpt | Just started using AI, need time to quantify | Yes | Yes | Well Managed | 4 | 4 | 3 | 5 | Partially/Incomplete | 4 | 4 | Individual | 3 | 3 | Yes | 3 | YES | Moderate | 10% to 20% | Yes | None | Over Utilised (90% and Above) | Optimal information available | Yes | Well Managed | Continuous Epic Grooming | Sprint Planning | Jira Details - Epic breakdown, DoD, Exit criteria, CS Bugs | Blocking Scope change | Efficient Jira Usage (New Fields such as - Due date, QA Lead, QA Involvement, QA Signoff date) | Improper Epic Breakdown & Estimations - Missing Sprint Backlog | Less than 5% | NA | YES | NA
2024-11-07 12:42 | Jegadeesh Santhana Krishnan | Dev | Skywalker | Yes | copilot | 10% or below | No | Yes | Balanced | 4 | 3 | 4 | 4 | Partially/Incomplete | 4 | 5 | Individual | 5 | 4 | Yes | 4 | YES | Moderate | 20% to 30% | Yes | Moderate | Under Utilisation (80% Below) | Some Information but still need further details | Not aware of any such initiative. Though the release coordination among teams was better than previous releases among teams | Well Managed | Epic Breakdown | Sprint Planning | Tech Design | Change in Due date and QA Sign off Date restrictions | None | Reviews | Less than 5% |  | YES | none
2024-11-07 12:43 | Jegadeesh Santhana Krishnan | Dev | Eirene | Yes | ChatGPT and Copilot | 20% to 30% | Yes | Yes | Well Managed | 5 | 5 | 5 | 5 | Yes | 5 | 5 | Individual | 5 | 5 | Yes | 5 | YES | Moderate | Less than 10% | Yes | None | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Continuous Epic Grooming | Sprint Retrospective | Jira Details - Epic breakdown, DoD, Exit criteria, CS Bugs | Blocking Scope change | Sprint Planning Structure | Improper Epic Breakdown & Estimations - Missing Sprint Backlog | Less than 5% |  | YES | NA
2024-11-07 12:45 | Sandeep Kumar | Dev & Scrum Master | Iota | Yes | Copilot | 10% or below | Yes | Yes | Well Managed | 4 | 4 | 5 | 5 | Yes | 5 | 5 | Scrum Team | 5 | 5 | Yes | 5 | YES | Moderate | 10% to 20% | Yes | None | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Epic Breakdown | Sprint Closure/review | Backlog & CS bugs prioritisation | Strict Bug SLA's | Better & transparent commitments | CS Bugs higher than the reserved Capacity | My role involves process improvement and enablement (EM's, SM's & Other folks responsible for process streamlining) |  | YES | NA
2024-11-07 12:45 | Jegadeesh Santhana Krishnan | Dev | Skywalker | No |  |  |  | No
2024-11-07 12:54 | Mohammed Fayaz | QA | Titans | Yes | chatgpt | Just started using AI, need time to quantify | Yes | Yes | Well Managed | 5 | 5 | 5 | 5 | Yes | 5 | 5 | Individual | 5 | 5 | Yes | 4 | YES | None | Less than 10% | Yes | None | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Committed Epic Prioritisation | Sprint Closure/review | Ad-hoc requests prioritisation and acceptance | Risk call out during Weekly SoS | Effective communication | Delay in commitments from dependant team | More than 10% but Less than 20% |  | YES | NA
2024-11-07 12:55 | Mohammed Fayaz | QA | Enigma | Yes | Custom ChatGPT | 10% or below | Yes | Yes | Balanced | 4 | 4 | 5 | 4 | Partially/Incomplete | 4 | 4 | Individual | 5 | 4 | Yes | 4 | YES | Moderate | 10% to 20% | No | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Monitoring and Controlling Progress | Sprint Closure/review | Ad-hoc requests prioritisation and acceptance | Change in Due date and QA Sign off Date restrictions | Efficient Jira Usage (New Fields such as - Due date, QA Lead, QA Involvement, QA Signoff date) | CS Bugs higher than the reserved Capacity | More than 10% but Less than 20% |  | YES | more of automated template in sprint review meeting instead of manually populating the story points completed
2024-11-07 12:59 | Mohammed Fayaz | QA | E2E | Yes | understanding new concepts | 20% to 30% | Yes | No
2024-11-07 13:05 | Mohammed Fayaz | QA | Chakra | Yes | Chatgpt | 10% or below | Yes | Yes | Balanced | 5 | 5 | 5 | 5 | Yes | 5 | 5 | Scrum Team | 5 | 5 | Yes | 5 | YES | Multiple | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Epic Breakdown | Sprint Planning | Jira Details - Epic breakdown, DoD, Exit criteria, CS Bugs | Strict Bug SLA's | Better Estimations & Epic Breakdown | Ad-hoc Tasks & improper prioritisation | Less than 5% |  | YES | NA
2024-11-07 13:09 | Sandeep Kumar | Dev & Scrum Master | Phi | Yes | ChatGPT and Git CoPilot | 10% to 20% | No | Yes | Balanced | 3 | 5 | 5 | 5 | Partially/Incomplete | 4 | 3 | Individual | 4 | 4 | Yes | 3 | Moderately | None | Less than 10% | Yes | Moderate | Over Utilised (90% and Above) | Some Information but still need further details | Yes | Average | Monitoring and Controlling Progress | Sprint Planning | Backlog & CS bugs prioritisation | Change in Due date and QA Sign off Date restrictions | Efficient Jira Usage (New Fields such as - Due date, QA Lead, QA Involvement, QA Signoff date) | Non Release Activities | More Than 5% but less than 10% |  | Not Efficiently | NA
2024-11-07 13:14 | Mujtaba Ahmad | Dev & Scrum Master | Enigma | No |  |  |  | Yes | Balanced | 4 | 4 | 4 | 4 | Partially/Incomplete | 4 | 4 | Scrum Team | 4 | 3 | Yes | 4 | YES | Moderate | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Average | Continuous Epic Grooming | Sprint Planning | CI/CD, Testing & Continuous planning | Risk call out during Weekly SoS | None | Non Release Activities | My role involves process improvement and enablement (EM's, SM's & Other folks responsible for process streamlining) |  | YES | -
2024-11-07 13:38 | Sandeep Kumar | Dev | Gryffindor | Yes | Copilot, ChatGPT | 10% to 20% | Yes | Yes | Balanced | 3 | 4 | 4 | 4 | Partially/Incomplete | 4 | 4 | Scrum Team | 4 | 4 | Yes | 4 | Moderately | Multiple | 10% to 20% | No | Multiple | Balanced (80% - 90%) | Optimal information available | Yes | Average | Committed Epic Prioritisation | Sprint Retrospective | Ad-hoc requests prioritisation and acceptance | Risk call out during Weekly SoS | Sprint Planning Structure | Ad-hoc Tasks & improper prioritisation | Less than 5% |  | YES | NA
2024-11-07 13:39 | Jegadeesh Santhana Krishnan | EM | EM | No |  |  |  | Yes | Well Managed | 5 | 5 | 5 | 5 | Yes | 5 | 5 | Individual | 5 | 5 | Yes | 5 | YES | Multiple | Less than 10% | Yes | None | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Continuous Epic Grooming | Sprint Planning | Intra Team Collaboration - Dependency linking on Jira by Individual owners | Change in Due date and QA Sign off Date restrictions | Better Estimations & Epic Breakdown | Intra team collaboration | My role involves process improvement and enablement (EM's, SM's & Other folks responsible for process streamlining) |  | YES | NO
2024-11-07 13:42 | Jegadeesh Santhana Krishnan | Dev | Dexter | Yes | Copliot and gpt | 10% or below | Yes | Yes | Balanced | 4 | 5 | 2 | 5 | Yes | 3 | 4 | Individual | 5 | 4 | Yes | 4 | Moderately | Moderate | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Some Information but still need further details | Not aware and did not find any significant change in the release coordination among teams | Average | Committed Epic Prioritisation | Sprint Retrospective | KT and recording repository | Risk call out during Weekly SoS | Better & transparent commitments | PR Merges | More Than 5% but less than 10% |  | YES | No
2024-11-07 13:42 | Mujtaba Ahmad | Dev | Chakra | Yes | Chat gpt | 10% or below | No | Yes | Well Managed | 4 | 5 | 3 | 5 | Partially/Incomplete | 5 | 5 | Scrum Team | 5 | 5 | Yes | 5 | YES | Moderate | Less than 10% | Yes | Moderate | Over Utilised (90% and Above) | Optimal information available | Yes | Well Managed | Monitoring and Controlling Progress | Sprint DSU's | Ad-hoc requests prioritisation and acceptance | Risk call out during Weekly SoS | Effective communication | Ad-hoc Tasks & improper prioritisation | Less than 5% |  | YES | -
2024-11-07 13:46 | Jegadeesh Santhana Krishnan | Dev & Scrum Master | Eirene | Yes | copilot and chatgpt | 10% or below | Yes | No
2024-11-07 13:47 | Jegadeesh Santhana Krishnan | Dev & Scrum Master | Chloris | Yes | Copilot | 10% or below | Yes | Yes | Well Managed | 4 | 4 | 4 | 4 | Yes | 5 | 5 | Individual | 5 | 5 | Yes | 5 | YES | Moderate | Less than 10% | Yes | None | Balanced (80% - 90%) | Some Information but still need further details | Yes | Well Managed | Committed Epic Prioritisation | Sprint Planning | Jira Details - Epic breakdown, DoD, Exit criteria, CS Bugs | Blocking Scope change | Better & transparent commitments | Delayed Response on open Queries, need multiple followups | My role involves process improvement and enablement (EM's, SM's & Other folks responsible for process streamlining) |  | YES | nil
2024-11-07 13:52 | Mujtaba Ahmad | Dev | Enigma | Yes | copilot | 10% to 20% | Yes | Yes | Balanced | 4 | 4 | 3 | 4 | Partially/Incomplete | 4 | 4 | Scrum Team | 4 | 3 | Yes | 5 | YES | Moderate | Less than 10% | Yes | None | Over Utilised (90% and Above) | Optimal information available | Not aware and did not find any significant change in the release coordination among teams | Average | Committed Epic Prioritisation | Sprint Closure/review | Bugs Management & Deferring | Risk call out during Weekly SoS | Efficient Jira Usage (New Fields such as - Due date, QA Lead, QA Involvement, QA Signoff date) | Non Release Activities | More Than 5% but less than 10% | No | YES | No
2024-11-07 13:59 | Jegadeesh Santhana Krishnan | Dev | Aurora | Yes | Copilot | 10% to 20% | Yes | No
2024-11-07 14:05 | Jegadeesh Santhana Krishnan | Dev | Aurora | Yes | ChatGPT, GitHub copilot | 30% and Above | Yes | Yes | Balanced | 4 | 3 | 4 | 4 | Yes | 4 | 4 | Scrum Team | 4 | 2 | Yes | 4 | YES | Multiple | 20% to 30% | Yes | Moderate | Balanced (80% - 90%) | Some Information but still need further details | Yes | Well Managed | Monitoring and Controlling Progress | Sprint Retrospective | Bugs Management & Deferring | Blocking Scope change | None | Reviews | Less than 5% |  | YES | Nothing
2024-11-07 14:07 | Sandeep Kumar | Dev | Iota | Yes | Copilot, Chat GPT | 20% to 30% | No | No
2024-11-07 14:10 | Mujtaba Ahmad | EM | Stark | Yes | GPT | 10% or below | Yes | Yes | Balanced | 5 | 5 | 5 | 5 | Yes | 5 | 5 | Scrum Team | 5 | 5 | Yes | 5 | YES | Moderate | 10% to 20% | Yes | None | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Continuous Epic Grooming | Sprint Planning | Jira Automation | Blocking Scope change | Better & transparent commitments | Delayed Test Designs | My role involves process improvement and enablement (EM's, SM's & Other folks responsible for process streamlining) |  | YES | More bandwidth reservation for designs within release.
2024-11-07 14:15 | Jegadeesh Santhana Krishnan | Dev | Skywalker | Yes | Git Chat | 10% to 20% | Yes | Yes | Balanced | 4 | 4 | 4 | 4 | Yes | 4 | 4 | Scrum Team | 4 | 4 | Yes | 4 | YES | Moderate | Less than 10% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Continuous Epic Grooming | Sprint Planning | Intra Team Collaboration - Dependency linking on Jira by Individual owners | Risk call out during Weekly SoS | Work allocation with sufficient capacity reserve | Reviews | Less than 5% |  | YES | NA
2024-11-07 14:15 | Mujtaba Ahmad | Dev | Titans | Yes | Chat GPT | 20% to 30% | Yes | Yes | Well Managed | 5 | 5 | 5 | 5 | Yes | 4 | 4 | Individual | 5 | 5 | Yes | 5 | YES | Moderate | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Continuous Epic Grooming | Sprint Planning | Jira Details - Epic breakdown, DoD, Exit criteria, CS Bugs | Blocking Scope change | Better & transparent commitments | Ad-hoc Tasks & improper prioritisation | More Than 5% but less than 10% |  | YES | n/a
2024-11-07 14:23 | Jegadeesh Santhana Krishnan | Dev | Pheonix | Yes | copilot , chat gpt | 10% to 20% | Yes | Yes | Balanced | 4 | 4 | 4 | 4 | Yes | 4 | 4 | Individual | 4 | 4 | Yes | 4 | YES | Moderate | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Some Information but still need further details | Yes | Average | Committed Epic Prioritisation | Sprint Planning | Intra Team Collaboration - Dependency linking on Jira by Individual owners | Change in Due date and QA Sign off Date restrictions | Better Estimations & Epic Breakdown | Improper Epic Breakdown & Estimations - Missing Sprint Backlog | More Than 5% but less than 10% |  | YES | N/A
2024-11-07 14:26 | Jegadeesh Santhana Krishnan | Dev | Eirene | No |  |  |  | No
2024-11-07 14:32 | Mujtaba Ahmad | Dev | Enigma | No |  |  |  | Yes | Well Managed | 5 | 5 | 5 | 5 | Yes | 5 | 5 | Individual | 5 | 5 | Yes | 5 | YES | Moderate | 10% to 20% | Yes | None | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Epic Breakdown | Sprint DSU's | CI/CD, Testing & Continuous planning | Strict Bug SLA's | Sprint Planning Structure | Delay in commitments from dependant team | More than 10% but Less than 20% |  | YES | no
2024-11-07 14:56 | Jegadeesh Santhana Krishnan | Dev | Aurora | Yes | Github copilot and chatgpt | 10% to 20% | Yes | No
2024-11-07 14:58 | Jegadeesh Santhana Krishnan | Dev | Sharks | Yes | Copilot, Copilot Chat | 10% to 20% | Yes | Yes | Balanced | 5 | 5 | 5 | 5 | Yes | 5 | 5 | Scrum Team | 5 | 5 | Yes | 5 | YES | Moderate | Less than 10% | Yes | Moderate | Over Utilised (90% and Above) | Optimal information available | Yes | Well Managed | Epic Breakdown | Sprint Planning | Jira Automation | Blocking Scope change | Efficient Jira Usage (New Fields such as - Due date, QA Lead, QA Involvement, QA Signoff date) | Delayed Response on open Queries, need multiple followups | More Than 5% but less than 10% |  | YES | Everything is good.
2024-11-07 15:22 | Sandeep Kumar | Dev | Tranformers | Yes | Copilot, chatgpt | 10% to 20% | No | Yes | Balanced | 4 | 5 | 2 | 3 | Yes | 4 | 3 | Individual | 5 | 4 | Yes | 4 | YES | Moderate | Less than 10% | Yes | Multiple | Over Utilised (90% and Above) | Some Information but still need further details | Not aware and did not find any significant change in the release coordination among teams | Average | Monitoring and Controlling Progress | Sprint Planning | Intra Team Collaboration - Dependency linking on Jira by Individual owners | Blocking Scope change | Efficient Jira Usage (New Fields such as - Due date, QA Lead, QA Involvement, QA Signoff date) | Ad-hoc Tasks & improper prioritisation | More Than 5% but less than 10% |  | Not Efficiently | Ad-hoc tasks often shift story due dates. Even when we allocate some ad-hoc bandwidth within a sprint, there’s no way to control when these tasks come in—whether on day 1, day 4, or any other time. This disrupts planned due dates and QA sign-offs. We also spend time daily in meetings and discussions, roughly equal to 1 story point per sprint, yet this bandwidth isn’t factored into our planning. These activities are essential for staying informed and supporting team members but are not accounted for as tasks. Regarding due dates, if a story is 1 point, starting on the 1st, its due date is also assumed to be the 1st, with no consideration of meeting time. This oversight leads to overwork. Although I try to manage it myself, I see teammates with even more meetings. Are these accounted for? Finally, for PR reviews, the responsibility currently falls solely on the code owner to chase reviews. If the reviewer delays, it feels like I’m pestering them by constantly following up. The review task should also be owned by the reviewer, who should provide their own due date. Cross-team reviewers, who don’t attend our sprint planning, also add uncertainty to our timelines, as we randomly allocate due dates, hoping for a timely review.
2024-11-07 16:06 | Mujtaba Ahmad | Dev | Titans | Yes | Copilot | 10% or below | Yes | Yes | Balanced | 4 | 5 | 4 | 5 | Yes | 4 | 4 | Scrum Team | 5 | 5 | Yes | 5 | YES | Moderate | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Some Information but still need further details | Yes | Average | Continuous Epic Grooming | Sprint Planning | KT and recording repository | Blocking Scope change | Efficient Jira Usage (New Fields such as - Due date, QA Lead, QA Involvement, QA Signoff date) | Improper Epic Breakdown & Estimations - Missing Sprint Backlog | Less than 5% |  | YES | Improvement in KT, tech design, and epic grooming.
2024-11-07 16:08 | Mujtaba Ahmad | Dev | Chakra | Yes | github copilot | 10% to 20% | Yes | Yes | Balanced | 3 | 2 | 1 | 3 | Yes | 4 | 4 | Scrum Team | 4 | 4 | Yes | 4 | YES | Moderate | Less than 10% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Not aware of any such initiative. Though the release coordination among teams was better than previous releases among teams | Well Managed | Monitoring and Controlling Progress | Sprint Closure/review | KT and recording repository | Blocking Scope change | Work allocation with sufficient capacity reserve | CS Bugs higher than the reserved Capacity | Less than 5% |  | YES | -
2024-11-07 16:32 | Jegadeesh Santhana Krishnan | Dev | Iris | Yes | Chatgpt and Copilot | 20% to 30% | Yes | Yes | Balanced | 4 | 5 | 5 | 5 | Yes | 5 | 4 | Individual | 5 | 3 | Yes | 4 | YES | Multiple | Less than 10% | Yes | Moderate | Balanced (80% - 90%) | Some Information but still need further details | Not aware of any such initiative. Though the release coordination among teams was better than previous releases among teams | Well Managed | Committed Epic Prioritisation | Sprint DSU's | Intra Team Collaboration - Dependency linking on Jira by Individual owners | Blocking Scope change | Better Estimations & Epic Breakdown | Intra team collaboration | Less than 5% |  | Not Efficiently | No
2024-11-07 16:38 | Mujtaba Ahmad | Dev | Indus | Yes | ChatGPT and copilot | 10% to 20% | Yes | Yes | Balanced | 4 | 4 | 4 | 4 | Yes | 4 | 4 | Scrum Team | 4 | 4 | Yes | 4 | YES | Moderate | 20% to 30% | Yes | Moderate | Balanced (80% - 90%) | Some Information but still need further details | Not aware of any such initiative. Though the release coordination among teams was better than previous releases among teams | Average | Code Freeze Milestones and hardening phase | Sprint Closure/review | CI/CD, Testing & Continuous planning | Change in Due date and QA Sign off Date restrictions | Better Estimations & Epic Breakdown | Ad-hoc Tasks & improper prioritisation | Less than 5% |  | YES | No
2024-11-07 17:34 | Jegadeesh Santhana Krishnan | Dev & Scrum Master | Pheonix | Yes | Github copilot | 10% or below | Yes | Yes | Balanced | 4 | 5 | 5 | 5 | Yes | 4 | 4 | Individual | 5 | 3 | Yes | 3 | YES | Moderate | Less than 10% | Yes | None | Balanced (80% - 90%) | Optimal information available | Yes | Average | Continuous Epic Grooming | Sprint Closure/review | Jira Automation | Blocking Scope change | Reduced over commit | Delay in commitments from dependant team | My role involves process improvement and enablement (EM's, SM's & Other folks responsible for process streamlining) |  | YES | NA
2024-11-07 18:30 | Sandeep Kumar | Dev & Scrum Master | Iota | Yes | ChatGPT, GitHub AI review | 10% to 20% | Yes | Yes | Balanced | 4 | 5 | 3 | 5 | Partially/Incomplete | 4 | 4 | Scrum Team | 4 | 4 | Yes | 4 | YES | Moderate | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Some Information but still need further details | Yes | Average | Monitoring and Controlling Progress | Sprint Planning | Ad-hoc requests prioritisation and acceptance | Strict Bug SLA's | Release Planning, Strategy & Schedule (Proper Checkpoint and dates on jira tickets) | Improper Epic Breakdown & Estimations - Missing Sprint Backlog | Less than 5% |  | YES | To have post release analysis and insights to iteratively improve the release process
2024-11-07 19:01 | Mohammed Fayaz | QA | Aurora | Yes | ChatGPT | 10% to 20% | Yes | Yes | Balanced |  |  |  |  | Yes |  |  | Individual |  |  | Yes | 4 | YES | Moderate | Less than 10% | Yes |  |  | Some Information but still need further details | Not aware of any such initiative. Though the release coordination among teams was better than previous releases among teams |  | Code Freeze Milestones and hardening phase | Sprint Planning | Non Release Activity Identification & capacity reserve | Change in Due date and QA Sign off Date restrictions | Better & transparent commitments | Ad-hoc Tasks & improper prioritisation | Less than 5% |  | YES | NO
2024-11-07 19:04 | Sandeep Kumar | Dev | Gryffindor | Yes | ChatGpt, CoPilot | 10% or below | Yes | Yes | Balanced | 4 | 5 | 5 | 5 | Yes | 4 | 4 | Scrum Team | 4 | 5 | Yes | 4 | YES | Moderate | 10% to 20% | No | Moderate | Over Utilised (90% and Above) | Optimal information available | Yes | Average | Committed Epic Prioritisation | Sprint Planning | Intra Team Collaboration - Dependency linking on Jira by Individual owners | Blocking Scope change | Better Estimations & Epic Breakdown | Ad-hoc Tasks & improper prioritisation | More than 10% but Less than 20% |  | YES | NA
2024-11-07 19:53 | Sandeep Kumar | Dev & Scrum Master | Tranformers | Yes | CoPilot, ChatGPT | 10% to 20% | Yes | Yes | Balanced | 5 | 5 | 4 | 4 | Yes | 4 | 4 | Scrum Team | 4 | 4 | Yes | 4 | YES | Multiple | 10% to 20% | No | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Continuous Epic Grooming | Sprint Closure/review | CI/CD, Testing & Continuous planning | Blocking Scope change | Work allocation with sufficient capacity reserve | Reviews | My role involves process improvement and enablement (EM's, SM's & Other folks responsible for process streamlining) |  | YES | NA
2024-11-07 20:14 | Sandeep Kumar | EM | Transformers, Dynamos | Yes | ChatGPT | 20% to 30% | Yes | No
2024-11-07 20:24 | Mohammed Fayaz | QA & Scrum Master | Dynamos | Yes | Chatgpt | 10% or below | Yes | Yes | Well Managed | 5 | 5 | 5 | 5 | Yes | 5 | 5 | Scrum Team | 5 | 5 | Yes | 5 | YES | Moderate | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Continuous Epic Grooming | Sprint Planning | Jira Details - Epic breakdown, DoD, Exit criteria, CS Bugs | Blocking Scope change | Release Planning, Strategy & Schedule (Proper Checkpoint and dates on jira tickets) | Improper Epic Breakdown & Estimations - Missing Sprint Backlog | More Than 5% but less than 10% |  | YES | encourage teams to update the jiras proactively to get proper efforts reflected in Jira
2024-11-07 21:24 | Mujtaba Ahmad | Dev | Enigma | No |  |  |  | Yes | Balanced | 4 | 5 | 5 | 5 | Partially/Incomplete | 4 | 5 | Individual | 5 | 4 | Yes | 5 | YES | Moderate | 10% to 20% | Yes | None | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Continuous Epic Grooming | Sprint Closure/review | Ad-hoc requests prioritisation and acceptance | Risk call out during Weekly SoS | Better Estimations & Epic Breakdown | Partial or missing details on Jira Trackers Description | More Than 5% but less than 10% |  | YES | No
2024-11-07 22:56 | Jegadeesh Santhana Krishnan | Dev | Iris | Yes | Github Co-pilot | 30% and Above | Yes | Yes | Well Managed | 5 | 5 | 5 | 4 | Yes | 5 | 4 | Individual | 5 | 5 | Yes | 4 | YES | Moderate | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Monitoring and Controlling Progress | Sprint Closure/review | Intra Team Collaboration - Dependency linking on Jira by Individual owners | Risk call out during Weekly SoS | Better & transparent commitments | Delay in commitments from dependant team | Less than 5% |  | YES | -
2024-11-08 00:18 | Mujtaba Ahmad | Dev | Falcon | Yes | Github copilot, chat-gpt | 20% to 30% | Yes | Yes | Well Managed | 5 | 5 | 5 | 5 | Yes | 5 | 5 | Scrum Team | 5 | 3 | Yes | 4 | YES | Moderate | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Monitoring and Controlling Progress | Sprint Closure/review | CI/CD, Testing & Continuous planning | Change in Due date and QA Sign off Date restrictions | Release Planning, Strategy & Schedule (Proper Checkpoint and dates on jira tickets) | Ad-hoc Tasks & improper prioritisation | More Than 5% but less than 10% |  | YES | NA
2024-11-08 01:28 | Mohammed Fayaz | QA & Scrum Master | Ganges | Yes | ChatGpt | 10% to 20% | Yes | Yes | Well Managed | 5 | 5 | 5 | 5 | Yes | 5 | 5 | Scrum Team | 5 | 5 | Yes | 5 | YES | Moderate | 10% to 20% | Yes | None | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Continuous Epic Grooming | Sprint Planning | Backlog & CS bugs prioritisation | Risk call out during Weekly SoS | Better & transparent commitments | Reviews | My role involves process improvement and enablement (EM's, SM's & Other folks responsible for process streamlining) |  | YES | Nothing from my side, currently we are strict with our dates as well so everything is good
2024-11-08 03:27 | Mohammed Fayaz | QA | Pheonix | Yes | chatgpt | Just started using AI, need time to quantify | Yes | Yes | Well Managed | 5 | 5 | 5 | 5 | Yes | 5 | 5 | Scrum Team | 5 | 5 | Yes | 5 | YES | Moderate | 10% to 20% | Yes | None | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Epic Breakdown | Sprint Closure/review | Backlog & CS bugs prioritisation | Risk call out during Weekly SoS | Sprint Planning Structure | Reviews | More Than 5% but less than 10% |  | YES | NA
2024-11-08 08:41 | Jegadeesh Santhana Krishnan | Dev | Helios | Yes | Copilot | 10% to 20% | Yes | No
2024-11-08 08:46 | Jegadeesh Santhana Krishnan | EM | Chloris | Yes | ChatGPT | 20% to 30% | Yes | Yes | Well Managed | 5 | 5 | 5 | 5 | Yes | 5 | 5 | Individual | 4 | 4 | Yes | 4 | YES | Multiple | 10% to 20% | Yes | None | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Continuous Epic Grooming | Sprint Planning | Bugs Management & Deferring | Change in Due date and QA Sign off Date restrictions | Better Estimations & Epic Breakdown | Delay in commitments from dependant team | My role involves process improvement and enablement (EM's, SM's & Other folks responsible for process streamlining) |  | YES | Nothing speicifically
2024-11-08 08:55 | Sandeep Kumar | Dev | Tranformers | Yes | copilot . chatgpt | 10% or below | Yes | Yes | Balanced | 4 | 4 | 4 | 4 | Yes | 4 | 4 | Scrum Team | 4 | 4 | Yes | 4 | YES | Moderate | Less than 10% | Yes | Moderate | Over Utilised (90% and Above) | Optimal information available | Yes | Well Managed | Committed Epic Prioritisation | Sprint Planning | Jira Details - Epic breakdown, DoD, Exit criteria, CS Bugs | Blocking Scope change | Release Planning, Strategy & Schedule (Proper Checkpoint and dates on jira tickets) | Ad-hoc Tasks & improper prioritisation | More Than 5% but less than 10% |  | YES | No
2024-11-08 08:59 | Jegadeesh Santhana Krishnan | Dev | Hercules | Yes | Github co-pilot | 10% to 20% | Yes | No
2024-11-08 09:04 | Jegadeesh Santhana Krishnan | Dev | Skywalker | Yes | chatGPT | 10% to 20% | Yes | Yes | Balanced | 5 | 5 | 5 | 4 | Yes | 5 | 4 | Scrum Team | 5 | 3 | No |  | YES | Moderate | Less than 10% | Yes | None | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Continuous Epic Grooming | Sprint Closure/review | KT and recording repository | Change in Due date and QA Sign off Date restrictions | None | Delayed Response on open Queries, need multiple followups | Less than 5% |  | YES | No
2024-11-08 09:09 | Jegadeesh Santhana Krishnan | Dev | Tintin | Yes | Copilot | 10% to 20% | Yes | Yes | Balanced | 4 | 4 | 4 | 4 | Yes | 4 | 4 | Scrum Team | 4 | 4 | Yes | 4 | Moderately | Moderate | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Some Information but still need further details | No | Average | Continuous Epic Grooming | Sprint DSU's | Jira Details - Epic breakdown, DoD, Exit criteria, CS Bugs | Blocking Scope change | Work allocation with sufficient capacity reserve | Non Release Activities | More than 20% |  | YES | NA
2024-11-08 09:40 | Mujtaba Ahmad | Dev | Stark | Yes | copilot | 10% to 20% | Yes | Yes | Well Managed | 5 | 5 | 5 | 5 | Yes | 5 | 5 | Scrum Team | 5 | 5 | Yes | 5 | YES | Multiple | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Committed Epic Prioritisation | Sprint Closure/review | Backlog & CS bugs prioritisation | Blocking Scope change | Better Estimations & Epic Breakdown | CS Bugs higher than the reserved Capacity | More Than 5% but less than 10% |  | YES | NA
2024-11-08 09:51 | Krishna Kishore Mothukuri | Dev & Scrum Master | Velocity | Yes | chatgpt & copilot | 30% and Above | Yes | Yes | Well Managed | 5 | 5 | 5 | 5 | Yes | 5 | 4 | Individual | 5 | 5 | Yes | 5 | YES | Multiple | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Continuous Epic Grooming | Sprint DSU's | CI/CD, Testing & Continuous planning | Risk call out during Weekly SoS | Efficient Jira Usage (New Fields such as - Due date, QA Lead, QA Involvement, QA Signoff date) | Delay in commitments from dependant team | My role involves process improvement and enablement (EM's, SM's & Other folks responsible for process streamlining) | N/A | YES | Ci/CD pipeline has to be improved
2024-11-08 09:53 | Jegadeesh Santhana Krishnan | Dev & Scrum Master | Skywalker | Yes | github copilot | 10% to 20% | Yes | Yes | Balanced | 4 | 4 | 4 | 4 | Yes | 4 | 4 | Individual | 5 | 4 | Yes | 5 | YES | Multiple | 20% to 30% | Yes |  | Balanced (80% - 90%) | Optimal information available | Not aware of any such initiative. Though the release coordination among teams was better than previous releases among teams | Well Managed | Continuous Epic Grooming | Sprint Planning | KT and recording repository | Blocking Scope change | Better Estimations & Epic Breakdown | Reviews | More than 10% but Less than 20% | No | YES | No
2024-11-08 10:00 | Krishna Kishore Mothukuri | Dev | Velocity | Yes | Chatgpt and copilot | 10% to 20% | No | Yes | Balanced | 5 | 5 | 5 | 5 | Yes | 5 | 5 | Scrum Team | 4 | 4 | Yes | 5 | YES | Moderate | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Some Information but still need further details | Not aware of any such initiative. Though the release coordination among teams was better than previous releases among teams | Average | Epic Breakdown | Sprint Planning | KT and recording repository | Change in Due date and QA Sign off Date restrictions | Effective communication | Ad-hoc Tasks & improper prioritisation | More than 10% but Less than 20% |  | YES | NO
2024-11-08 10:04 | Mujtaba Ahmad | Dev | Apollo | Yes | Copilot | 10% or below | Yes | Yes | Balanced | 5 |  | 4 | 4 | Yes | 4 | 4 | Scrum Team | 5 | 4 | Yes | 4 | YES | Moderate | Less than 10% | No | Moderate | Over Utilised (90% and Above) | Optimal information available | Yes | Well Managed | Code Freeze Milestones and hardening phase | Sprint Planning | Ad-hoc requests prioritisation and acceptance | Blocking Scope change | Dependency management | Ad-hoc Tasks & improper prioritisation | More Than 5% but less than 10% |  | YES | We can more buffer for senior engineer as they are getting involved in multiple discussions ( adhoc as well )
2024-11-08 10:04 | Mohammed Fayaz | QA | Ganges | Yes | Chat GPT | 10% to 20% | Yes | Yes | Balanced | 4 | 4 | 4 | 4 | Partially/Incomplete | 4 | 4 | Scrum Team | 4 | 4 | Yes | 3 | Moderately | Multiple | 10% to 20% | Yes | Moderate | Under Utilisation (80% Below) | Some Information but still need further details | Yes | Average | Continuous Epic Grooming | Sprint Planning | Jira Details - Epic breakdown, DoD, Exit criteria, CS Bugs | Blocking Scope change | Efficient Jira Usage (New Fields such as - Due date, QA Lead, QA Involvement, QA Signoff date) | Ad-hoc Tasks & improper prioritisation | More than 10% but Less than 20% | NO | YES | NO
2024-11-08 10:29 | Sandeep Kumar | EM | Zeta | Yes | Chatgpt | 10% to 20% | Yes | No
2024-11-08 10:38 | Mohammed Fayaz | QA | Helios | Yes | ChatGPT | 10% to 20% | Yes | Yes | Balanced | 4 | 3 | 4 | 4 | Yes | 3 | 3 | Individual | 4 | 4 | Yes | 4 | Moderately | Moderate | 20% to 30% | Yes | Moderate | Balanced (80% - 90%) | Some Information but still need further details | Yes | Average | Monitoring and Controlling Progress | Sprint Planning | Jira Details - Epic breakdown, DoD, Exit criteria, CS Bugs | Blocking Scope change | Work allocation with sufficient capacity reserve | Delay in commitments from dependant team | Less than 5% |  | YES | NO
2024-11-08 10:44 | Others | Dev | Epsilon(CEE) | Yes | ai-product-kb | 20% to 30% | Yes | No
2024-11-08 10:59 | Jegadeesh Santhana Krishnan | Dev & Scrum Master | Echo | Yes | Copilot, Chatgpt, Claude | 10% to 20% | Yes | Yes | Balanced | 4 | 4 | 4 | 4 | Yes | 4 | 4 | Individual | 4 | 4 | Yes | 4 | YES | Moderate | More than 30% | No | Multiple | Balanced (80% - 90%) | Optimal information available | Not aware of any such initiative. Though the release coordination among teams was better than previous releases among teams | Well Managed | Monitoring and Controlling Progress | Sprint Planning | Ad-hoc requests prioritisation and acceptance | Risk call out during Weekly SoS | Effective communication | CS Bugs higher than the reserved Capacity | More than 10% but Less than 20% |  | YES | NA
2024-11-08 11:01 | Sandeep Kumar | Dev | Individual Capacity, Not Associated with any particular team | Yes | ChatGPT | 10% to 20% | Yes | No
2024-11-08 11:13 | Jegadeesh Santhana Krishnan | Dev | Hercules | Yes | Github Copilot | 10% to 20% | Yes | No
2024-11-08 11:14 | Jegadeesh Santhana Krishnan | Dev | Eirene | Yes | github copilot | 10% to 20% | Yes | No
2024-11-08 11:15 | Jegadeesh Santhana Krishnan | Dev | Chloris | Yes | Copilot | 10% or below | Yes | Yes | Balanced | 4 | 4 | 4 | 4 | Yes | 5 | 5 | Individual | 5 | 5 | Yes | 5 | Moderately | Moderate | Less than 10% | Yes | Moderate | Balanced (80% - 90%) | Some Information but still need further details | Yes | Average | Continuous Epic Grooming | Sprint Closure/review | Test Design | Blocking Scope change | Reduced over commit | Ad-hoc Tasks & improper prioritisation | Less than 5% |  | YES | To block FRD changes after its approval or after the development has started.
2024-11-08 11:28 | Jegadeesh Santhana Krishnan | EM | Iris | Yes | Chatgpt, copilot | 20% to 30% | Yes | Yes | Well Managed | 5 | 5 | 5 | 5 | Yes | 5 | 5 | Individual | 5 | 5 | Yes | 5 | YES | Multiple | Less than 10% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Committed Epic Prioritisation | Sprint Retrospective | Intra Team Collaboration - Dependency linking on Jira by Individual owners | Risk call out during Weekly SoS | Effective communication | Ad-hoc Tasks & improper prioritisation | My role involves process improvement and enablement (EM's, SM's & Other folks responsible for process streamlining) | - | YES | No
2024-11-08 11:40 | Jegadeesh Santhana Krishnan | Dev | Skywalker | Yes | ChatGPT, Github copilot | 30% and Above | Yes | No
2024-11-08 11:50 | Sandeep Kumar | Dev | Dynamos | Yes | co pilot | 20% to 30% | No | Yes | Balanced | 3 | 3 | 3 | 2 | Yes | 3 | 3 | Scrum Team | 3 | 3 | Yes | 3 | Moderately | Moderate | 20% to 30% | Yes | Moderate | Balanced (80% - 90%) | Some Information but still need further details | Yes | Average | Epic Breakdown | Sprint Planning | Tech Design | Change in Due date and QA Sign off Date restrictions | Better & transparent commitments | Improper Epic Breakdown & Estimations - Missing Sprint Backlog | More Than 5% but less than 10% |  | YES | na
2024-11-08 12:12 | Jegadeesh Santhana Krishnan | Dev & Scrum Master | Helios | Yes | copilot and chat gpt | 20% to 30% | Yes | Yes | Balanced | 4 | 4 | 4 | 4 | Yes | 4 | 4 | Individual | 5 | 4 | Yes | 4 | YES | Multiple | 20% to 30% | Yes | Moderate | Balanced (80% - 90%) | Some Information but still need further details | Yes | Well Managed | Monitoring and Controlling Progress | Sprint Planning | Intra Team Collaboration - Dependency linking on Jira by Individual owners | Blocking Scope change | Better Estimations & Epic Breakdown | Delayed Response on open Queries, need multiple followups | More than 10% but Less than 20% |  | YES | NA
2024-11-08 12:18 | Jegadeesh Santhana Krishnan | Dev | Helios | Yes | Openai | 10% to 20% | Yes | Yes | Balanced | 4 | 4 | 5 | 5 | Yes | 5 | 4 | Individual | 5 | 5 | Yes | 5 | YES | Moderate | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes |  | Release Kick Off | Sprint Closure/review | Jira Automation | Blocking Scope change | None | Delayed Response on open Queries, need multiple followups | Less than 5% |  | YES | N/A
2024-11-08 12:25 | Krishna Kishore Mothukuri | Dev | Ganges | No |  |  |  | Yes | Well Managed | 4 | 4 | 4 | 4 | Partially/Incomplete | 5 | 4 | Scrum Team | 5 | 4 | Yes | 4 | YES | Multiple | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Not aware and did not find any significant change in the release coordination among teams | Average | Code Freeze Milestones and hardening phase | Sprint Planning | Intra Team Collaboration - Dependency linking on Jira by Individual owners | Risk call out during Weekly SoS | Work allocation with sufficient capacity reserve | Ad-hoc Tasks & improper prioritisation | More Than 5% but less than 10% | NA | YES | NA
2024-11-08 12:29 | Sandeep Kumar | Dev | Dynamos | No |  |  |  | Yes | Well Managed | 4 | 4 | 4 | 4 | Yes | 5 | 5 | Scrum Team | 5 | 5 | Yes | 5 | YES | Moderate | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Continuous Epic Grooming | Sprint Retrospective | Jira Details - Epic breakdown, DoD, Exit criteria, CS Bugs | Change in Due date and QA Sign off Date restrictions | Better Estimations & Epic Breakdown | Ad-hoc Tasks & improper prioritisation | More Than 5% but less than 10% |  | YES | No Suggestion
2024-11-08 12:34 | Jegadeesh Santhana Krishnan | Dev | Iris | Yes | copilot | 10% or below | Yes | Yes | Balanced | 4 | 4 | 3 | 4 | Yes | 4 | 4 | Individual | 4 | 4 | Yes | 5 | Moderately | Multiple | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Average | Epic Breakdown | Sprint Planning | Ad-hoc requests prioritisation and acceptance | Risk call out during Weekly SoS | Better Estimations & Epic Breakdown | Delayed Response on open Queries, need multiple followups | Less than 5% |  | YES | None
2024-11-08 12:51 | Mohammed Fayaz | QA | Iris | Yes | Chatgpt | 10% to 20% | Yes | Yes | Chaotic | 3 | 4 | 4 | 4 | Partially/Incomplete | 4 | 4 | Individual | 4 | 3 | Yes | 4 | YES | Moderate | Less than 10% | Yes | Moderate | Over Utilised (90% and Above) | Some Information but still need further details | Yes | Average | Code Freeze Milestones and hardening phase | Sprint Planning | Intra Team Collaboration - Dependency linking on Jira by Individual owners | Change in Due date and QA Sign off Date restrictions | Risk call out (Release Confluence Page) | Delayed Response on open Queries, need multiple followups | More Than 5% but less than 10% | Dependency should be checked once we have tech design ready | YES | Have a handover call between BE and UI Dev so that they have better understanding on dependency
2024-11-08 13:25 | Mohammed Fayaz | EM | QAM | Yes | ChatGPT | 20% to 30% | Yes | Yes | Well Managed | 4 | 5 | 5 | 5 | Yes | 5 | 4 | Scrum Team | 4 | 4 | Yes | 5 | YES | Moderate | 10% to 20% | Yes | Moderate | Over Utilised (90% and Above) | Some Information but still need further details | Yes | Well Managed | Epic Breakdown | Sprint Closure/review | Intra Team Collaboration - Dependency linking on Jira by Individual owners | Risk call out during Weekly SoS | Effective communication | Improper Epic Breakdown & Estimations - Missing Sprint Backlog | My role involves process improvement and enablement (EM's, SM's & Other folks responsible for process streamlining) |  | YES | Ownership & Accountability
2024-11-08 15:25 | Jegadeesh Santhana Krishnan | Dev & Scrum Master | Iris | Yes | Co-pilot, chatgpt | 20% to 30% | Yes | Yes | Well Managed | 5 | 5 | 5 | 5 | Yes | 5 | 5 | Individual | 5 | 5 | Yes | 5 | YES | Multiple | 10% to 20% | Yes | Moderate | Over Utilised (90% and Above) | Some Information but still need further details | Yes | Well Managed | Monitoring and Controlling Progress | Sprint Closure/review | Intra Team Collaboration - Dependency linking on Jira by Individual owners | Change in Due date and QA Sign off Date restrictions | Work allocation with sufficient capacity reserve | Intra team collaboration | More Than 5% but less than 10% |  | YES
2024-11-08 15:43 | Krishna Kishore Mothukuri | Dev | Pathfinders | Yes | Co- Pilot, ChatGPT | 30% and Above | Yes | No
2024-11-08 16:35 | Sandeep Kumar | Dev & Scrum Master | Zeta | Yes | Github copilot and chat GPT (mainly) | 10% to 20% | Yes | Yes | Balanced | 4 | 4 | 5 | 5 | Yes | 5 | 5 | Scrum Team | 4 | 4 | No |  | YES | Multiple | Less than 10% | Yes | Moderate | Balanced (80% - 90%) | Some Information but still need further details | Yes | Well Managed | Epic Breakdown | Sprint Closure/review | Ad-hoc requests prioritisation and acceptance | Change in Due date and QA Sign off Date restrictions | Better Estimations & Epic Breakdown | Reviews | More than 10% but Less than 20% | NA | YES | NA
2024-11-08 16:43 | Mujtaba Ahmad | Dev | Chakra | Yes | chat gpt | 10% or below | Yes | Yes | Balanced | 4 | 4 | 4 | 4 | Yes | 4 | 5 | Scrum Team | 5 | 4 | Yes | 4 | YES | Moderate | Less than 10% | Yes | Moderate | Over Utilised (90% and Above) | Some Information but still need further details | Yes | Well Managed | Continuous Epic Grooming | Sprint Planning | Tech Design | Blocking Scope change | Release Planning, Strategy & Schedule (Proper Checkpoint and dates on jira tickets) | Partial or missing details on Jira Trackers Description | More Than 5% but less than 10% |  | YES | -
2024-11-08 17:11 | Mohammed Fayaz | QA | Stark | Yes | chat GPT | 10% to 20% | Yes | Yes | Balanced | 4 | 4 | 4 |  | Yes | 4 | 4 | Individual | 5 | 5 | Yes | 5 | YES | Multiple | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Some Information but still need further details | Yes | Well Managed | Committed Epic Prioritisation | Sprint Planning | Tech Design | Risk call out during Weekly SoS | Better Estimations & Epic Breakdown | Non Release Activities | More Than 5% but less than 10% | na | YES | na
2024-11-08 18:31 | Sandeep Kumar | Dev | Iota | Yes | GitHub Copilot | 10% to 20% | Yes | Yes | Balanced | 4 | 4 | 3 | 3 | Yes | 4 | 4 | Scrum Team | 4 | 4 | Yes | 5 | YES | Moderate | 10% to 20% | No | Moderate | Balanced (80% - 90%) | Some Information but still need further details | No | Well Managed | Continuous Epic Grooming | Sprint Closure/review | Intra Team Collaboration - Dependency linking on Jira by Individual owners | Blocking Scope change | Reduced over commit | Modifications on Approved Tech designs | More than 10% but Less than 20% |  | YES | -
2024-11-08 19:49 | Jegadeesh Santhana Krishnan | EM | Avengers | Yes | Chat gpt, copilot | 10% or below | Yes | Yes | Well Managed | 4 | 5 | 5 | 5 | Partially/Incomplete | 5 | 5 | Scrum Team | 5 | 5 | Yes | 5 | YES | Moderate | 20% to 30% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Continuous Epic Grooming | Sprint Planning | Jira Details - Epic breakdown, DoD, Exit criteria, CS Bugs | Blocking Scope change | None | Delayed Test Designs | My role involves process improvement and enablement (EM's, SM's & Other folks responsible for process streamlining) |  | YES | NA
2024-11-09 09:38 | Jegadeesh Santhana Krishnan | Dev | Chloris | Yes | Co-pilot and gpt | 10% to 20% | Yes | Yes | Balanced | 4 | 4 | 4 | 4 | Yes | 4 | 4 | Individual | 4 | 4 | Yes | 4 | YES | Moderate | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Committed Epic Prioritisation | Sprint Retrospective | KT and recording repository | Blocking Scope change | Effective communication | Ad-hoc Tasks & improper prioritisation | Less than 5% |  | YES | -