## Form Responses 1
Timestamp | You are part of which of the following directors org | What's your primary role? | Enter the Team/Scrum team that you are mostly associated with during the release. (Select Only One) | Are you using AI for efficiency improvement in your day to day Dev/QA activity? | With the usage of AI what has been increase in your productivity? | Are you getting the required support and guidance within Engineering to explore and increase efficiency using AI? | Are you directly involved in the Release Deliverables for current release items or items planned and in progress for future releases? | How would you rate Release Overall (Individual Perspective) ? | How would you rate the release planning in comparison to previous release plannings? (1-Poor, 5- Improved) | How well were you as an individual aware of your teams commitments and scope of work prior to release implementation start ? (1-Not Aware, 5- Aware) | What was your involvement in Release planning and the selection of commitments? (1-Not Involved, 5- Fully Involved) | Were you as an individual aware of the Release timelines and your tasks in hand for the Release ? (1-Somewhat Aware, 5- Fully Aware) | Detailed Epic Breakdown with estimates and scrum team ownership were done for your trackers parent epic prior to Release Implementation Initiation. | How confident were you in terms of your teams commitments and deliverables? (1-Not Confident, 5- Full Confidence) | How would you rate effectiveness the Sprint Planning Meetings ? (1-Not Effective, 5- Effective) | Individual items efforts estimate for completion of the task is done by whom ? | How would you rate effectiveness of the Daily Standup connect to understand and analyse your tasks in hand ? (1-Not Effective, 5- Effective) | How would you rate effectiveness of the Sprint Closure / review meetings ? (1-Not Effective, 5- Effective) | Was Sprint retrospective Conducted for your Team at the end of each Sprint | Sprint Retrospective Effectiveness | Do you as an individual get sufficient opportunity to raise risk or concerns during agile ceremonies? | Do you get opportunity to learn new things in accordance to your role release over release? | What percentage of your capacity in the sprint was reserved for Items such as CS Support Bugs/Requests which cannot be estimated but as a team you reserve some bandwidth, as per history your are aware of such requests and your team reserves capacity for it ? | Is your reserved capacity for the Historical support activities such as CS Bugs/Support tickets and others, sufficient during the release. | How much Adhoc requests (Request for which no bandwidth was reserved during Release/Sprint Planning) were received during implementation Phase. | How was your available capacity utilised during the Release i.e. your workload. (1-Under Utilisation, 5- Over Utilisation) | Do you have sufficient details available on Jira to successfully and independently complete your assigned tasks | Was the Release Coordination Group initiated with representatives from each directors org, helpful and more efficient in managing the Release checkpoints and ensuring the key asks were routed better to the respective team/people? | How well were dependencies managed in the Release. | Check the Release Ceremony where there is need to spend more efforts to make the release more effective. | Check the Sprint Ceremony where there is need to spend more efforts to make the release more effective. | What is the top improvement area in the below list you would suggest to improve for a smoother release? | What do we need to improve in Release Implementation | Anything that you would like to call out which improved in this release as compared to the previous releases. | What is the most probable reason that deviates the planned timelines? | Applicable only for pure DEV or QA Resources - What percent of your available capacity is impacted by process changes and new processes enablement on regular tasks not the other cleanup activities from previous releases (Not Applicable to EM's, SM's & Other Folks responsible for process streamlining) | Any other thought you would like to share related to the releases. | In Your individual opinion are we considering the release Delivery Timelines and milestones while we are planning and delivering our assigned tasks | Do you have any suggestion for improving and streamlining the release further?
2024-09-20 11:48 | Mujtaba Ahmad | Dev | Apollo | Yes | 10% to 20% | Yes | Yes | Balanced | 3 | 4 | 4 | 4 | Yes | 4 | 4 | Scrum Team | 4 | 3 | No |  | YES | Moderate | Less than 10% | Yes | Moderate | Over Utilised (90% and Above) | Some Information but still need further details | Yes | Average | Continuous Epic Grooming | Sprint Planning | Jira Details - Epic breakdown, DoD, Exit criteria, CS Bugs | Change in Due date and QA Sign off Date restrictions | Efficient Jira Usage (New Fields such as - Due date, QA Lead, QA Involvement, QA Signoff date) | Ad-hoc Tasks & improper prioritisation | More than 10% but Less than 20% |  | Not Efficiently | better prioritisation
2024-09-20 11:48 | Jegadeesh Santhana Krishnan | Dev | Echo | Yes | 20% to 30% | Yes | Yes | Chaotic |  |  |  |  | Yes |  |  | SME/Epic Owner/EM/QM (Pre Defined Efforts Estimates) |  |  | Yes | 5 | YES | Multiple | Less than 10% | No | None | Over Utilised (90% and Above) | Optimal information available | Not aware and did not find any significant change in the release coordination among teams | Well Managed | Committed Epic Prioritisation | Sprint Planning | Bugs Management & Deferring | Change in Due date and QA Sign off Date restrictions | Better Estimations & Epic Breakdown | CS Bugs higher than the reserved Capacity | Less than 5% |  | YES | NA
2024-09-20 12:07 | Jegadeesh Santhana Krishnan | Dev | Dexter | Yes | 20% to 30% | Yes | Yes | Well Managed | 5 | 5 | 5 | 5 | Yes | 5 |  | Individual | 5 | 5 | Yes | 4 | YES | Multiple | 10% to 20% | Yes | Moderate | Over Utilised (90% and Above) | Optimal information available | Yes | Well Managed | Monitoring and Controlling Progress | Sprint Closure/review | Non Release Activity Identification & capacity reserve | Blocking Scope change | Work allocation with sufficient capacity reserve | CS Bugs higher than the reserved Capacity | Less than 5% |  | YES | I believe we should consider testing some other AI tools apart from ChatGpt as its performance is low in several benchmarks and devs should discuss how their experience has been. I personally found Claude to be much better in code completion and suggesting strategies.
2024-09-20 12:08 | Sandeep Kumar | Dev | Sudo | Yes | 10% to 20% | Yes | Yes | Balanced | 3 | 3 | 3 | 3 | Yes | 4 | 3 | Scrum Team | 3 | 2 | Yes | 3 | YES | Multiple | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Committed Epic Prioritisation | Sprint DSU's | Test Design | Blocking Scope change | Better & transparent commitments | Ad-hoc Tasks & improper prioritisation | More than 10% but Less than 20% |  | YES | NA
2024-09-20 12:12 | Mohammed Fayaz | QA | Gryffindor | Yes | Just started using AI, need time to quantify | Yes | Yes | Well Managed | 5 | 5 | 5 | 5 | Yes | 5 | 4 | Individual | 5 | 5 | Yes | 5 | YES | None | Less than 10% | Yes | None | Over Utilised (90% and Above) | Optimal information available | Yes | Well Managed | Committed Epic Prioritisation | Sprint Planning | Jira Details - Epic breakdown, DoD, Exit criteria, CS Bugs | Change in Due date and QA Sign off Date restrictions | Work allocation with sufficient capacity reserve | Reviews | More Than 5% but less than 10% |  | YES | NA
2024-09-20 13:29 | Sandeep Kumar | Dev | Sudo | Yes | 10% to 20% | Yes | Yes | Balanced | 3 | 3 | 4 | 4 | Yes | 4 | 3 | SME/Epic Owner/EM/QM (Pre Defined Efforts Estimates) | 4 | 3 | No |  | YES | Moderate | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Some Information but still need further details | Yes | Well Managed | Committed Epic Prioritisation | Sprint Planning | Bugs Management & Deferring | Blocking Scope change | Release Planning, Strategy & Schedule (Proper Checkpoint and dates on jira tickets) | Intra team collaboration | More Than 5% but less than 10% |  | YES
2024-09-20 14:03 | Mujtaba Ahmad | Dev | Stark | Yes | 10% to 20% | Yes | Yes | Well Managed | 5 | 5 | 5 | 5 | Yes | 5 | 5 | Scrum Team | 5 | 5 | Yes | 5 | YES | Moderate | 10% to 20% | Yes | Moderate | Over Utilised (90% and Above) | Optimal information available | Yes | Average | Continuous Epic Grooming | Sprint Planning | CI/CD, Testing & Continuous planning | Blocking Scope change | Better & transparent commitments | Ad-hoc Tasks & improper prioritisation | More Than 5% but less than 10% | N/A | YES | N/A
2024-09-20 15:49 | Mohammed Fayaz | QA | E2E | Yes | 10% to 20% | Yes | No
2024-09-20 16:00 | Jegadeesh Santhana Krishnan | Dev | Pheonix | Yes | 10% to 20% | Yes | Yes | Balanced | 4 | 5 | 2 | 5 | Yes | 5 | 5 | Individual | 5 | 5 | Yes | 5 | YES | Moderate | Less than 10% | Yes | None | Balanced (80% - 90%) | Optimal information available | Yes | Average | Epic Breakdown | Sprint Closure/review | Intra Team Collaboration - Dependency linking on Jira by Individual owners | Change in Due date and QA Sign off Date restrictions | None | Delay in commitments from dependant team | Less than 5% |  | YES | NA
2024-09-20 16:03 | Sandeep Kumar | Dev | Zeta | Yes | 20% to 30% | Yes | Yes | Balanced | 4 | 4 | 5 | 5 | Yes | 5 | 5 | Individual | 5 | 5 | Yes | 5 | YES | Moderate | 20% to 30% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Continuous Epic Grooming | Sprint DSU's | KT and recording repository | Change in Due date and QA Sign off Date restrictions | Work allocation with sufficient capacity reserve | Ad-hoc Tasks & improper prioritisation | More than 20% |  | YES | none
2024-09-20 16:08 | Mohammed Fayaz | QA | Sudo | Yes | Just started using AI, need time to quantify | Yes | Yes | Balanced | 5 | 5 | 5 | 5 | Yes | 5 | 5 | Individual | 5 | 4 | Yes | 5 | YES | Moderate | 10% to 20% | Yes | Moderate | Over Utilised (90% and Above) | Optimal information available | Yes | Well Managed | Committed Epic Prioritisation | Sprint Planning | Intra Team Collaboration - Dependency linking on Jira by Individual owners | Risk call out during Weekly SoS | Release Planning, Strategy & Schedule (Proper Checkpoint and dates on jira tickets) | Ad-hoc Tasks & improper prioritisation | Less than 5% |  | YES | NO
2024-09-20 16:16 | Jegadeesh Santhana Krishnan | Dev | Hercules | Yes | 10% to 20% | Yes | Yes | Well Managed | 5 | 5 | 5 | 4 | Yes | 5 | 4 | Scrum Team | 5 | 4 | Yes | 4 | YES | Moderate | 10% to 20% | Yes | Moderate | Over Utilised (90% and Above) | Optimal information available | Yes | Well Managed | Epic Breakdown | Sprint Closure/review | Backlog & CS bugs prioritisation | Blocking Scope change | Sprint Planning Structure | Modifications on Approved Tech designs | Less than 5% |  | YES | no
2024-09-20 16:19 | Mohammed Fayaz | QA | Ganges | Yes | 10% to 20% | Yes | Yes | Balanced | 5 | 5 | 5 | 5 | Yes | 5 | 5 | Scrum Team | 5 | 5 | Yes | 5 | YES | Multiple | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Code Freeze Milestones and hardening phase | Sprint Planning | Non Release Activity Identification & capacity reserve | Risk call out during Weekly SoS | Reduced over commit | Ad-hoc Tasks & improper prioritisation | More Than 5% but less than 10% |  | YES | Nothing
2024-09-20 16:19 | Sandeep Kumar | EM | Iota | No |  |  | No
2024-09-20 16:23 | Sandeep Kumar | Dev & Scrum Master | Sudo | Yes | 30% and Above | Yes | Yes | Balanced | 4 | 4 | 4 | 4 | Yes | 4 | 4 | Scrum Team | 4 | 3 | Yes | 5 | YES | Moderate | 10% to 20% | No | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Epic Breakdown | Sprint Retrospective | Intra Team Collaboration - Dependency linking on Jira by Individual owners | Change in Due date and QA Sign off Date restrictions | Reduced over commit | Delay in commitments from dependant team | More than 10% but Less than 20% |  | YES | NA
2024-09-20 16:28 | Jegadeesh Santhana Krishnan | Dev | Hercules | Yes | 10% to 20% | Yes | Yes | Balanced | 4 | 3 | 4 | 4 | Yes | 4 | 4 | Individual | 4 | 4 | Yes | 4 | Moderately | Moderate | 20% to 30% | Yes | Moderate | Balanced (80% - 90%) | Some Information but still need further details | Yes | Average | Continuous Epic Grooming | Sprint Planning | Tech Design | Risk call out during Weekly SoS | Release Planning, Strategy & Schedule (Proper Checkpoint and dates on jira tickets) | Ad-hoc Tasks & improper prioritisation | More Than 5% but less than 10% |  | YES | NA
2024-09-20 16:33 | Sandeep Kumar | Dev & Scrum Master | Iota | Yes | 10% to 20% | Yes | Yes | Well Managed | 5 | 5 | 3 | 5 | Yes | 5 | 4 | Scrum Team | 5 | 3 | Yes | 5 | YES | Moderate | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Some Information but still need further details | Yes | Well Managed | Continuous Epic Grooming | Sprint Closure/review | Ad-hoc requests prioritisation and acceptance | Strict Bug SLA's | Release Planning, Strategy & Schedule (Proper Checkpoint and dates on jira tickets) | Modifications on Approved Tech designs | My role involves process improvement and enablement (EM's, SM's & Other folks responsible for process streamlining) |  | YES | NA
2024-09-20 16:38 | Sandeep Kumar | Dev & Scrum Master | Iota | Yes | 10% to 20% | Yes | Yes | Balanced | 4 | 5 | 4 | 4 | Partially/Incomplete | 4 | 3 | Scrum Team | 4 | 4 | Yes | 4 | YES | Moderate | Less than 10% | Yes | Moderate | Balanced (80% - 90%) | Some Information but still need further details | Yes | Well Managed | Epic Breakdown | Sprint Closure/review | Ad-hoc requests prioritisation and acceptance | Blocking Scope change | Efficient Jira Usage (New Fields such as - Due date, QA Lead, QA Involvement, QA Signoff date) | Improper Epic Breakdown & Estimations - Missing Sprint Backlog | Less than 5% |  | YES | NA
2024-09-20 17:30 | Mohammed Fayaz | QA | Falcon | Yes | 10% or below | Yes | Yes | Balanced | 5 | 5 | 5 | 5 | Yes | 4 | 5 | Scrum Team | 5 | 5 | Yes | 5 | YES | Moderate | 10% to 20% | No | Moderate | Over Utilised (90% and Above) | Optimal information available | Not aware of any such initiative. Though the release coordination among teams was better than previous releases among teams | Well Managed | Code Freeze Milestones and hardening phase | Sprint Planning | Ad-hoc requests prioritisation and acceptance | Blocking Scope change | Work allocation with sufficient capacity reserve | Ad-hoc Tasks & improper prioritisation | More than 10% but Less than 20% | NA | YES | NA
2024-09-20 18:44 | Jegadeesh Santhana Krishnan | Dev | Helios | Yes | 10% or below | Yes | Yes | Balanced | 4 | 3 | 4 | 3 | Yes | 4 | 4 | Scrum Team | 4 | 4 | Yes | 4 | YES | Moderate | Less than 10% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Not aware of any such initiative. Though the release coordination among teams was better than previous releases among teams | Average | Epic Breakdown | Sprint Planning | Jira Automation | Change in Due date and QA Sign off Date restrictions | Release Planning, Strategy & Schedule (Proper Checkpoint and dates on jira tickets) | Improper Epic Breakdown & Estimations - Missing Sprint Backlog | Less than 5% | NA | YES | NA
2024-09-21 20:22 | Jegadeesh Santhana Krishnan | Dev & Scrum Master | Sharks | Yes | 10% or below | Yes | Yes | Balanced | 4 | 4 | 4 | 4 | Partially/Incomplete | 4 | 4 | Scrum Team | 5 | 5 | Yes | 5 | YES | Multiple | Less than 10% | Yes | Moderate | Over Utilised (90% and Above) | Optimal information available | Yes | Well Managed | Code Freeze Milestones and hardening phase | Sprint Planning | CI/CD, Testing & Continuous planning | Blocking Scope change | None | Intra team collaboration | My role involves process improvement and enablement (EM's, SM's & Other folks responsible for process streamlining) |  | YES | no
2024-09-22 12:27 | Jegadeesh Santhana Krishnan | Dev & Scrum Master | Chloris | Yes | 10% or below | Yes | Yes | Balanced | 5 | 5 | 5 | 5 | Yes | 5 | 5 | Scrum Team | 5 | 5 | Yes | 5 | YES | Multiple | Less than 10% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Committed Epic Prioritisation | Sprint Planning | Intra Team Collaboration - Dependency linking on Jira by Individual owners | Blocking Scope change | Better Estimations & Epic Breakdown | Delayed Response on open Queries, need multiple followups | My role involves process improvement and enablement (EM's, SM's & Other folks responsible for process streamlining) |  | YES | NIL
2024-09-23 09:22 | Jegadeesh Santhana Krishnan | Dev | Pheonix | Yes | 30% and Above | Yes | Yes | Balanced | 4 | 5 | 5 | 5 | Yes | 5 | 4 | Individual | 5 | 4 | Yes | 4 | YES | Multiple | More than 30% | Yes | Multiple | Balanced (80% - 90%) | Some Information but still need further details | Yes | Well Managed | Continuous Epic Grooming | Sprint Planning | Jira Details - Epic breakdown, DoD, Exit criteria, CS Bugs | Risk call out during Weekly SoS | Better & transparent commitments | Ad-hoc Tasks & improper prioritisation | Less than 5% |  | YES | Processes during branch lock and bugs management can be improved.
2024-09-23 09:48 | Mohammed Fayaz | QA | Iota | Yes | Just started using AI, need time to quantify | No | Yes | Chaotic | 3 | 3 | 3 | 5 | Partially/Incomplete | 4 | 4 | Individual | 5 | 3 | Yes | 3 | YES | None | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Average | Monitoring and Controlling Progress | Sprint Planning | Intra Team Collaboration - Dependency linking on Jira by Individual owners | Blocking Scope change | Reduced over commit | Delayed Response on open Queries, need multiple followups | Less than 5% |  | YES
2024-09-23 09:53 | Jegadeesh Santhana Krishnan | Dev | Eirene | Yes | 10% to 20% | Yes | Yes | Well Managed | 5 | 5 | 5 | 5 | Yes | 4 | 5 | Individual | 5 | 5 | Yes | 4 | YES | Multiple | Less than 10% | Yes | Moderate | Balanced (80% - 90%) | Some Information but still need further details | Yes | Well Managed | Release Kick Off | Sprint Planning | Jira Details - Epic breakdown, DoD, Exit criteria, CS Bugs | Blocking Scope change | Risk call out (Release Confluence Page) | Partial or missing details on Jira Trackers Description | Less than 5% |  | YES | Release planning should be distinguishable
2024-09-23 09:58 | Sandeep Kumar | QA | Iota | Yes | 10% or below | Yes | Yes | Well Managed | 5 | 5 | 5 | 5 | Yes | 5 | 5 | Individual | 5 | 5 | Yes | 5 | YES | None | Less than 10% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Committed Epic Prioritisation | Sprint Planning | Intra Team Collaboration - Dependency linking on Jira by Individual owners | Blocking Scope change | Better & transparent commitments | Delay in commitments from dependant team | Less than 5% |  | YES | No
2024-09-23 10:22 | Sandeep Kumar | Dev & Scrum Master | Phi | Yes | 10% or below | Yes | Yes | Balanced | 3 | 4 | 5 | 4 | Yes | 4 | 4 | Individual | 4 | 4 | Yes | 4 | YES | Moderate | 10% to 20% | No | Moderate | Balanced (80% - 90%) | Some Information but still need further details | Not aware and did not find any significant change in the release coordination among teams | Average | Monitoring and Controlling Progress | Sprint Closure/review | Non Release Activity Identification & capacity reserve | Change in Due date and QA Sign off Date restrictions | Reduced over commit | Delay in commitments from dependant team | Less than 5% |  | Not Efficiently | NA
2024-09-23 10:25 | Mohammed Fayaz | QA | Ganges | Yes | 10% to 20% | Yes | Yes | Balanced | 4 | 4 | 4 | 4 | Partially/Incomplete | 4 | 4 | Scrum Team | 4 | 4 | Yes | 4 | YES | Moderate | Less than 10% | Yes | Moderate | Balanced (80% - 90%) | Some Information but still need further details | Yes | Average | Continuous Epic Grooming | Sprint Planning | Jira Details - Epic breakdown, DoD, Exit criteria, CS Bugs | Change in Due date and QA Sign off Date restrictions | Better & transparent commitments | Ad-hoc Tasks & improper prioritisation | More Than 5% but less than 10% | NA | YES | NA
2024-09-23 10:34 | Mohammed Fayaz | QA | Iota | Yes | 10% or below | Yes | Yes | Chaotic | 2 | 3 | 5 | 3 | Yes | 4 | 4 | Individual | 4 | 4 | Yes | 4 | YES | Moderate | Less than 10% | Yes | Moderate | Balanced (80% - 90%) | Some Information but still need further details | Yes | Average | Continuous Epic Grooming | Sprint Closure/review | Test Design | Blocking Scope change | Release Planning, Strategy & Schedule (Proper Checkpoint and dates on jira tickets) | Improper Epic Breakdown & Estimations - Missing Sprint Backlog | Less than 5% | na | YES | na
2024-09-23 10:35 | Sandeep Kumar | Dev | Zeta | Yes | 20% to 30% | Yes | Yes | Balanced | 4 | 5 | 5 | 5 | Partially/Incomplete | 5 | 5 | Scrum Team | 5 | 4 | Yes | 5 | YES | Moderate | Less than 10% | Yes | Moderate | Over Utilised (90% and Above) | Some Information but still need further details | Yes | Average | Epic Breakdown | Sprint Planning | CI/CD, Testing & Continuous planning | Blocking Scope change | Better Estimations & Epic Breakdown | Intra team collaboration | Less than 5% |  | YES | No
2024-09-23 10:41 | Mujtaba Ahmad | Dev & Scrum Master | Stark | Yes | 10% to 20% | Yes | Yes | Balanced | 4 | 4 | 4 | 4 | Yes | 4 | 4 | Individual | 4 | 4 | No |  | YES | Moderate | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Some Information but still need further details | Not aware of any such initiative. Though the release coordination among teams was better than previous releases among teams | Average | Epic Breakdown | Sprint Closure/review | Tech Design | Blocking Scope change | Better & transparent commitments | Ad-hoc Tasks & improper prioritisation | More than 10% but Less than 20% |  | YES | NA
2024-09-23 10:43 | Sandeep Kumar | Dev | Tranformers | Yes | 10% or below | Yes | Yes | Well Managed | 5 | 5 | 5 | 5 | Yes | 4 | 5 | Scrum Team | 5 | 5 | Yes | 5 | YES | Moderate | Less than 10% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Monitoring and Controlling Progress | Sprint Planning | Ad-hoc requests prioritisation and acceptance | Risk call out during Weekly SoS | Better Estimations & Epic Breakdown | Delayed Response on open Queries, need multiple followups | More Than 5% but less than 10% |  | YES | no
2024-09-23 11:01 | Jegadeesh Santhana Krishnan | Dev & Scrum Master | Pheonix | No |  |  | Yes | Balanced | 4 | 5 | 5 | 5 | Yes | 5 | 5 | Individual | 4 | 4 | Yes | 4 | YES | Moderate | Less than 10% | Yes | None | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Continuous Epic Grooming | Sprint Closure/review | Intra Team Collaboration - Dependency linking on Jira by Individual owners | Change in Due date and QA Sign off Date restrictions | Better & transparent commitments | Intra team collaboration | My role involves process improvement and enablement (EM's, SM's & Other folks responsible for process streamlining) |  | YES | NA
2024-09-23 11:07 | Sandeep Kumar | Dev | Dynamos | No |  |  | Yes | Well Managed | 5 | 5 | 5 | 5 | Yes | 5 | 5 | Scrum Team | 5 | 5 | Yes | 5 | YES | Multiple | 10% to 20% | Yes | None | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Continuous Epic Grooming | Sprint Planning | CI/CD, Testing & Continuous planning | Change in Due date and QA Sign off Date restrictions | Work allocation with sufficient capacity reserve | Reviews | More Than 5% but less than 10% |  | YES | No
2024-09-23 11:11 | Mohammed Fayaz | QA | Pheonix | Yes | 10% to 20% | Yes | Yes | Balanced | 5 | 5 | 5 | 5 | Yes | 5 | 5 | Scrum Team | 5 | 5 | Yes | 5 | YES | Multiple | 20% to 30% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Release Kick Off | Sprint Closure/review | Non Release Activity Identification & capacity reserve | Risk call out during Weekly SoS | Dependency management | Non Release Activities | More Than 5% but less than 10% | NA | YES | NA
2024-09-23 11:11 | Sandeep Kumar | Dev & Scrum Master | Gryffindor | Yes | 10% to 20% | Yes | Yes | Chaotic | 3 | 5 | 5 | 5 | Yes | 5 | 4 | Scrum Team | 5 | 3 | Yes | 5 | YES | None | Less than 10% | No | Multiple | Over Utilised (90% and Above) | Optimal information available | Yes | Average | Committed Epic Prioritisation | Sprint Planning | Ad-hoc requests prioritisation and acceptance | Blocking Scope change | Risk call out (Release Confluence Page) | Ad-hoc Tasks & improper prioritisation | Less than 5% |  | YES | Effectively managing the adhoc things from the other team
2024-09-23 11:12 | Jegadeesh Santhana Krishnan | Dev | Chipmuks | Yes | 10% to 20% | Yes | No
2024-09-23 11:16 | Jegadeesh Santhana Krishnan | Dev | Chipmuks | Yes | 10% or below | Yes | Yes | Balanced | 4 | 5 | 4 | 3 | Yes | 3 | 4 | Scrum Team | 5 | 5 | Yes | 3 | YES | Moderate | 10% to 20% | Yes | Moderate | Over Utilised (90% and Above) | Some Information but still need further details | Not aware and did not find any significant change in the release coordination among teams | Average | Continuous Epic Grooming | Sprint Retrospective | KT and recording repository | Risk call out during Weekly SoS | None | Ad-hoc Tasks & improper prioritisation | More Than 5% but less than 10% |  | YES | no
2024-09-23 11:17 | Sandeep Kumar | Dev | Iota | Yes | 10% or below | No | Yes | Chaotic | 4 | 4 | 4 | 4 | Yes | 4 | 4 | Scrum Team | 4 | 5 | Yes | 5 | YES | Multiple | Less than 10% | Yes | Moderate | Over Utilised (90% and Above) | Optimal information available | Not aware and did not find any significant change in the release coordination among teams | Well Managed | Monitoring and Controlling Progress | Sprint Closure/review | Intra Team Collaboration - Dependency linking on Jira by Individual owners | Change in Due date and QA Sign off Date restrictions | Work allocation with sufficient capacity reserve | Delay in commitments from dependant team | More Than 5% but less than 10% |  | YES | -
2024-09-23 11:23 | Mohammed Fayaz | QA | Zeta | No |  |  | Yes | Balanced | 4 | 4 | 4 | 4 | Yes | 4 | 4 | Scrum Team | 4 | 4 | Yes | 4 | YES | Moderate | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Average | Continuous Epic Grooming | Sprint Planning | Intra Team Collaboration - Dependency linking on Jira by Individual owners | Strict Bug SLA's | Release Planning, Strategy & Schedule (Proper Checkpoint and dates on jira tickets) | Ad-hoc Tasks & improper prioritisation | Less than 5% |  | YES | No
2024-09-23 11:28 | Mohammed Fayaz | QA | Dynamos | Yes | 10% or below | Yes | Yes | Well Managed | 5 | 5 | 5 | 5 | Yes | 5 | 5 | Individual | 5 | 5 | Yes | 4 | YES | Moderate | Less than 10% | No | Multiple | Over Utilised (90% and Above) | Optimal information available | Yes | Well Managed | Epic Breakdown | Sprint Planning | Jira Automation | Blocking Scope change | Release Planning, Strategy & Schedule (Proper Checkpoint and dates on jira tickets) | Ad-hoc Tasks & improper prioritisation | More Than 5% but less than 10% |  | YES | we could improve in how we break down the epics and deliver the stories to completion with dev and qa efforts in sprint
2024-09-23 11:29 | Mohammed Fayaz | QA | Dynamos | Yes | Just started using AI, need time to quantify | Yes | Yes | Well Managed | 5 | 5 | 5 | 5 | Yes | 5 | 4 | Scrum Team | 5 | 5 | Yes | 4 | YES | Moderate | Less than 10% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Average | Committed Epic Prioritisation | Sprint Closure/review | Intra Team Collaboration - Dependency linking on Jira by Individual owners | Risk call out during Weekly SoS | Efficient Jira Usage (New Fields such as - Due date, QA Lead, QA Involvement, QA Signoff date) | Delayed Response on open Queries, need multiple followups | Less than 5% |  | YES | NA
2024-09-23 11:30 | Sandeep Kumar | Dev | Dynamos | Yes | 10% or below | Yes | Yes | Balanced | 4 | 4 | 4 | 4 | Yes | 4 | 4 | Scrum Team | 4 | 4 | Yes | 5 | YES | Multiple | Less than 10% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Continuous Epic Grooming | Sprint Planning | Ad-hoc requests prioritisation and acceptance | Change in Due date and QA Sign off Date restrictions | Release Planning, Strategy & Schedule (Proper Checkpoint and dates on jira tickets) | Ad-hoc Tasks & improper prioritisation | More Than 5% but less than 10% |  | YES | NA
2024-09-23 11:31 | Sandeep Kumar | EM | Transformers Dynamos | No |  |  | Yes | Well Managed |  | 5 | 5 | 5 | Yes | 5 | 5 | Scrum Team | 3 | 4 | Yes | 5 | YES | Multiple | 20% to 30% | Yes | Moderate | Balanced (80% - 90%) | Some Information but still need further details | Yes | Well Managed | Monitoring and Controlling Progress | Sprint Closure/review | Jira Automation | Risk call out during Weekly SoS | Better & transparent commitments | PR Merges | My role involves process improvement and enablement (EM's, SM's & Other folks responsible for process streamlining) | . | YES | .
2024-09-23 11:32 | Sandeep Kumar | Dev | Leo | No |  |  | Yes | Balanced | 4 | 5 | 5 | 4 | Partially/Incomplete | 4 | 4 | Scrum Team | 3 | 4 | Yes | 4 | Moderately | Multiple | 10% to 20% | No | Moderate | Balanced (80% - 90%) | Not at All | Not aware of any such initiative. Though the release coordination among teams was better than previous releases among teams | Average | Committed Epic Prioritisation | Sprint Planning | Backlog & CS bugs prioritisation | Blocking Scope change | Release Planning, Strategy & Schedule (Proper Checkpoint and dates on jira tickets) | Ad-hoc Tasks & improper prioritisation | More Than 5% but less than 10% |  | YES | Jira Management needs to be improved
2024-09-23 11:32 | Sandeep Kumar | Dev | Dynamos | Yes | 20% to 30% | Yes | Yes | Balanced | 4 | 4 | 4 | 4 | Yes | 5 | 4 | Individual | 4 | 2 | Yes | 2 | YES | Moderate | 10% to 20% | Yes | Moderate | Over Utilised (90% and Above) | Some Information but still need further details | Not aware of any such initiative. Though the release coordination among teams was better than previous releases among teams | Average | Monitoring and Controlling Progress | Sprint Closure/review | Intra Team Collaboration - Dependency linking on Jira by Individual owners | Blocking Scope change | Effective communication | PR Merges | Less than 5% | NA | YES | NA
2024-09-23 11:33 | Jegadeesh Santhana Krishnan | Dev | Echo | Yes | 20% to 30% | Yes | Yes | Balanced | 5 | 5 | 5 | 5 | Yes | 4 | 5 | Individual | 5 | 5 | Yes | 5 | YES | Multiple | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Code Freeze Milestones and hardening phase | Sprint Planning | Ad-hoc requests prioritisation and acceptance | Risk call out during Weekly SoS | Dependency management | Ad-hoc Tasks & improper prioritisation | More than 10% but Less than 20% |  | YES | .
2024-09-23 11:34 | Sandeep Kumar | Dev | Phi | Yes | 30% and Above | Yes | No
2024-09-23 11:41 | Sandeep Kumar | Dev | Iota | Yes | 10% or below | Yes | No
2024-09-23 11:43 | Sandeep Kumar | Dev | Dynamos | Yes | 10% to 20% | Yes | Yes | Balanced | 3 | 3 | 3 | 4 | Yes | 2 | 3 | SME/Epic Owner/EM/QM (Pre Defined Efforts Estimates) | 3 | 2 | Yes | 4 | Moderately | Moderate | 10% to 20% | Yes | Moderate | Over Utilised (90% and Above) | Some Information but still need further details | Not aware of any such initiative. Though the release coordination among teams was better than previous releases among teams | Average | Continuous Epic Grooming | Sprint Planning | Ad-hoc requests prioritisation and acceptance | Blocking Scope change | Effective communication | Ad-hoc Tasks & improper prioritisation | More Than 5% but less than 10% |  | YES | More time to be spent in designing and review, to reduce the number of new changes required later on.
2024-09-23 11:45 | Jegadeesh Santhana Krishnan | Dev | Hercules | Yes | 10% to 20% | Yes | No
2024-09-23 11:58 | Jegadeesh Santhana Krishnan | Dev | Pheonix | Yes | 10% to 20% | Yes | Yes | Balanced | 4 | 4 | 4 | 4 | Yes | 4 | 4 | Individual | 4 | 4 | Yes | 4 | YES | Moderate | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Some Information but still need further details | Not aware of any such initiative. Though the release coordination among teams was better than previous releases among teams | Average | Committed Epic Prioritisation | Sprint Planning | Intra Team Collaboration - Dependency linking on Jira by Individual owners | Blocking Scope change | Efficient Jira Usage (New Fields such as - Due date, QA Lead, QA Involvement, QA Signoff date) | Modifications on Approved Tech designs | More Than 5% but less than 10% |  | YES | N/A
2024-09-23 12:02 | Mohammed Fayaz | QA | Tranformers | Yes | 10% to 20% | Yes | Yes | Balanced | 4 | 4 | 4 | 5 | Yes | 4 | 4 | Scrum Team | 5 | 4 | Yes | 5 | YES | Moderate | 10% to 20% | No | Moderate | Balanced (80% - 90%) | Some Information but still need further details | Yes | Well Managed | Committed Epic Prioritisation | Sprint Closure/review | Non Release Activity Identification & capacity reserve | Change in Due date and QA Sign off Date restrictions | Reduced over commit | Non Release Activities | More Than 5% but less than 10% | NA | YES | follow the timelines and process strictly
2024-09-23 12:17 | Sandeep Kumar | Dev | Tranformers | Yes | 10% to 20% | No | Yes | Chaotic | 3 | 4 | 3 | 4 | Partially/Incomplete | 3 | 3 | Scrum Team | 5 | 4 | Yes | 4 | Moderately | Multiple | More than 30% | Yes | Multiple | Over Utilised (90% and Above) | Some Information but still need further details | Yes | Average | Committed Epic Prioritisation | Sprint Closure/review | Backlog & CS bugs prioritisation | Risk call out during Weekly SoS | Release Planning, Strategy & Schedule (Proper Checkpoint and dates on jira tickets) | Ad-hoc Tasks & improper prioritisation | More than 10% but Less than 20% |  | YES | NA
2024-09-23 12:20 | Krishna Kishore Mothukuri | Dev | Velocity | Yes | 30% and Above | Yes | Yes | Well Managed | 5 | 4 | 5 | 4 | Yes | 4 | 4 | Scrum Team | 4 | 4 | Yes | 4 | Moderately | Moderate | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Average | Committed Epic Prioritisation | Sprint DSU's | KT and recording repository | Blocking Scope change | Effective communication | Improper Epic Breakdown & Estimations - Missing Sprint Backlog | Less than 5% | NO | YES | no
2024-09-23 12:22 | Product Management | Dev & Scrum Master | Zeta | Yes | 20% to 30% | Yes | Yes | Well Managed | 4 | 5 | 5 | 5 | Yes | 5 | 4 | Scrum Team | 4 | 4 | Yes | 4 | YES | Moderate | Less than 10% | Yes | Moderate | Balanced (80% - 90%) | Some Information but still need further details | Yes | Well Managed | Epic Breakdown | Sprint Closure/review | Test Design | Risk call out during Weekly SoS | Release Planning, Strategy & Schedule (Proper Checkpoint and dates on jira tickets) | Ad-hoc Tasks & improper prioritisation | My role involves process improvement and enablement (EM's, SM's & Other folks responsible for process streamlining) |  | YES | no
2024-09-23 12:41 | Mohammed Fayaz | QA | Gryffindor | Yes | 10% to 20% | Yes | Yes | Balanced | 4 | 4 | 4 | 4 | Partially/Incomplete | 3 | 3 | Scrum Team | 4 | 3 | Yes | 3 | Moderately | Moderate | 10% to 20% | Yes | Moderate | Over Utilised (90% and Above) | Some Information but still need further details | Yes | Average | Committed Epic Prioritisation | Sprint Closure/review | Jira Details - Epic breakdown, DoD, Exit criteria, CS Bugs | Change in Due date and QA Sign off Date restrictions | Effective communication | Reviews | More Than 5% but less than 10% |  | Not Efficiently | NA
2024-09-23 12:43 | Krishna Kishore Mothukuri | Dev | Velocity | Yes | 10% to 20% | Yes | Yes | Well Managed | 5 | 5 | 4 | 4 | Yes | 5 | 5 | Individual | 4 | 4 | Yes | 4 | YES | Moderate | 10% to 20% | No | None | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Monitoring and Controlling Progress | Sprint Closure/review | Test Design | Change in Due date and QA Sign off Date restrictions | None | Intra team collaboration | More Than 5% but less than 10% |  | YES | NA
2024-09-23 12:47 | Krishna Kishore Mothukuri | Dev | Velocity | Yes | 30% and Above | Yes | No
2024-09-23 12:56 | Krishna Kishore Mothukuri | Dev | Pathfinders | Yes | 30% and Above | Yes | Yes | Balanced | 5 | 5 | 5 | 5 | Partially/Incomplete | 5 | 4 | Individual | 4 | 4 | Yes | 5 | YES | Multiple | 10% to 20% | No | Moderate | Over Utilised (90% and Above) | Some Information but still need further details | Yes | Well Managed | Epic Breakdown | Sprint Planning | Jira Details - Epic breakdown, DoD, Exit criteria, CS Bugs | Blocking Scope change | Work allocation with sufficient capacity reserve | Ad-hoc Tasks & improper prioritisation | More than 20% |  | YES | NA
2024-09-23 12:59 | Mujtaba Ahmad | Dev | Ganges | No |  |  | Yes | Balanced | 4 | 5 | 4 | 5 | Yes | 4 | 5 | Scrum Team | 5 | 4 | Yes | 4 | YES | Multiple | Less than 10% | No | Moderate | Over Utilised (90% and Above) | Optimal information available | Not aware of any such initiative. Though the release coordination among teams was better than previous releases among teams | Average | Monitoring and Controlling Progress | Sprint Planning | Ad-hoc requests prioritisation and acceptance | Risk call out during Weekly SoS | Release Planning, Strategy & Schedule (Proper Checkpoint and dates on jira tickets) | Reviews | Less than 5% |  | YES | Improving on inter team dependencies in case of micro services
2024-09-23 13:00 | Mujtaba Ahmad | Dev | Ganges | Yes | 10% to 20% | Yes | Yes | Balanced | 3 | 5 | 5 | 4 | Yes | 4 | 4 | Scrum Team | 4 | 4 | Yes | 4 | YES | Moderate | Less than 10% | Yes | Moderate | Over Utilised (90% and Above) | Optimal information available | Not aware of any such initiative. Though the release coordination among teams was better than previous releases among teams | Average | Epic Breakdown | Sprint Planning | Jira Details - Epic breakdown, DoD, Exit criteria, CS Bugs | Blocking Scope change | Effective communication | Ad-hoc Tasks & improper prioritisation | Less than 5% |  | YES | no
2024-09-23 13:09 | Mujtaba Ahmad | Dev | Ganges | Yes | Just started using AI, need time to quantify | Yes | Yes | Well Managed | 4 | 4 | 4 | 4 | Yes | 4 | 5 | Scrum Team | 5 | 5 | Yes | 5 | YES | Multiple | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Epic Breakdown | Sprint Planning | CI/CD, Testing & Continuous planning | Strict Bug SLA's | Release Planning, Strategy & Schedule (Proper Checkpoint and dates on jira tickets) | Delayed Response on open Queries, need multiple followups | Less than 5% |  | YES | No
2024-09-23 13:15 | Mohammed Fayaz | QA | Chakra | Yes | 10% to 20% | Yes | Yes | Balanced | 5 | 5 | 5 | 5 | Yes | 5 | 5 | Scrum Team | 5 | 5 | Yes | 5 | YES | Multiple | Less than 10% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Epic Breakdown | Sprint Planning | Jira Details - Epic breakdown, DoD, Exit criteria, CS Bugs | Change in Due date and QA Sign off Date restrictions | Better Estimations & Epic Breakdown | Improper Epic Breakdown & Estimations - Missing Sprint Backlog | Less than 5% |  | YES | NA
2024-09-23 13:40 | Sandeep Kumar | Dev & Scrum Master | Tranformers | Yes | 10% to 20% | Yes | Yes | Balanced | 4 | 4 | 5 | 5 | Yes | 4 | 4 | Scrum Team | 4 | 2 | Yes | 5 | YES | Moderate | 20% to 30% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Average | Monitoring and Controlling Progress | Sprint Closure/review | Non Release Activity Identification & capacity reserve | Change in Due date and QA Sign off Date restrictions | Efficient Jira Usage (New Fields such as - Due date, QA Lead, QA Involvement, QA Signoff date) | Ad-hoc Tasks & improper prioritisation | My role involves process improvement and enablement (EM's, SM's & Other folks responsible for process streamlining) | NA | YES | NA
2024-09-23 13:55 | Sandeep Kumar | QA | Phi | Yes | 10% or below | Yes | Yes | Chaotic | 3 | 3 | 3 | 3 | Partially/Incomplete | 3 | 3 | Scrum Team | 3 | 3 | Yes | 4 | NO | None | Less than 10% | No | Multiple | Over Utilised (90% and Above) | Optimal information available | Not aware and did not find any significant change in the release coordination among teams | Average | Monitoring and Controlling Progress | Sprint Planning | Non Release Activity Identification & capacity reserve | Strict Bug SLA's | Dependency management | Ad-hoc Tasks & improper prioritisation | More Than 5% but less than 10% |  | Not Efficiently | Proritise task properly
2024-09-23 14:44 | Sandeep Kumar | Dev | Iota | Yes | 10% to 20% | No | No
2024-09-23 14:54 | Sandeep Kumar | Dev | Iota | Yes | 30% and Above | Yes | Yes | Chaotic | 3 | 4 | 4 | 3 | Yes | 3 | 4 | Scrum Team | 4 | 3 | Yes | 4 | YES | Moderate | 20% to 30% | Yes | Multiple | Balanced (80% - 90%) | Some Information but still need further details | Yes | Average | Code Freeze Milestones and hardening phase | Sprint Closure/review | Ad-hoc requests prioritisation and acceptance | Change in Due date and QA Sign off Date restrictions | Better Estimations & Epic Breakdown | Ad-hoc Tasks & improper prioritisation | More Than 5% but less than 10% |  | YES | NA
2024-09-23 16:56 | Jegadeesh Santhana Krishnan | Others | architects | Yes | 10% or below | No | No
2024-09-23 18:51 | Krishna Kishore Mothukuri | Dev & Scrum Master | Velocity | Yes | 20% to 30% | Yes | Yes | Balanced | 4 | 5 | 5 | 5 | Yes | 5 | 4 | Individual | 4 | 4 | Yes | 4 | YES | Multiple | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Some Information but still need further details | Yes | Average | Epic Breakdown | Sprint Planning | Intra Team Collaboration - Dependency linking on Jira by Individual owners | Blocking Scope change | Release Planning, Strategy & Schedule (Proper Checkpoint and dates on jira tickets) | Improper Epic Breakdown & Estimations - Missing Sprint Backlog | More Than 5% but less than 10% |  | YES | No
2024-09-23 21:10 | Sandeep Kumar | EM | Gryffindor | Yes | 10% to 20% | Yes | No
2024-09-23 21:43 | Mohammed Fayaz | EM | Chipmuks | Yes | 10% or below | Yes | Yes | Balanced | 4 | 4 | 5 | 5 | Partially/Incomplete | 5 | 4 | Scrum Team | 5 | 4 | Yes | 4 | YES | Moderate | 10% to 20% | Yes | None | Balanced (80% - 90%) | Some Information but still need further details | Yes | Well Managed | Continuous Epic Grooming | Sprint Planning | Jira Details - Epic breakdown, DoD, Exit criteria, CS Bugs | Change in Due date and QA Sign off Date restrictions | Release Planning, Strategy & Schedule (Proper Checkpoint and dates on jira tickets) | Improper Epic Breakdown & Estimations - Missing Sprint Backlog | My role involves process improvement and enablement (EM's, SM's & Other folks responsible for process streamlining) |  | YES | NA
2024-09-23 22:08 | Mujtaba Ahmad | Dev & Scrum Master | Enigma | Yes | Just started using AI, need time to quantify | Yes | Yes | Balanced | 5 | 5 | 5 | 5 | Yes | 4 | 5 | Individual | 5 | 4 | Yes | 5 | YES | Moderate | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Some Information but still need further details | Yes | Well Managed | Committed Epic Prioritisation | Sprint Planning | Backlog & CS bugs prioritisation | Risk call out during Weekly SoS | Efficient Jira Usage (New Fields such as - Due date, QA Lead, QA Involvement, QA Signoff date) | Partial or missing details on Jira Trackers Description | More Than 5% but less than 10% |  | YES | No
2024-09-23 23:09 | Mohammed Fayaz | QA | Sharks | Yes | 10% or below | Yes | Yes | Well Managed | 5 | 5 | 5 | 5 | Yes | 5 | 5 | Individual | 5 | 5 | Yes | 5 | YES | Moderate | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes |  | Committed Epic Prioritisation | Sprint Planning | Backlog & CS bugs prioritisation | Strict Bug SLA's | Better Estimations & Epic Breakdown | Ad-hoc Tasks & improper prioritisation | Less than 5% |  | YES | NA
2024-09-23 23:40 | Sandeep Kumar | Dev | Gryffindor | Yes | 10% or below | Yes | Yes | Balanced | 4 | 5 | 3 | 5 | Partially/Incomplete | 4 | 4 | Scrum Team | 4 | 4 | Yes | 4 | YES | Moderate | 10% to 20% | No | Moderate | Balanced (80% - 90%) | Some Information but still need further details | Yes | Average | Committed Epic Prioritisation | Sprint Planning | Intra Team Collaboration - Dependency linking on Jira by Individual owners | Blocking Scope change | Risk call out (Release Confluence Page) | CS Bugs higher than the reserved Capacity | More Than 5% but less than 10% |  | YES | NA
2024-09-24 00:09 | Sandeep Kumar | Dev | Zeta | Yes | 10% to 20% | Yes | Yes | Well Managed | 5 | 3 | 2 | 4 | Yes | 5 | 5 | Scrum Team | 5 | 4 | Yes | 5 | YES | Moderate | 20% to 30% | Yes | Multiple | Over Utilised (90% and Above) | Optimal information available | Not aware of any such initiative. Though the release coordination among teams was better than previous releases among teams | Well Managed | Committed Epic Prioritisation | Sprint Planning | KT and recording repository | Blocking Scope change | Efficient Jira Usage (New Fields such as - Due date, QA Lead, QA Involvement, QA Signoff date) | Ad-hoc Tasks & improper prioritisation | More Than 5% but less than 10% |  | YES | No
2024-09-24 08:41 | Mohammed Fayaz | QA | Stark | Yes | Just started using AI, need time to quantify | Yes | Yes | Balanced | 3 | 5 | 5 | 4 | Yes | 4 | 4 | Individual | 4 | 3 | Yes | 3 | Moderately | Multiple | Less than 10% | Yes | Multiple | Over Utilised (90% and Above) | Some Information but still need further details | Yes | Well Managed | Continuous Epic Grooming | Sprint Planning | Ad-hoc requests prioritisation and acceptance | Change in Due date and QA Sign off Date restrictions | Efficient Jira Usage (New Fields such as - Due date, QA Lead, QA Involvement, QA Signoff date) | Ad-hoc Tasks & improper prioritisation | More Than 5% but less than 10% | NA | YES | NA
2024-09-24 09:32 | Jegadeesh Santhana Krishnan | Dev | Sharks | Yes | 20% to 30% | Yes | Yes | Well Managed | 5 | 5 | 5 | 5 | Yes | 5 | 5 | Scrum Team | 5 | 5 | Yes | 5 | YES | Multiple | Less than 10% | Yes | Moderate | Over Utilised (90% and Above) | Optimal information available | Yes | Well Managed | Epic Breakdown | Sprint DSU's | Intra Team Collaboration - Dependency linking on Jira by Individual owners | Strict Bug SLA's | Release Planning, Strategy & Schedule (Proper Checkpoint and dates on jira tickets) | PR Merges | More than 10% but Less than 20% |  | YES | All good.
2024-09-24 09:48 | Jegadeesh Santhana Krishnan | EM | Hercules | Yes | 30% and Above | Yes | Yes | Well Managed | 5 | 5 | 5 | 5 | Yes | 5 | 5 | Individual | 5 | 5 | Yes | 5 | YES | Moderate | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Monitoring and Controlling Progress | Sprint Closure/review | Ad-hoc requests prioritisation and acceptance | Risk call out during Weekly SoS | Reduced over commit | Missing SLA's for Bugs, Trackers on Jira | My role involves process improvement and enablement (EM's, SM's & Other folks responsible for process streamlining) |  | YES | -
2024-09-24 10:07 | Jegadeesh Santhana Krishnan | Dev & Scrum Master | Hercules | Yes | 10% to 20% | Yes | Yes | Balanced | 4 | 4 | 5 | 4 | Yes | 4 | 4 | Individual | 4 | 4 | Yes | 3 | YES | Multiple | Less than 10% | Yes | None | Balanced (80% - 90%) | Optimal information available | Yes | Average | Release Kick Off | Sprint Retrospective | Jira Details - Epic breakdown, DoD, Exit criteria, CS Bugs | Change in Due date and QA Sign off Date restrictions | Release Planning, Strategy & Schedule (Proper Checkpoint and dates on jira tickets) | Improper Epic Breakdown & Estimations - Missing Sprint Backlog | My role involves process improvement and enablement (EM's, SM's & Other folks responsible for process streamlining) |  | YES | N/A
2024-09-24 10:23 | Jegadeesh Santhana Krishnan | Dev | Echo | Yes | 10% to 20% | Yes | No
2024-09-24 10:35 | Jegadeesh Santhana Krishnan | Dev | Chipmuks | Yes | 10% to 20% | Yes | Yes | Well Managed | 4 | 5 | 4 | 4 | Yes | 5 | 4 | Scrum Team | 4 | 4 | No |  | YES | Multiple | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Not aware of any such initiative. Though the release coordination among teams was better than previous releases among teams | Well Managed | Monitoring and Controlling Progress | Sprint Closure/review | Non Release Activity Identification & capacity reserve | Blocking Scope change | Better Estimations & Epic Breakdown | Reviews | Less than 5% |  | YES | -
2024-09-24 10:57 | Jegadeesh Santhana Krishnan | Dev | Iris | Yes | 30% and Above | Yes | Yes | Well Managed | 4 | 4 | 4 | 4 | Yes | 4 | 5 | Individual | 4 | 4 | Yes | 5 | YES | Moderate | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Monitoring and Controlling Progress | Sprint Closure/review | Backlog & CS bugs prioritisation | Risk call out during Weekly SoS | Better & transparent commitments | Reviews | More Than 5% but less than 10% |  | YES | None
2024-09-24 11:03 | Krishna Kishore Mothukuri | Dev | Hercules | Yes | 20% to 30% | Yes | No
2024-09-24 11:07 | Jegadeesh Santhana Krishnan | Dev | Chloris | Yes | 10% to 20% | Yes | Yes | Balanced | 4 | 4 | 5 | 5 | Yes | 4 | 4 | Individual | 4 | 4 | Yes | 4 | YES | Moderate | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Some Information but still need further details | Yes | Well Managed | Committed Epic Prioritisation | Sprint Closure/review | Ad-hoc requests prioritisation and acceptance | Risk call out during Weekly SoS | Better Estimations & Epic Breakdown | PR Merges | Less than 5% | - | YES | -
2024-09-24 11:08 | Krishna Kishore Mothukuri | Dev | Pathfinders | Yes | 20% to 30% | Yes | No
2024-09-24 11:09 | Jegadeesh Santhana Krishnan | Dev | Eirene | Yes | 20% to 30% | Yes | Yes | Well Managed | 5 | 5 | 5 | 5 | Yes | 5 | 5 | Individual | 5 | 5 | Yes | 5 | YES | Multiple | Less than 10% | Yes | None | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Continuous Epic Grooming | Sprint Retrospective | Jira Details - Epic breakdown, DoD, Exit criteria, CS Bugs | Risk call out during Weekly SoS | Better Estimations & Epic Breakdown | Improper Epic Breakdown & Estimations - Missing Sprint Backlog | Less than 5% |  | YES | -
2024-09-24 11:09 | Mujtaba Ahmad | Dev & Scrum Master | Indus | Yes | 10% to 20% | Yes | Yes | Well Managed | 5 | 5 | 4 | 5 | Yes | 4 | 3 | Scrum Team | 3 | 5 | Yes | 3 | YES | Moderate | 10% to 20% | Yes | Moderate | Over Utilised (90% and Above) | Optimal information available | Yes | Well Managed | Committed Epic Prioritisation | Sprint Planning | Backlog & CS bugs prioritisation | Risk call out during Weekly SoS | Better Estimations & Epic Breakdown | Improper Epic Breakdown & Estimations - Missing Sprint Backlog | More than 10% but Less than 20% |  | YES | NONE
2024-09-24 11:16 | Mujtaba Ahmad | Dev | Stark | Yes | 10% to 20% | Yes | Yes | Balanced | 3 | 3 | 4 | 4 | Yes | 4 | 4 | Scrum Team | 4 | 1 | Yes | 4 | Moderately | Moderate | 10% to 20% | No | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Monitoring and Controlling Progress | Sprint Retrospective | KT and recording repository | Change in Due date and QA Sign off Date restrictions | Better Estimations & Epic Breakdown | Ad-hoc Tasks & improper prioritisation | More Than 5% but less than 10% |  | YES | NA
2024-09-24 11:21 | Mohammed Fayaz | QA | Dexter | Yes | Just started using AI, need time to quantify | Yes | Yes | Balanced | 4 | 4 | 4 | 4 | Yes | 4 | 4 | Scrum Team | 4 | 4 | Yes | 4 | YES | Moderate | Less than 10% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Continuous Epic Grooming | Sprint Closure/review | Jira Details - Epic breakdown, DoD, Exit criteria, CS Bugs | Strict Bug SLA's | Efficient Jira Usage (New Fields such as - Due date, QA Lead, QA Involvement, QA Signoff date) | Delayed Response on open Queries, need multiple followups | Less than 5% |  | YES | NA
2024-09-24 11:25 | Jegadeesh Santhana Krishnan | EM | Aurora | Yes | 10% to 20% | Yes | Yes | Well Managed | 5 | 5 |  | 5 | Yes | 5 | 5 | Individual | 5 | 5 | Yes | 5 | YES | Multiple | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Continuous Epic Grooming | Sprint Planning | Ad-hoc requests prioritisation and acceptance | Blocking Scope change | Better Estimations & Epic Breakdown | Ad-hoc Tasks & improper prioritisation | My role involves process improvement and enablement (EM's, SM's & Other folks responsible for process streamlining) |  | YES | No
2024-09-24 11:25 | Jegadeesh Santhana Krishnan | Dev & Scrum Master | Eirene | Yes | 10% to 20% | Yes | Yes | Balanced | 4 | 4 | 4 | 4 | Yes | 4 | 4 | Individual | 4 | 4 | Yes | 4 | YES | Moderate | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Some Information but still need further details | Yes | Average | Continuous Epic Grooming | Sprint Planning | Jira Details - Epic breakdown, DoD, Exit criteria, CS Bugs | Change in Due date and QA Sign off Date restrictions | Better Estimations & Epic Breakdown | Partial or missing details on Jira Trackers Description | My role involves process improvement and enablement (EM's, SM's & Other folks responsible for process streamlining) |  | YES | na
2024-09-24 11:25 | Mohammed Fayaz | QA | Skywalker | Yes | 10% or below | Yes | Yes | Balanced | 4 | 4 | 4 | 3 | Partially/Incomplete | 4 | 4 | Individual | 4 | 4 | Yes | 4 | Moderately | Moderate | Less than 10% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Average | Monitoring and Controlling Progress | Sprint Planning | KT and recording repository | Strict Bug SLA's | None | Ad-hoc Tasks & improper prioritisation | Less than 5% |  | YES | no
2024-09-24 11:37 | Mujtaba Ahmad | Dev | Enigma | Yes | 20% to 30% | Yes | Yes | Well Managed | 5 | 5 | 5 | 5 | Yes | 5 | 5 | Individual | 5 | 5 | Yes | 5 | YES | Moderate | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Epic Breakdown | Sprint DSU's | CI/CD, Testing & Continuous planning | Blocking Scope change | Effective communication | PR Merges | More Than 5% but less than 10% |  | YES | Code tasks which do not have any deployment dependency should be accessible for the developer to move to closure.
2024-09-24 11:37 | Mohammed Fayaz | QA | Enigma | Yes | 10% to 20% | Yes | Yes | Balanced | 4 | 5 | 5 | 5 | Yes | 4 | 4 | Individual | 5 | 4 | Yes | 4 | YES | Moderate | 10% to 20% | Yes | Multiple | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Continuous Epic Grooming | Sprint Retrospective | Ad-hoc requests prioritisation and acceptance | Change in Due date and QA Sign off Date restrictions | Sprint Planning Structure | Ad-hoc Tasks & improper prioritisation | More Than 5% but less than 10% | PM demo's can be conducted for FRD walkthrough | YES | PM demo's can be conducted for FRD walkthrough
2024-09-24 11:39 | Jegadeesh Santhana Krishnan | Dev | Aurora | Yes | 20% to 30% | Yes | Yes | Well Managed | 3 | 5 | 5 | 5 | Yes | 5 | 3 | Individual | 5 | 2 | No |  | YES | Multiple | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Some Information but still need further details | Yes | Average | Continuous Epic Grooming | Sprint Planning | Intra Team Collaboration - Dependency linking on Jira by Individual owners | Risk call out during Weekly SoS | Better & transparent commitments | Intra team collaboration | Less than 5% |  | YES | No
2024-09-24 11:40 | Mujtaba Ahmad | Dev & Scrum Master | Chakra | Yes | 10% to 20% | No | Yes | Balanced | 5 | 5 | 5 | 5 | Partially/Incomplete | 5 | 5 | Scrum Team | 5 | 5 | Yes | 5 | YES | Moderate | Less than 10% | Yes | Moderate | Over Utilised (90% and Above) | Optimal information available | Yes | Well Managed | Monitoring and Controlling Progress | Sprint DSU's | Ad-hoc requests prioritisation and acceptance | Risk call out during Weekly SoS | Effective communication | Reviews | Less than 5% |  | YES | we need to find a way to automate package updates when ever needed..
2024-09-24 11:40 | Mohammed Fayaz | QA | Enigma | No |  |  | Yes | Balanced | 4 | 4 | 3 | 4 | Partially/Incomplete | 4 | 4 | Individual | 4 | 4 | Yes | 4 | Moderately | Moderate | 10% to 20% | No | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Monitoring and Controlling Progress | Sprint Closure/review | KT and recording repository | Blocking Scope change | Dependency management | Delayed Response on open Queries, need multiple followups | More Than 5% but less than 10% | NA | YES | NA
2024-09-24 11:40 | Mujtaba Ahmad | Dev | Enigma | Yes | 10% to 20% | Yes | Yes | Balanced | 5 | 5 | 3 | 5 | Yes | 4 | 4 | Scrum Team | 5 | 3 | Yes | 5 | YES | Moderate | Less than 10% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Committed Epic Prioritisation | Sprint Closure/review | Ad-hoc requests prioritisation and acceptance | Risk call out during Weekly SoS | Sprint Planning Structure | Ad-hoc Tasks & improper prioritisation | More Than 5% but less than 10% | no | YES | no
2024-09-24 11:41 | Mujtaba Ahmad | Dev | Enigma | Yes | Just started using AI, need time to quantify | Yes | Yes | Balanced | 4 | 4 | 4 | 4 | Yes | 4 | 4 | Scrum Team | 4 | 4 | Yes | 4 | Moderately | Moderate | Less than 10% | Yes | Moderate | Balanced (80% - 90%) | Some Information but still need further details | Yes | Average | Code Freeze Milestones and hardening phase | Sprint Planning | Non Release Activity Identification & capacity reserve | Blocking Scope change | Release Planning, Strategy & Schedule (Proper Checkpoint and dates on jira tickets) | Partial or missing details on Jira Trackers Description | More Than 5% but less than 10% |  | YES | No
2024-09-24 11:43 | Mohammed Fayaz | QA | Helios | Yes | 10% to 20% | Yes | Yes | Balanced | 4 | 4 | 4 | 5 | Yes | 5 | 4 | Scrum Team | 4 | 4 | Yes | 5 | YES | Moderate | 20% to 30% | Yes | Multiple | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Release Kick Off | Sprint Closure/review | Jira Details - Epic breakdown, DoD, Exit criteria, CS Bugs | Blocking Scope change | Better Estimations & Epic Breakdown | Modifications on Approved Tech designs | More Than 5% but less than 10% |  | YES | No
2024-09-24 11:44 | Jegadeesh Santhana Krishnan | Others | Individual Capacity, Not Associated with any particular team | Yes | 30% and Above | Yes | No
2024-09-24 11:44 | Mohammed Fayaz | QA | Echo | Yes | 30% and Above | Yes | No
2024-09-24 11:45 | Mujtaba Ahmad | Dev | Titans | Yes | 10% to 20% | Yes | Yes | Well Managed | 5 | 5 | 4 | 4 | Yes | 4 | 4 | Individual | 4 | 4 | Yes | 4 | YES | Moderate | 20% to 30% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Average | Committed Epic Prioritisation | Sprint Planning | Ad-hoc requests prioritisation and acceptance | Blocking Scope change | Better & transparent commitments | Reviews | Less than 5% |  | YES | n/a
2024-09-24 11:46 | Jegadeesh Santhana Krishnan | Dev | Skywalker | Yes | 10% to 20% | Yes | Yes | Balanced | 4 | 4 | 4 | 4 | Yes | 4 | 4 | Scrum Team | 4 | 4 | Yes | 4 | YES | Moderate | Less than 10% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Average | Code Freeze Milestones and hardening phase | Sprint Planning | Jira Details - Epic breakdown, DoD, Exit criteria, CS Bugs | Change in Due date and QA Sign off Date restrictions | Better Estimations & Epic Breakdown | Reviews | Less than 5% |  | YES | NA
2024-09-24 11:46 | Jegadeesh Santhana Krishnan | Dev | Chipmuks | Yes | 10% or below | Yes | Yes | Balanced | 4 | 4 | 5 | 5 | Yes | 4 | 4 | Scrum Team | 4 | 4 | Yes | 4 | YES | Moderate | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Some Information but still need further details | Yes | Well Managed | Continuous Epic Grooming | Sprint Closure/review | Ad-hoc requests prioritisation and acceptance | Blocking Scope change | Better Estimations & Epic Breakdown | Reviews | More Than 5% but less than 10% |  | YES | No
2024-09-24 11:48 | Mujtaba Ahmad | Dev | Falcon | Yes | 20% to 30% | Yes | Yes | Well Managed | 5 | 5 | 5 | 5 | Yes | 5 | 5 | Scrum Team | 4 | 4 | Yes | 5 | YES | Multiple | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Not aware of any such initiative. Though the release coordination among teams was better than previous releases among teams | Well Managed | Continuous Epic Grooming | Sprint Planning | Ad-hoc requests prioritisation and acceptance | Change in Due date and QA Sign off Date restrictions | Effective communication | Non Release Activities | More Than 5% but less than 10% |  | YES | NA
2024-09-24 11:54 | Mohammed Fayaz | QA | Tintin | Yes | 10% to 20% | No | Yes | Chaotic | 3 | 3 | 3 | 3 | Partially/Incomplete | 3 | 3 | Individual | 3 | 3 | No |  | Moderately | Moderate | 10% to 20% | No | Moderate | Over Utilised (90% and Above) | Some Information but still need further details | Yes | Average | Monitoring and Controlling Progress | Sprint Planning | Jira Details - Epic breakdown, DoD, Exit criteria, CS Bugs | Blocking Scope change | Better Estimations & Epic Breakdown | Ad-hoc Tasks & improper prioritisation | Less than 5% |  | YES | NA
2024-09-24 11:55 | Mujtaba Ahmad | Dev & Scrum Master | Falcon | Yes | 10% to 20% | Yes | Yes | Balanced | 4 | 5 | 5 | 5 | Yes | 4 | 4 | Scrum Team |  | 4 | Yes | 4 | YES | Moderate | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Some Information but still need further details | Yes | Average | Committed Epic Prioritisation | Sprint Planning | KT and recording repository | Blocking Scope change | Release Planning, Strategy & Schedule (Proper Checkpoint and dates on jira tickets) | Ad-hoc Tasks & improper prioritisation | More Than 5% but less than 10% |  | YES | Better epic breakdowns and sprint planning is necessary
2024-09-24 11:56 | Jegadeesh Santhana Krishnan | Dev | Skywalker | Yes | 10% to 20% | Yes | Yes | Well Managed | 5 | 5 | 5 | 5 | Yes | 4 | 5 | Scrum Team | 5 | 5 | No |  | YES | Multiple | Less than 10% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Epic Breakdown | Sprint Planning | Jira Details - Epic breakdown, DoD, Exit criteria, CS Bugs | Blocking Scope change | Better Estimations & Epic Breakdown | Ad-hoc Tasks & improper prioritisation | More Than 5% but less than 10% |  | YES | N/A
2024-09-24 11:59 | Jegadeesh Santhana Krishnan | Dev | Skywalker | Yes | 10% to 20% | No | Yes | Balanced | 4 | 4 | 4 | 4 | Partially/Incomplete | 4 | 3 | Individual | 5 | 5 | Yes | 4 | YES | Moderate | More than 30% | Yes | Moderate | Balanced (80% - 90%) | Some Information but still need further details | Yes | Average | Continuous Epic Grooming | Sprint Planning | Ad-hoc requests prioritisation and acceptance | Blocking Scope change | None | PR Merges | More Than 5% but less than 10% |  | YES | None
2024-09-24 12:00 | Mujtaba Ahmad | Dev | Enigma | Yes | 10% to 20% | Yes | Yes | Balanced | 4 | 4 | 4 | 4 | Yes | 4 | 4 | Scrum Team | 4 | 4 | Yes | 4 | YES | Multiple | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Continuous Epic Grooming | Sprint Planning | CI/CD, Testing & Continuous planning | Blocking Scope change | Effective communication | Delayed Response on open Queries, need multiple followups | More than 10% but Less than 20% |  | YES | No
2024-09-24 12:01 | Sandeep Kumar | Dev | Phi | Yes | 20% to 30% | Yes | Yes | Balanced | 4 | 4 | 5 | 4 | Yes | 4 | 4 | Scrum Team | 4 | 3 | Yes | 4 | YES | Moderate | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Average | Committed Epic Prioritisation | Sprint Planning | Backlog & CS bugs prioritisation | Change in Due date and QA Sign off Date restrictions | Release Planning, Strategy & Schedule (Proper Checkpoint and dates on jira tickets) | Improper Epic Breakdown & Estimations - Missing Sprint Backlog | My role involves process improvement and enablement (EM's, SM's & Other folks responsible for process streamlining) | NA | YES | NA
2024-09-24 12:07 | Mohammed Fayaz | QA | Chloris | Yes | 10% or below | Yes | Yes | Balanced | 4 | 4 | 4 | 4 | Partially/Incomplete | 4 | 3 | Individual | 4 | 3 | Yes | 3 | YES | Moderate | 10% to 20% | Yes | Moderate | Over Utilised (90% and Above) | Optimal information available | Yes | Average | Committed Epic Prioritisation | Sprint Closure/review | Intra Team Collaboration - Dependency linking on Jira by Individual owners | Change in Due date and QA Sign off Date restrictions | Release Planning, Strategy & Schedule (Proper Checkpoint and dates on jira tickets) | Delay in commitments from dependant team | More than 10% but Less than 20% |  | YES | Please focus on sprint closure activity and changes made in the code during hardening phase
2024-09-24 12:13 | Jegadeesh Santhana Krishnan | EM | Chipmuks | Yes | 10% to 20% | Yes | Yes | Well Managed | 5 | 5 | 5 | 5 | Yes | 5 | 5 | Scrum Team | 5 | 5 | Yes | 5 | YES | Moderate | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Some Information but still need further details | Yes | Well Managed | Code Freeze Milestones and hardening phase | Sprint Closure/review | Bugs Management & Deferring | Strict Bug SLA's | Better Estimations & Epic Breakdown | Non Release Activities | My role involves process improvement and enablement (EM's, SM's & Other folks responsible for process streamlining) |  | YES | NA
2024-09-24 12:18 | Jegadeesh Santhana Krishnan | Others | Dexter | Yes | Just started using AI, need time to quantify | No | No
2024-09-24 12:20 | Sandeep Kumar | Dev | Tranformers | Yes | 10% to 20% | No | Yes | Balanced | 3 | 3 | 4 | 4 | Yes | 3 | 2 | Individual | 4 | 3 | Yes | 4 | Moderately | Moderate | Less than 10% | No | Multiple | Over Utilised (90% and Above) | Some Information but still need further details | Not aware of any such initiative. Though the release coordination among teams was better than previous releases among teams | Average | Epic Breakdown | Sprint Planning | Jira Details - Epic breakdown, DoD, Exit criteria, CS Bugs | Blocking Scope change | Better Estimations & Epic Breakdown | PR Merges | More Than 5% but less than 10% |  | Not Efficiently | na
2024-09-24 12:23 | Jegadeesh Santhana Krishnan | Dev | Chipmuks | Yes | Just started using AI, need time to quantify | Yes | Yes | Balanced | 4 | 4 | 4 | 4 | Yes | 4 | 4 | Individual | 4 | 4 | Yes | 4 | YES | Moderate | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Some Information but still need further details | Yes | Average | Continuous Epic Grooming | Sprint Planning | KT and recording repository | Strict Bug SLA's | Release Planning, Strategy & Schedule (Proper Checkpoint and dates on jira tickets) | Improper Epic Breakdown & Estimations - Missing Sprint Backlog | Less than 5% | NA | YES | NA
2024-09-24 12:23 | Mohammed Fayaz | QA | Aurora | Yes | Just started using AI, need time to quantify | Yes | Yes | Balanced | 4 | 4 | 4 | 4 | Yes | 4 | 4 | Individual | 4 | 4 | Yes | 4 | YES | Multiple | Less than 10% | Yes | Moderate | Balanced (80% - 90%) | Some Information but still need further details | Not aware of any such initiative. Though the release coordination among teams was better than previous releases among teams | Average | Code Freeze Milestones and hardening phase | Sprint Planning | Non Release Activity Identification & capacity reserve | Change in Due date and QA Sign off Date restrictions | Better Estimations & Epic Breakdown | Delay in commitments from dependant team | Less than 5% |  | YES | No
2024-09-24 12:24 | Jegadeesh Santhana Krishnan | Dev & Scrum Master | Chipmuks | Yes | 10% to 20% | Yes | Yes | Well Managed | 3 | 5 | 5 | 5 | Yes | 5 | 5 | Scrum Team | 5 | 5 | Yes | 5 | YES | Moderate | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Monitoring and Controlling Progress | Sprint Closure/review | Ad-hoc requests prioritisation and acceptance | Blocking Scope change | Better Estimations & Epic Breakdown | Delayed Response on open Queries, need multiple followups | More Than 5% but less than 10% |  | YES | none
2024-09-24 12:27 | Jegadeesh Santhana Krishnan | Dev & Scrum Master | Echo | Yes | 10% to 20% | Yes | Yes | Chaotic | 4 | 4 | 4 | 4 | Yes | 4 | 4 | Individual | 4 | 1 | Yes | 5 | Moderately | Moderate | More than 30% | No | Multiple |  | Some Information but still need further details | Yes | Average | Epic Breakdown | Sprint DSU's | Ad-hoc requests prioritisation and acceptance | Risk call out during Weekly SoS | Release Planning, Strategy & Schedule (Proper Checkpoint and dates on jira tickets) | Improper Epic Breakdown & Estimations - Missing Sprint Backlog | More than 20% |  | YES | NA
2024-09-24 12:28 | Mohammed Fayaz | QA | Chipmuks | No |  |  | Yes | Balanced | 4 | 4 | 4 | 4 | Yes | 4 | 4 | Scrum Team | 5 | 5 | Yes | 4 | YES | Moderate | Less than 10% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Average | Committed Epic Prioritisation | Sprint DSU's | Jira Details - Epic breakdown, DoD, Exit criteria, CS Bugs | Blocking Scope change | Better Estimations & Epic Breakdown | Modifications on Approved Tech designs | Less than 5% | NA | YES | NA
2024-09-24 12:32 | Jegadeesh Santhana Krishnan | EM | Tintin | Yes | 10% or below | Yes | Yes | Well Managed | 4 | 5 | 5 | 5 | Yes | 5 | 5 | Scrum Team | 5 | 5 | Yes | 5 | YES | Moderate | 20% to 30% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Epic Breakdown | Sprint Planning | Jira Automation | Risk call out during Weekly SoS | Reduced over commit | Ad-hoc Tasks & improper prioritisation | My role involves process improvement and enablement (EM's, SM's & Other folks responsible for process streamlining) | Please reduce the size of this survey. | YES | Please reduce the size of this survey.
2024-09-24 12:38 | Sandeep Kumar | Dev | Phi | Yes | 10% or below | Yes | Yes | Balanced | 4 | 4 | 4 | 5 | Partially/Incomplete | 4 | 5 | Individual | 4 | 5 | Yes | 4 | NO | None | 10% to 20% | No | Multiple | Over Utilised (90% and Above) | Some Information but still need further details | Not aware of any such initiative. Though the release coordination among teams was better than previous releases among teams | Average | Monitoring and Controlling Progress | Sprint Planning | Ad-hoc requests prioritisation and acceptance | Blocking Scope change | Reduced over commit | Ad-hoc Tasks & improper prioritisation | More than 10% but Less than 20% | NA | YES | NA
2024-09-24 12:54 | Mohammed Fayaz | QA | Skywalker | Yes | 10% or below | Yes | Yes | Balanced | 4 | 4 | 5 | 5 | Yes | 4 | 4 | Individual | 5 | 3 | Yes | 4 | YES | Moderate | 10% to 20% | Yes | Multiple | Over Utilised (90% and Above) | Some Information but still need further details | Not aware of any such initiative. Though the release coordination among teams was better than previous releases among teams | Well Managed | Continuous Epic Grooming | Sprint Planning | Jira Details - Epic breakdown, DoD, Exit criteria, CS Bugs | Change in Due date and QA Sign off Date restrictions | Reduced over commit | Modifications on Approved Tech designs | More than 10% but Less than 20% |  | Not Efficiently | We should revisit and reconsider aggressive release timelines we set for releases
2024-09-24 12:56 | Jegadeesh Santhana Krishnan | Dev | Sharks | Yes | 30% and Above | Yes | Yes | Balanced | 5 | 5 | 5 | 5 | Yes | 4 | 5 | Individual | 5 | 5 | Yes | 4 | Moderately | Moderate | Less than 10% | Yes | Moderate | Balanced (80% - 90%) | Not at All | Yes | Well Managed | Continuous Epic Grooming | Sprint Planning | Intra Team Collaboration - Dependency linking on Jira by Individual owners | Blocking Scope change | Sprint Planning Structure | Ad-hoc Tasks & improper prioritisation | Less than 5% |  | YES | no
2024-09-24 13:16 | Mujtaba Ahmad | Dev | Indus | Yes | 30% and Above | Yes | Yes | Well Managed | 4 | 5 | 5 | 4 | Yes | 4 | 5 | Scrum Team | 5 | 5 | Yes | 5 | YES | Multiple | More than 30% | Yes | Multiple | Over Utilised (90% and Above) | Optimal information available | Yes | Well Managed | Code Freeze Milestones and hardening phase | Sprint Closure/review | KT and recording repository | Blocking Scope change | Effective communication | Ad-hoc Tasks & improper prioritisation | Less than 5% | N/A | YES | N/A
2024-09-24 13:56 | Mujtaba Ahmad | Dev & Scrum Master | Titans | Yes | Just started using AI, need time to quantify | Yes | Yes | Balanced | 5 | 5 | 5 | 5 | Yes | 5 | 5 | Scrum Team | 4 | 5 | Yes | 5 | YES | Moderate | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Average | Monitoring and Controlling Progress | Sprint Closure/review | CI/CD, Testing & Continuous planning | Blocking Scope change | Effective communication | Improper Epic Breakdown & Estimations - Missing Sprint Backlog | Less than 5% |  | YES | NA
2024-09-24 14:01 | Mohammed Fayaz | QA | Eirene | Yes | 10% or below | Yes | Yes | Balanced | 4 | 4 | 5 | 5 | Yes | 4 | 3 | Individual | 4 | 4 | Yes | 4 | YES | Moderate | Less than 10% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Epic Breakdown | Sprint Planning | Non Release Activity Identification & capacity reserve | Change in Due date and QA Sign off Date restrictions | Efficient Jira Usage (New Fields such as - Due date, QA Lead, QA Involvement, QA Signoff date) | Ad-hoc Tasks & improper prioritisation | Less than 5% |  | YES | NA
2024-09-24 14:03 | Mohammed Fayaz | QA | Stark | Yes | 10% to 20% | Yes | Yes | Balanced | 4 | 4 | 5 | 5 | Yes | 4 | 4 | Individual | 4 | 4 | Yes | 4 | YES | Multiple | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Some Information but still need further details | Yes | Well Managed | Committed Epic Prioritisation | Sprint Planning | Jira Details - Epic breakdown, DoD, Exit criteria, CS Bugs | Risk call out during Weekly SoS | Better Estimations & Epic Breakdown | Ad-hoc Tasks & improper prioritisation | Less than 5% | JIRA needs an update to check what all service dependency we have to verify asa part of any tracker | YES | NA
2024-09-24 14:17 | Jegadeesh Santhana Krishnan | Dev | Skywalker | No |  |  | No
2024-09-24 15:14 | Jegadeesh Santhana Krishnan | Dev | Tintin | Yes | 10% to 20% | Yes | Yes | Balanced |  |  |  |  | Yes |  |  | Individual |  |  | Yes | 4 | YES | Moderate | Less than 10% | Yes |  |  | Some Information but still need further details | Yes |  | Continuous Epic Grooming | Sprint Planning | Ad-hoc requests prioritisation and acceptance | Blocking Scope change | Effective communication | Ad-hoc Tasks & improper prioritisation | Less than 5% |  | YES | -
2024-09-24 15:31 | Sandeep Kumar | Dev | Phi | Yes | 20% to 30% | Yes | Yes | Balanced | 3 | 3 | 3 | 3 | Yes | 3 | 3 | Individual | 3 | 3 | Yes | 3 | Moderately | Moderate | 20% to 30% | No | Moderate | Balanced (80% - 90%) | Some Information but still need further details | Not aware and did not find any significant change in the release coordination among teams | Well Managed | Code Freeze Milestones and hardening phase | Sprint Planning | Jira Automation | Change in Due date and QA Sign off Date restrictions | Risk call out (Release Confluence Page) | CS Bugs higher than the reserved Capacity | More than 10% but Less than 20% |  | YES | Better communication with the PM team regarding deliverables
2024-09-24 15:46 | Jegadeesh Santhana Krishnan | Dev & Scrum Master | Skywalker | Yes | 10% or below | Yes | Yes | Balanced | 3 | 4 | 4 | 4 | Yes | 4 | 3 | Individual | 5 | 4 | Yes | 3 | YES | Multiple | 10% to 20% | Yes | Multiple | Balanced (80% - 90%) | Optimal information available | Yes | Average | Monitoring and Controlling Progress | Sprint DSU's | KT and recording repository | Blocking Scope change | Release Planning, Strategy & Schedule (Proper Checkpoint and dates on jira tickets) | Non Release Activities | More than 10% but Less than 20% | Should have separate tracking for performance | YES | None
2024-09-24 16:09 | Jegadeesh Santhana Krishnan | Dev | Skywalker | Yes | 10% to 20% | Yes | Yes | Balanced | 3 | 3 | 3 | 4 | Yes | 3 | 2 | Individual | 4 | 3 | Yes | 4 | YES | Moderate | 10% to 20% | Yes | Moderate | Over Utilised (90% and Above) | Optimal information available | Not aware of any such initiative. Though the release coordination among teams was better than previous releases among teams | Well Managed | Continuous Epic Grooming | Sprint Retrospective | Non Release Activity Identification & capacity reserve | Blocking Scope change | None | CS Bugs higher than the reserved Capacity | Less than 5% |  | YES | -
2024-09-24 16:18 | Jegadeesh Santhana Krishnan | Dev | Hercules | Yes | 10% to 20% | Yes | No
2024-09-24 17:38 | Sandeep Kumar | Dev | Gryffindor | Yes | 10% to 20% | Yes | Yes | Chaotic | 3 | 4 | 4 | 4 | Partially/Incomplete | 4 | 4 | Scrum Team | 4 |  | Yes | 4 | Moderately | Multiple | 10% to 20% | Yes | Multiple | Balanced (80% - 90%) | Optimal information available | No | Average | Committed Epic Prioritisation | Sprint Closure/review | Ad-hoc requests prioritisation and acceptance | Risk call out during Weekly SoS | Sprint Planning Structure | Improper Epic Breakdown & Estimations - Missing Sprint Backlog | Less than 5% |  | Not Efficiently | NA
2024-09-24 18:32 | Mujtaba Ahmad | Dev | Titans | Yes | 10% or below | Yes | Yes | Balanced | 4 | 5 | 5 | 5 | Yes | 4 | 4 | Scrum Team | 5 | 5 | Yes | 5 | YES | Moderate | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Average | Epic Breakdown | Sprint Planning | Jira Details - Epic breakdown, DoD, Exit criteria, CS Bugs | Blocking Scope change | None | Improper Epic Breakdown & Estimations - Missing Sprint Backlog | Less than 5% |  | YES | Big epics that are subdivided into smaller epics have some issues with dependency management, which can be improved.
2024-09-24 22:37 | Jegadeesh Santhana Krishnan | EM | Individual Capacity, Not Associated with any particular team | No |  |  | Yes | Well Managed | 5 | 5 | 5 | 5 | Yes | 5 | 5 | Individual | 5 | 5 | Yes | 5 | YES | Multiple | Less than 10% | Yes | None | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Epic Breakdown | Sprint Retrospective | Intra Team Collaboration - Dependency linking on Jira by Individual owners | Blocking Scope change | None | Improper Epic Breakdown & Estimations - Missing Sprint Backlog | My role involves process improvement and enablement (EM's, SM's & Other folks responsible for process streamlining) |  | YES | NO
2024-09-25 09:31 | Jegadeesh Santhana Krishnan | Dev & Scrum Master | Aurora | Yes | 10% to 20% | Yes | No
2024-09-25 10:07 | Jegadeesh Santhana Krishnan | Dev | Eirene | Yes | 10% or below | Yes | No
2024-09-25 10:16 | Mohammed Fayaz | QA | Helios | Yes | 10% to 20% | Yes | Yes | Balanced | 4 | 5 | 5 | 5 | Partially/Incomplete | 3 | 4 | Individual | 4 | 4 | Yes | 4 | Moderately | Moderate | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Some Information but still need further details | Yes | Average | Epic Breakdown | Sprint Planning | Jira Details - Epic breakdown, DoD, Exit criteria, CS Bugs | Risk call out during Weekly SoS | Reduced over commit | Improper Epic Breakdown & Estimations - Missing Sprint Backlog | Less than 5% | None | YES | None
2024-09-25 10:19 | Mujtaba Ahmad | Dev | Apollo | Yes | 10% to 20% | Yes | Yes | Chaotic | 3 | 4 | 4 | 4 | Yes | 4 | 4 | Individual | 4 | 3 | Yes | 3 | YES | Moderate | Less than 10% | No | Multiple | Over Utilised (90% and Above) | Optimal information available | Yes | Well Managed | Monitoring and Controlling Progress | Sprint Retrospective | Ad-hoc requests prioritisation and acceptance | Blocking Scope change | Efficient Jira Usage (New Fields such as - Due date, QA Lead, QA Involvement, QA Signoff date) | Ad-hoc Tasks & improper prioritisation | Less than 5% |  | YES | Better management of adhoc requests and adhoc discussions
2024-09-25 10:52 | Jegadeesh Santhana Krishnan | Dev | Chloris | Yes | 10% or below | Yes | Yes | Chaotic | 4 | 2 | 4 | 3 | Partially/Incomplete | 5 | 4 | Individual | 5 | 5 | Yes | 5 | YES | Moderate | Less than 10% | No | Multiple | Over Utilised (90% and Above) | Some Information but still need further details | Not aware of any such initiative. Though the release coordination among teams was better than previous releases among teams | Well Managed | Epic Breakdown | Sprint Planning | Non Release Activity Identification & capacity reserve | Blocking Scope change | Sprint Planning Structure | Ad-hoc Tasks & improper prioritisation | Less than 5% |  | YES | NA
2024-09-25 10:52 | Jegadeesh Santhana Krishnan | Dev | Helios | Yes | 10% to 20% | Yes | Yes | Well Managed | 5 | 4 | 4 | 5 | Yes | 5 | 5 | Individual | 5 | 4 | Yes | 5 | YES | Multiple | Less than 10% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Continuous Epic Grooming | Sprint Retrospective | CI/CD, Testing & Continuous planning | Blocking Scope change | Release Planning, Strategy & Schedule (Proper Checkpoint and dates on jira tickets) | Modifications on Approved Tech designs | More Than 5% but less than 10% |  | YES | no
2024-09-25 10:53 | Jegadeesh Santhana Krishnan | Dev | Iris | Yes | 10% or below | Yes | Yes | Well Managed | 4 | 4 | 4 | 4 | Yes | 4 | 4 | Individual | 4 | 4 | Yes | 4 | YES | Moderate | Less than 10% | Yes | None | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Continuous Epic Grooming | Sprint Retrospective | Ad-hoc requests prioritisation and acceptance | Risk call out during Weekly SoS | Risk call out (Release Confluence Page) | Delay in commitments from dependant team | Less than 5% |  | YES | no. but avoid large retro forms
2024-09-25 10:58 | Jegadeesh Santhana Krishnan | Dev & Scrum Master | Helios | Yes | 10% to 20% | Yes | Yes | Balanced | 4 | 4 | 4 | 4 | Yes | 5 | 4 | Individual | 4 | 4 | Yes | 4 | YES | Multiple | 20% to 30% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Continuous Epic Grooming | Sprint Closure/review | Intra Team Collaboration - Dependency linking on Jira by Individual owners | Blocking Scope change | None | PR Merges | More Than 5% but less than 10% |  | YES | NA
2024-09-25 11:05 | Mujtaba Ahmad | Dev | Falcon | Yes | 10% to 20% | Yes | No
2024-09-25 11:09 | Mujtaba Ahmad | Dev | Falcon | Yes | 20% to 30% | Yes | Yes | Balanced | 4 | 4 | 4 | 4 | Partially/Incomplete | 4 | 4 | Scrum Team | 4 | 4 | Yes | 3 | Moderately | Multiple | 10% to 20% | Yes | Moderate | Over Utilised (90% and Above) | Some Information but still need further details | Not aware of any such initiative. Though the release coordination among teams was better than previous releases among teams | Average | Committed Epic Prioritisation | Sprint Planning | CI/CD, Testing & Continuous planning | Change in Due date and QA Sign off Date restrictions | Better & transparent commitments | Improper Epic Breakdown & Estimations - Missing Sprint Backlog | More Than 5% but less than 10% |  | YES | NA
2024-09-25 11:21 | Mujtaba Ahmad | Dev | Apollo | Yes | 10% to 20% | Yes | Yes | Balanced | 4 | 5 | 4 | 4 | Yes | 4 | 4 | Scrum Team | 3 | 3 | Yes | 3 | YES | Multiple | Less than 10% | Yes | Moderate | Over Utilised (90% and Above) | Some Information but still need further details | Yes | Average | Monitoring and Controlling Progress | Sprint Planning | Bugs Management & Deferring | Risk call out during Weekly SoS | Release Planning, Strategy & Schedule (Proper Checkpoint and dates on jira tickets) | Delayed Response on open Queries, need multiple followups | Less than 5% |  | YES | no
2024-09-25 11:30 | Mohammed Fayaz | EM | Platform Teams | Yes | 10% to 20% | Yes | No
2024-09-25 11:31 | Mohammed Fayaz | QA | Indus | Yes | 10% or below | Yes | Yes | Well Managed | 5 | 5 | 5 | 5 | Yes | 5 | 5 | Scrum Team | 5 | 5 | Yes | 5 | YES | Moderate | Less than 10% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Committed Epic Prioritisation | Sprint Planning | Jira Details - Epic breakdown, DoD, Exit criteria, CS Bugs | Change in Due date and QA Sign off Date restrictions | Better Estimations & Epic Breakdown | Delayed Response on open Queries, need multiple followups | More Than 5% but less than 10% |  | YES | No
2024-09-25 11:46 | Jegadeesh Santhana Krishnan | Dev | Aurora | Yes | 20% to 30% | Yes | Yes | Balanced | 4 | 4 | 5 | 5 | Yes | 5 | 4 | Individual | 4 | 4 | Yes | 4 | YES | Multiple | Less than 10% | Yes | None | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Epic Breakdown | Sprint Closure/review | Intra Team Collaboration - Dependency linking on Jira by Individual owners | Strict Bug SLA's | Better & transparent commitments | Intra team collaboration | Less than 5% |  | YES | No other suggestions
2024-09-25 11:55 | Jegadeesh Santhana Krishnan | Dev | Chloris | Yes | 10% or below | Yes | Yes | Balanced | 5 | 5 | 5 | 5 | Yes | 5 | 5 | Individual | 5 | 4 | Yes | 4 | Moderately | Moderate | Less than 10% | Yes | None | Balanced (80% - 90%) | Optimal information available | Yes | Average | Epic Breakdown | Sprint Closure/review | KT and recording repository | Blocking Scope change | Release Planning, Strategy & Schedule (Proper Checkpoint and dates on jira tickets) | Modifications on Approved Tech designs | Less than 5% |  | YES | NA
2024-09-25 12:04 | Jegadeesh Santhana Krishnan | Dev | Iris | Yes | 20% to 30% | Yes | Yes | Balanced | 4 | 5 | 5 | 5 | Yes | 5 | 4 | Individual | 5 | 3 | Yes | 4 | YES | Moderate | Less than 10% | Yes | Moderate | Balanced (80% - 90%) | Some Information but still need further details | Not aware of any such initiative. Though the release coordination among teams was better than previous releases among teams | Well Managed | Committed Epic Prioritisation | Sprint Planning | Jira Details - Epic breakdown, DoD, Exit criteria, CS Bugs | Blocking Scope change | Release Planning, Strategy & Schedule (Proper Checkpoint and dates on jira tickets) | Delay in commitments from dependant team | Less than 5% |  | YES | No
2024-09-25 12:07 | Mujtaba Ahmad | EM | Enigma | Yes | Just started using AI, need time to quantify | Yes | Yes | Balanced | 4 | 5 | 5 | 5 | Partially/Incomplete | 4 | 4 | Scrum Team | 4 | 4 | Yes | 4 | YES | Multiple | Less than 10% | Yes | Moderate | Balanced (80% - 90%) | Some Information but still need further details | Yes | Well Managed | Continuous Epic Grooming | Sprint Planning | Jira Details - Epic breakdown, DoD, Exit criteria, CS Bugs | Blocking Scope change | Better Estimations & Epic Breakdown | Improper Epic Breakdown & Estimations - Missing Sprint Backlog | My role involves process improvement and enablement (EM's, SM's & Other folks responsible for process streamlining) |  | YES | NA
2024-09-25 12:10 | Mujtaba Ahmad | Dev | Titans | Yes | 10% to 20% | Yes | Yes | Balanced | 5 | 5 | 5 | 5 | Yes | 5 | 5 | Individual | 5 | 5 | Yes | 5 | YES | Moderate | 10% to 20% | Yes | Moderate | Over Utilised (90% and Above) | Optimal information available | Yes | Well Managed | Committed Epic Prioritisation | Sprint Planning | Ad-hoc requests prioritisation and acceptance | Risk call out during Weekly SoS | Better Estimations & Epic Breakdown | Ad-hoc Tasks & improper prioritisation | More Than 5% but less than 10% |  | YES | NA
2024-09-25 12:21 | Jegadeesh Santhana Krishnan | Dev | Aurora | Yes | 30% and Above | Yes | Yes | Well Managed | 5 | 5 | 5 | 5 | No | 5 | 5 | Scrum Team | 5 | 5 | No |  | YES | Multiple | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Code Freeze Milestones and hardening phase | Sprint Planning | KT and recording repository | Risk call out during Weekly SoS | Better Estimations & Epic Breakdown | Reviews | More than 20% |  | YES | nothing much
2024-09-25 12:38 | Jegadeesh Santhana Krishnan | Dev | Helios | Yes | 10% to 20% | Yes | Yes | Well Managed | 4 | 4 | 4 | 5 | Yes | 5 | 4 | Individual | 4 | 4 | Yes | 5 | YES | Moderate | Less than 10% | Yes | None | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Epic Breakdown | Sprint Planning | Bugs Management & Deferring | Risk call out during Weekly SoS | None | Delay in commitments from dependant team | More Than 5% but less than 10% |  | YES | NA
2024-09-25 12:51 | Jegadeesh Santhana Krishnan | EM | Chloris | No |  |  | Yes | Well Managed | 5 | 5 | 5 | 5 | Yes | 5 | 5 | Individual | 4 | 4 | Yes | 5 | YES | Moderate | Less than 10% | Yes | None | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Code Freeze Milestones and hardening phase | Sprint Closure/review | Jira Automation | Strict Bug SLA's | Better Estimations & Epic Breakdown | Delay in commitments from dependant team | My role involves process improvement and enablement (EM's, SM's & Other folks responsible for process streamlining) | Nothing | YES | Nothing
2024-09-25 13:04 | Jegadeesh Santhana Krishnan | Dev & Scrum Master | Iris | Yes | 20% to 30% | Yes | Yes | Well Managed | 5 | 5 | 5 | 5 | Yes | 5 | 5 | Individual | 5 | 5 | Yes | 5 | YES | Multiple | 20% to 30% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Monitoring and Controlling Progress | Sprint Closure/review | Intra Team Collaboration - Dependency linking on Jira by Individual owners | Change in Due date and QA Sign off Date restrictions | Dependency management | Intra team collaboration | My role involves process improvement and enablement (EM's, SM's & Other folks responsible for process streamlining) |  | YES | Nothing
2024-09-25 14:05 | Mujtaba Ahmad | EM | Stark | No |  |  | Yes | Balanced | 5 | 5 | 5 | 5 | Yes | 5 | 5 | Individual | 4 | 4 | Yes | 4 | YES | Moderate | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Code Freeze Milestones and hardening phase | Sprint Planning | Bugs Management & Deferring | Blocking Scope change | Effective communication | PR Merges | My role involves process improvement and enablement (EM's, SM's & Other folks responsible for process streamlining) |  | YES | We need better planning for backlog
2024-09-25 15:55 | Mujtaba Ahmad | Dev | Chakra | Yes | 10% or below | Yes | Yes | Balanced | 5 | 5 | 5 | 4 | Partially/Incomplete | 4 | 4 | Scrum Team | 4 | 4 | Yes | 4 | YES | Moderate | Less than 10% | Yes | Moderate | Over Utilised (90% and Above) | Some Information but still need further details | No | Average | Epic Breakdown | Sprint Planning | Test Design | Blocking Scope change | None | Non Release Activities | More Than 5% but less than 10% |  | YES | -
2024-09-25 16:01 | Mujtaba Ahmad | Dev | Titans | No |  |  | No
2024-09-25 21:48 | Mohammed Fayaz | EM | Individual Capacity, Not Associated with any particular team | Yes | 10% to 20% | Yes | Yes | Balanced | 4 | 5 | 5 | 5 | Partially/Incomplete | 5 | 3 | Scrum Team | 4 | 3 | Yes | 4 | YES | Multiple | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Some Information but still need further details | Yes | Well Managed | Code Freeze Milestones and hardening phase | Sprint Planning | CI/CD, Testing & Continuous planning | Risk call out during Weekly SoS | Effective communication | Missing SLA's for Bugs, Trackers on Jira | My role involves process improvement and enablement (EM's, SM's & Other folks responsible for process streamlining) |  | YES | Triaging bugs reported during the release testing on time by adhering to Bug SLAs.
2024-09-26 02:39 | Mujtaba Ahmad | Dev | Indus | Yes | 20% to 30% | Yes | Yes | Chaotic | 3 | 4 | 4 | 4 | Yes | 4 | 5 | Individual | 5 | 4 | Yes | 5 | YES | Moderate | 10% to 20% | Yes | None | Balanced (80% - 90%) | Optimal information available | Not aware of any such initiative. Though the release coordination among teams was better than previous releases among teams | Well Managed | Continuous Epic Grooming | Sprint Closure/review | KT and recording repository | Blocking Scope change | Sprint Planning Structure | Reviews | Less than 5% | no | YES | no
2024-09-26 09:52 | Jegadeesh Santhana Krishnan | Dev | Tintin | Yes | 20% to 30% | Yes | Yes | Balanced | 4 | 4 | 4 | 4 | Yes | 4 | 4 | Individual | 3 | 3 | No |  | NO | Moderate | 20% to 30% | No | Multiple | Over Utilised (90% and Above) | Some Information but still need further details | No | Average | Epic Breakdown | Sprint DSU's | Tech Design | Blocking Scope change | Effective communication | Ad-hoc Tasks & improper prioritisation | More Than 5% but less than 10% |  | YES | NA
2024-09-26 10:14 | Mohammed Fayaz | QA | Hercules | Yes | 10% or below | Yes | Yes | Balanced | 3 | 4 | 5 | 5 | Yes | 5 | 5 | Individual | 5 | 5 | Yes | 5 | Moderately | Moderate | 20% to 30% | Yes | Moderate | Balanced (80% - 90%) | Some Information but still need further details | Yes | Average | Monitoring and Controlling Progress | Sprint Closure/review | Ad-hoc requests prioritisation and acceptance | Blocking Scope change | None | Reviews | More than 10% but Less than 20% |  | YES | None
2024-09-26 10:27 | Mujtaba Ahmad | EM | Ganges | Yes | 10% to 20% | Yes | Yes | Well Managed | 4 | 5 | 5 | 5 | Yes | 5 | 5 | Scrum Team | 5 | 5 | Yes | 5 | YES | Moderate | Less than 10% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Code Freeze Milestones and hardening phase | Sprint DSU's | Jira Details - Epic breakdown, DoD, Exit criteria, CS Bugs | Change in Due date and QA Sign off Date restrictions | Release Planning, Strategy & Schedule (Proper Checkpoint and dates on jira tickets) | Improper Epic Breakdown & Estimations - Missing Sprint Backlog | My role involves process improvement and enablement (EM's, SM's & Other folks responsible for process streamlining) |  | YES | NO
2024-09-26 10:30 | Jegadeesh Santhana Krishnan | Dev & Scrum Master | Dexter | Yes | 10% or below | Yes | Yes | Balanced | 4 | 4 | 4 | 5 | Yes | 4 | 4 | Individual | 5 | 4 | Yes | 4 | YES | Moderate | Less than 10% | No | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Committed Epic Prioritisation | Sprint Planning | Non Release Activity Identification & capacity reserve | Change in Due date and QA Sign off Date restrictions | Sprint Planning Structure | Ad-hoc Tasks & improper prioritisation | My role involves process improvement and enablement (EM's, SM's & Other folks responsible for process streamlining) |  | YES | -
2024-09-26 10:44 | Mohammed Fayaz | QA | Titans | Yes | 10% or below | Yes | Yes | Balanced | 4 | 4 | 4 | 4 | Yes | 4 | 4 | Individual | 4 | 4 | Yes | 4 | YES | None | Less than 10% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Monitoring and Controlling Progress | Sprint Closure/review | Ad-hoc requests prioritisation and acceptance | Risk call out during Weekly SoS | Better Estimations & Epic Breakdown | Ad-hoc Tasks & improper prioritisation | Less than 5% |  | YES | NA