## Form Responses 1
Timestamp | You are part of which of the following directors org | Select reporting manager per Sage? | What's your primary role for the release? | Enter the Team/Scrum team that you are mostly associated with during the release. (Select Only One) Note: If associated with multiple teams, please select individual capacity | Sprint Retrospective Effectiveness | Were the action item from the Sprint retrospectives addressed during this release? | What was the action item and how was it resolved during the release? | Are you directly involved in the Release Deliverables for current release items or items planned and in progress for future releases? | How would you rate Release Overall (Individual Perspective) ? | How would you rate the release planning in comparison to previous release plannings? (1-Poor, 5- Improved) | How well were you as an individual aware of your teams commitments and scope of work prior to release implementation start ? (1-Not Aware, 5- Aware) | What was your involvement in Release planning and the selection of commitments? (1-Not Involved, 5- Fully Involved) | Were you as an individual aware of the Release timelines and your tasks in hand for the Release ? (1-Somewhat Aware, 5- Fully Aware) | Detailed Epic Breakdown with estimates and scrum team ownership were done for your trackers parent epic prior to Release Implementation Initiation. | How confident were you in terms of your teams commitments and deliverables? (1-Not Confident, 5- Full Confidence) | How would you rate effectiveness the Sprint Planning Meetings ? (1-Not Effective, 5- Effective) | Individual items efforts estimate for completion of the task is done by whom ? (Desired state is by scrum team) | How would you rate effectiveness of the Daily Standup connect to understand and analyse your tasks in hand ? (1-Not Effective, 5- Effective) | How would you rate effectiveness of the Sprint Closure / review meetings ? (1-Not Effective, 5- Effective) | Was Sprint retrospective Conducted for your Team at the end of each Sprint | Do you as an individual get sufficient opportunity to raise risk or concerns during agile ceremonies? | Do you get opportunity to learn new things in accordance to your role release over release? | What percentage of your capacity in the sprint was reserved for Items such as CS Support Bugs/Requests which cannot be estimated but as a team you reserve some bandwidth, as per history you are aware of such requests and your team reserves capacity for it ?(individual capacity reserved) | Is your reserved capacity for the Historical support activities such as CS Bugs/Support tickets and others, sufficient during the release. | How much Adhoc requests (Request for which no bandwidth was reserved during Release/Sprint Planning) were received post sprint planning. | How was your available capacity utilised during the Release i.e. your workload. (1-Under Utilisation, 5- Over Utilisation) | Do you have sufficient details available on Jira to successfully and independently complete your assigned tasks(details like description, acceptance criteria and timeline) | Was the Release Coordination Group initiated with representatives from each directors org, helpful and more efficient in managing the Release checkpoints and ensuring the key asks were routed better to the respective team/people? | How well were dependencies managed in the Release. | Check the Release Ceremony where there is need to spend more efforts to make the release more effective. | Check the Sprint Ceremony where there is need to spend more efforts to make the release more effective. | What is the top improvement area in the below list you would suggest to improve for a smoother release? | What do we need to improve in Release Implementation | Anything that you would like to call out which improved in this release as compared to the previous releases. | What is the most probable reason that deviates the planned timelines? | Applicable only for pure DEV or QA Resources - What percent of your available capacity is impacted by process changes and new processes enablement on regular tasks not the other cleanup activities from previous releases (Not Applicable to EM's, SM's & Other Folks responsible for process streamlining) | Any other thought you would like to share related to the releases. | In Your individual opinion are we considering the release Delivery Timelines and milestones while we are planning and delivering our assigned tasks | Do you have any suggestion for improving and streamlining the release further? | Any Suggestions for Jira enhancements? | What was your engagement area during this release while not associated with the release deliverables? | Would you prefer Cursor as your AI code companion ? | What types of tasks do you use Cursor, Copilot for ? (select all that apply) | How much Productivity boost have you experienced with Cursor ? | Share an interesting use case where Cursor helped you | Any feedback/suggestion on Cursor Usage ? | Are you getting all the support for AI adoption from various forums (Slack / email / Lunch n Learn series) ? Please highlight where the support can be further improved.
2025-09-18 15:42 | Jegadeesh Santhana Krishnan | Ramakrishna Grandhi | Dev | Avengers | 4 | No Action items | NA | No | [33 empty] | Yes | Dev Prototype, Exploring / understanding existing codebase, Writing code for new features, Debugging and Fixing Bugs, Writing Unit tests, Creating test cases or test scripts, Design brainstorming | 20% to 50% | Migration tooling for clickhouse | Its good | Yes
2025-09-18 15:46 | Diksha Khatri | SWATANTRA ROUT | Dev | Nexus | 5 | Yes | We raised some bugs and fixes are done in this release | No | [32 empty] | AutomatingTestcases and maintianing stability in the Suites | Yes | Writing code for new features, Review PRs, Debugging and Fixing Bugs, Creating test cases or test scripts | Greater than 50% | I helped to update the coupun code in like 30+tc in a single go | No | No
2025-09-18 15:47 | Diksha Khatri | SWATANTRA ROUT | Dev | Nexus | 5 | Yes | N/A | No | [33 empty] | Yes | Review PRs, Debugging and Fixing Bugs, Creating test cases or test scripts | 20% to 50% | In Generating the test script/skeleton cursor does this in 5-10 mins then after I only need to change the setting/payloads which save a lot of time. | Most of time cursor does unwanted changes which leads to another issues, now I have explicitly set user rule for cursor, what not to do. | Yes
2025-09-18 15:48 | Mohammed Fayaz | Prasad Deverakonda | QA | Tetris(E2E) | 5 | Yes | Action item on various things considered | Yes | Chaotic | 5 | 5 | 5 | 5 | Yes | 5 | 5 | Scrum Team | 5 | 5 | Yes | YES | Multiple | 20% to 30% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Release Kick Off | Sprint Closure/review | CI/CD, Testing & Continuous planning | Strict Bug SLA's | Better Estimations & Epic Breakdown | Missing SLA's for Bugs, Trackers on Jira | More Than 5% but less than 10% |  | YES | NA |  |  | Yes | Dev Prototype, Exploring / understanding existing codebase, Writing code for new features, Review PRs, Debugging and Fixing Bugs, Creating test cases or test scripts, Developing tools, utilities for team | 20% to 50% | Helped in cases to analyze prod issues from IO, IA and many such utilities and use cases for E2E team - its a good learning curve. Also useful in Historical Bug Pattern Analysis & Prevention Production Incident Response & Learning Snowflake Analytics Dashboard Analyze historical CS tickets (Oct-Dec, past years) to identify trends and prevent October ticket spikes and other deep analysis. | More process and standards should come up in company | Yes
2025-09-18 15:51 | Jegadeesh Santhana Krishnan | Selvakumar Thiyagarajan | EM |  |  |  |  | Yes | Well Managed | 5 | 5 | 5 | 5 | Yes | 5 | 5 | Scrum Team | 5 | 5 | Yes | YES | Multiple | Less than 10% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Continuous Epic Grooming | Sprint Planning | Intra Team Collaboration - Dependency linking on Jira by Individual owners | Change in Due date and QA Sign off Date restrictions | Release Planning, Strategy & Schedule (Proper Checkpoint and dates on jira tickets) | Intra team collaboration | My role involves process improvement and enablement (EM's, SM's & Other folks responsible for process streamlining) |  | YES | No |  |  | Yes | Exploring / understanding existing codebase | Greater than 50% | NA | NA | Yes
2025-09-18 15:52 | Diksha Khatri | Diksha Khatri | Dev | Astra | 5 | Yes | Proper description in jira with recreation steps | Yes | Balanced | 3 | 4 | 4 | 5 | Partially/Incomplete | 4 | 5 | Scrum Team | 4 | 4 | Yes | YES | Moderate | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Some Information but still need further details | Yes | Average | Epic Breakdown | Sprint Planning | Jira Details - Epic breakdown, DoD, Exit criteria, CS Bugs | Risk call out during Weekly SoS | Better & transparent commitments | Improper Epic Breakdown & Estimations - Missing Sprint Backlog | More Than 5% but less than 10% |  | YES | better epic breakdown and backlog grooming |  |  | Yes | Dev Prototype, Exploring / understanding existing codebase, Writing code for new features, Review PRs, Writing Unit tests, Creating test cases or test scripts | 20% to 50% | generating automation script going through the existing scripts and identifying similar patterns | NA | yes
2025-09-18 15:52 | Jegadeesh Santhana Krishnan | Selvakumar Thiyagarajan | Dev & Scrum Master | Chloris | 5 | No Action items | NIL | Yes | Well Managed | 5 | 5 | 5 | 5 | Yes | 5 | 5 | Individual | 5 | 5 | Yes | YES | Multiple | Less than 10% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Continuous Epic Grooming | Sprint Planning | CI/CD, Testing & Continuous planning | Blocking Scope change | Better Estimations & Epic Breakdown | Delay in commitments from dependant team | My role involves process improvement and enablement (EM's, SM's & Other folks responsible for process streamlining) |  | YES | NO |  |  | Yes | Dev Prototype, Exploring / understanding existing codebase, Writing code for new features, Review PRs, Debugging and Fixing Bugs, Writing Unit tests | 20% to 50% | cursor has helped in figuring out which part of the code base will be impacted by a figma | NO | yes
2025-09-18 15:53 | Jegadeesh Santhana Krishnan | Chandra Sekhar Kusupati | Dev & Scrum Master | Eirene | 4 | No Action items | na | Yes | Balanced | 4 | 4 | 4 | 4 | Yes | 4 | 4 | Scrum Team | 4 | 4 | Yes | YES | Moderate | Less than 10% | Yes | None | Balanced (80% - 90%) | Some Information but still need further details | Yes | Average | Continuous Epic Grooming | Sprint Planning | Jira Details - Epic breakdown, DoD, Exit criteria, CS Bugs | Blocking Scope change | Better Estimations & Epic Breakdown | Communication gap b/w dependent teams | My role involves process improvement and enablement (EM's, SM's & Other folks responsible for process streamlining) |  | YES | na |  |  | Yes | Dev Prototype, Exploring / understanding existing codebase, Review PRs, Writing Unit tests | 20% to 50% | na | na | yes
2025-09-18 15:59 | Jegadeesh Santhana Krishnan | Jegadeesh Santhana Krishnan | EM |  |  |  |  | Yes | Chaotic | 5 | 5 | 4 | 5 | Yes | 5 | 5 | Scrum Team | 5 | 5 | Yes | YES | Moderate | 10% to 20% | Yes | Multiple | Over Utilised (90% and Above) | Some Information but still need further details | Yes | Well Managed | Code Freeze Milestones and hardening phase | Sprint Closure/review | CI/CD, Testing & Continuous planning | Change in Due date and QA Sign off Date restrictions | Better & transparent commitments | Ad-hoc Tasks & improper prioritisation | My role involves process improvement and enablement (EM's, SM's & Other folks responsible for process streamlining) |  | YES | Cross team and cross functional collaboration can be better |  |  | Yes | Dev Prototype, | Less than 10% | creating tech debt epics | nonw | Slef
2025-09-18 16:00 | Mujtaba Ahmad | Raman Soni | Dev | Ganges | 5 | Yes | unittests were made priority than component tests in this release which lead to less number of bugs. If there were any, they were caught during implementation only because of good coverage of unit tests | Yes | Chaotic | 1 | 2 | 1 | 5 | Partially/Incomplete | 5 | 3 | Scrum Team | 5 | 5 | Yes | Moderately | None | Less than 10% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Average | Continuous Epic Grooming | Sprint Planning | Ad-hoc requests prioritisation and acceptance | Risk call out during Weekly SoS | None | Reviews | Less than 5% |  | YES | Resolve integrator-common-util intermittent issues or atleast document the fixes for those issues so that every one can refer. That is becoming a blocker of everyone | no |  | Yes | Exploring / understanding existing codebase, Writing code for new features, Writing Unit tests | Greater than 50% | Handlebars complete epic was implemented by cursor with no major bugs along with unit tests. | it is able to explain existing code, implement new features when design doc is provided | yes
2025-09-18 16:01 | Mohammed Fayaz | Anusha Jharupula | QA | Indus | 5 | Yes | Having slack reported issues ownership on rotational basis along with dev at sprint level | Yes | Balanced | 4 | 4 | 4 | 4 | Yes | 4 | 4 | Scrum Team | 4 | 4 | Yes | YES | Moderate | Less than 10% | Yes | Moderate | Balanced (80% - 90%) | Some Information but still need further details | Yes | Average | Committed Epic Prioritisation | Sprint Planning | Jira Details - Epic breakdown, DoD, Exit criteria, CS Bugs | Risk call out during Weekly SoS | Efficient Jira Usage (New Fields such as - Due date, QA Lead, QA Involvement, QA Signoff date) | Improper Epic Breakdown & Estimations - Missing Sprint Backlog | Less than 5% | na | YES | na | na |  | Yes | Exploring / understanding existing codebase, Writing code for new features, Review PRs, Debugging and Fixing Bugs | 20% to 50% | Recent on aws sdk upgrade v3, able to identify few areas with commit ID from the PR's and prepared test strategy and they were few missed areas as well | Better prompting will provide us good usage | yes
2025-09-18 16:04 | Jegadeesh Santhana Krishnan | Ankur Sachdeva | Dev & Scrum Master | Echo | 5 | No Action items | NA | Yes | Balanced | 4 | 5 | 5 | 5 | Yes | 5 | 5 | Scrum Team | 5 | 5 | Yes | YES | Multiple | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Code Freeze Milestones and hardening phase | Sprint Planning | Ad-hoc requests prioritisation and acceptance | Risk call out during Weekly SoS | Effective communication | Ad-hoc Tasks & improper prioritisation | More Than 5% but less than 10% |  | YES | no |  |  | Yes | Exploring / understanding existing codebase, Writing Unit tests, Creating test cases or test scripts | 20% to 50% | very very useful for Exploring / understanding existing codebase | no | yes
2025-09-18 16:07 | Diksha Khatri | Prasad Deverakonda | QA | Individual Capacity, Not Associated with any particular team | 5 | Yes | we have picked the previously raised bugs and solved them, perform regression before the relese timeline successfully | Yes | Balanced | 5 | 5 | 5 | 5 | Yes | 4 | 4 | Scrum Team | 4 | 4 | Yes | Moderately | Moderate | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Some Information but still need further details | Yes | Well Managed | Continuous Epic Grooming | Sprint Planning | Jira Details - Epic breakdown, DoD, Exit criteria, CS Bugs | Change in Due date and QA Sign off Date restrictions | None | Improper Epic Breakdown & Estimations - Missing Sprint Backlog | Less than 5% |  | YES | task and bandwidth allocation |  |  | Yes | Exploring / understanding existing codebase | 20% to 50% | understanding the project and writing the similar test cases | its good for doing work in speed it saves alot of time | yes
2025-09-18 16:09 | Jegadeesh Santhana Krishnan | Ankur Sachdeva | Dev | Chipmuks | 4 | No Action items | No items | Yes | Well Managed | 5 | 5 | 5 | 5 | Partially/Incomplete | 5 | 4 | Individual | 5 | 4 | Yes | YES | Multiple | 20% to 30% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Continuous Epic Grooming | Sprint Planning | Bugs Management & Deferring | Blocking Scope change | Release Planning, Strategy & Schedule (Proper Checkpoint and dates on jira tickets) | Ad-hoc Tasks & improper prioritisation | Less than 5% |  | YES | - |  |  | Yes | Dev Prototype, Exploring / understanding existing codebase, Writing code for new features, Debugging and Fixing Bugs, Writing Unit tests | 20% to 50% | Analysing bugs | - | Yes
2025-09-18 16:12 | Mohammed Fayaz | Anusha Jharupula | QA | Titans | 5 | No Action items | NA | Yes | Well Managed | 5 | 5 | 5 | 5 | Yes | 5 | 5 | Scrum Team | 5 | 5 | Yes | YES | Moderate | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Code Freeze Milestones and hardening phase | Sprint Retrospective | Ad-hoc requests prioritisation and acceptance | Risk call out during Weekly SoS | None | Ad-hoc Tasks & improper prioritisation | Less than 5% |  | YES | NA |  |  | Yes | Exploring / understanding existing codebase, Review PRs, Creating test cases or test scripts | Greater than 50% | Test case creation while validating fixes, Cursor assisted me by suggesting edge cases I might miss, which improved the overall coverage of my testing. | Having AI suggest test scenarios based on recent commits or requirements would make it even more useful | yes
2025-09-18 16:17 | Jegadeesh Santhana Krishnan | Chandra Sekhar Kusupati | Dev | Hercules | 5 | No Action items | NA | Yes | Well Managed | 5 | 5 | 5 | 5 | Yes | 5 | 5 | Scrum Team | 5 | 5 | Yes | YES | Moderate | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Committed Epic Prioritisation | Sprint DSU's | Jira Details - Epic breakdown, DoD, Exit criteria, CS Bugs | Strict Bug SLA's | Better & transparent commitments | Ad-hoc Tasks & improper prioritisation | Less than 5% |  | YES | no | no |  | Yes | Exploring / understanding existing codebase, Writing code for new features, Review PRs, Debugging and Fixing Bugs, Writing Unit tests, Creating test cases or test scripts | 20% to 50% | writing new features from scratch | it helps a lot while trying to implement feature from figma and also in validating after implementation | yes
2025-09-18 16:29 | Jegadeesh Santhana Krishnan | Anusha Badveeti | Dev | Minions | 5 | No Action items | Need to have some buffer points in order to avoid last minute timeline pressure. | Yes | Balanced | 4 | 5 | 5 | 5 | Yes | 4 | 4 | Scrum Team | 5 | 5 | Yes | YES | Multiple | 10% to 20% | Yes | Moderate | Over Utilised (90% and Above) | Optimal information available | Not aware of any such initiative. Though the release coordination among teams was better than previous releases among teams | Well Managed | Monitoring and Controlling Progress | Sprint Planning | Tech Design | Blocking Scope change | Effective communication | Improper Epic Breakdown & Estimations - Missing Sprint Backlog | More Than 5% but less than 10% |  | YES | NA |  |  | Yes | Exploring / understanding existing codebase, Writing code for new features, Debugging and Fixing Bugs, Writing Unit tests, Creating test cases or test scripts | 20% to 50% | Cursor helped in validating all the edge case coverage in the new user signup feature. | NA | YES
2025-09-18 16:29 | Jegadeesh Santhana Krishnan | Rajesh Subramani | Dev & Scrum Master | Hercules | 3 | No Action items | N/A | Yes | Balanced | 4 | 4 | 5 | 5 | Yes | 4 | 4 | Scrum Team | 4 | 3 | Yes | YES | Moderate | Less than 10% | Yes | None | Balanced (80% - 90%) | Optimal information available | Yes | Average | Monitoring and Controlling Progress | Sprint Closure/review | CI/CD, Testing & Continuous planning | Strict Bug SLA's | Release Planning, Strategy & Schedule (Proper Checkpoint and dates on jira tickets) | Delayed Test Designs | My role involves process improvement and enablement (EM's, SM's & Other folks responsible for process streamlining) |  | YES | N/A |  |  | Yes | Dev Prototype, Writing code for new features, Debugging and Fixing Bugs, Writing Unit tests | 20% to 50% | One use case involved adding keyboard navigation to a menu, where a menu item can serve as a parent to other menus. Since the menu item does not support internal keyboard navigation, the cursor implemented this logic in the component. Another use case involved using the cursor to apply the exact required styling to a component based on the provided Figma design. | N/A | Email
2025-09-18 16:40 | Mohammed Fayaz | Prasad Deverakonda | QA | Tetris(E2E) | 4 | Yes | good | No | [33 empty] | Yes | Exploring / understanding existing codebase, Writing code for new features, Debugging and Fixing Bugs, Writing Unit tests, Creating test cases or test scripts | 20% to 50% | Cursor turns messy bug reports into rock-solid, automated guardrails—auto-generating reproducible tests, smart fixes, and CI wiring—so QA becomes fast, reliable, and nearly unbreakable. | Good | yes
2025-09-18 16:40 | Mohammed Fayaz | Prasad Deverakonda | QA | Tetris(E2E) | 5 | Yes | The E2E team successfully planned and executed release item testing once Scrum QA closed | Yes | Well Managed | 5 | 5 | 5 | 5 | Yes | 5 | 5 | Scrum Team | 5 | 5 | Yes | YES | Moderate | Less than 10% | Yes | None | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Monitoring and Controlling Progress | Sprint Closure/review | Bugs Management & Deferring | Strict Bug SLA's | None | Missing SLA's for Bugs, Trackers on Jira | Less than 5% |  | YES | No |  |  | Yes | Exploring / understanding existing codebase, Creating test cases or test scripts | Greater than 50% | Increased test coverage across epic,Early detection of test gaps | No | Yes
2025-09-18 16:44 | Jegadeesh Santhana Krishnan | Rajesh Subramani | Dev | Helios | 5 | Yes | refraining from adding any more items, mid way sprint . | Yes | Balanced | 3 | 4 | 4 | 5 | Yes | 5 | 5 | Scrum Team | 5 | 5 | Yes | YES | Moderate | Less than 10% | Yes | None | Balanced (80% - 90%) | Some Information but still need further details | Not aware and did not find any significant change in the release coordination among teams | Well Managed | Monitoring and Controlling Progress | Sprint Planning | Intra Team Collaboration - Dependency linking on Jira by Individual owners | Risk call out during Weekly SoS | None | Delay in commitments from dependant team | More than 10% but Less than 20% | NA | YES | NA | NA |  | Yes | Dev Prototype, Exploring / understanding existing codebase, Writing code for new features, Review PRs, Debugging and Fixing Bugs, Writing Unit tests, Creating test cases or test scripts | 20% to 50% | I use cursor daily, and it is making every step of SDLC very interesting, amplifying all my output, if asked for ! | There should be a usage notifier, i we over use it or something, instead of going to dashboard to check it, there should be a notification that should come, saying if the usage is matching the code contribution and is being used properly , sort of reminder ! | Yes, thank you to the teams/individuals keeping this alive and fueling it.
2025-09-18 16:47 | Jegadeesh Santhana Krishnan | Ashok Kumar Dantham | Dev & Scrum Master | Aurora | 5 | No Action items | NA | Yes | Well Managed | 5 | 5 | 5 | 5 | Yes | 5 | 5 | Scrum Team | 5 | 5 | Yes | YES | Multiple | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Continuous Epic Grooming | Sprint Planning | Intra Team Collaboration - Dependency linking on Jira by Individual owners | Blocking Scope change | Better & transparent commitments | Delay in commitments from dependant team | More than 20% |  | YES | - |  |  | Yes | Writing code for new features, Review PRs, Writing Unit tests | Greater than 50% | New feature and unit testing | - | -
2025-09-18 16:49 | Mohammed Fayaz | Varun Batra | QA | Sharks | 5 | Yes | update jira details properly | Yes | Chaotic | 1 | 5 | 5 | 5 | Yes | 5 | 5 | Individual | 5 | 5 | Yes | YES | Moderate | Less than 10% | No | Moderate | Over Utilised (90% and Above) | Optimal information available | Yes | Average | Monitoring and Controlling Progress | Sprint DSU's | Non Release Activity Identification & capacity reserve | Change in Due date and QA Sign off Date restrictions | None | Ad-hoc Tasks & improper prioritisation | More than 20% | Ad-hoc requests prioritisation should be done in DSU. | YES | Managers should join DSU, Sprint work item should not be impact with ad-hoc request, Prioritization of Epic, bug and task should be driven through DSU only(post discussion) | NA |  | Yes | Exploring / understanding existing codebase, Writing code for new features, Debugging and Fixing Bugs | 20% to 50% | Fixing the automation failure | NA | Yes
2025-09-18 16:53 | Mohammed Fayaz | Prasad Deverakonda | QA | Astra | 5 | Yes | NA | Yes | Well Managed | 5 | 4 | 4 | 4 | Yes | 5 | 5 | Scrum Team | 5 | 5 | Yes | YES | Moderate | Less than 10% | Yes | None | Balanced (80% - 90%) | Optimal information available | Not aware of any such initiative. Though the release coordination among teams was better than previous releases among teams | Well Managed | Monitoring and Controlling Progress | Sprint Planning | Non Release Activity Identification & capacity reserve | Change in Due date and QA Sign off Date restrictions | None | Communication gap b/w dependent teams | Less than 5% | NA | YES | NA |  |  | Yes | Exploring / understanding existing codebase, Review PRs | 20% to 50% | Test Automation | NA | Yes
2025-09-18 16:56 | Mujtaba Ahmad | Raman Soni | Dev | Apollo | 4 | Yes | Improving on the burndown and burnup charts | Yes | Balanced | 5 | 5 | 5 | 5 | Yes | 4 | 4 | Scrum Team | 5 | 3 | Yes | YES | Moderate | Less than 10% | Yes | Moderate | Over Utilised (90% and Above) | Some Information but still need further details | Yes | Well Managed | Continuous Epic Grooming | Sprint Closure/review | CI/CD, Testing & Continuous planning | Blocking Scope change | Efficient Jira Usage (New Fields such as - Due date, QA Lead, QA Involvement, QA Signoff date) | Ad-hoc Tasks & improper prioritisation | Less than 5% |  | YES | NA | JIRA reposrts can be brought to the subtask level instead of story for efficient tracking |  | Yes | Dev Prototype, Exploring / understanding existing codebase, Review PRs, Writing Unit tests | 20% to 50% | Cursor helped in identifying a potential bugs, memory leaks, edge cases with much lesser time. | Cursor is a great tool with some caveats of over engineering for certain scenarios. I have seen multiple use cases where cursor's suggestions were not right. | Yes, we can have dedicated trainings or courses as well.
2025-09-18 16:58 | Mohammed Fayaz | Mohammed Fayaz | EM |  |  |  |  | Yes | Chaotic | 3 | 5 | 5 | 5 | Yes | 4 | 5 | Scrum Team | 5 | 5 | Yes | YES | Multiple | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Some Information but still need further details | Yes | Average | Code Freeze Milestones and hardening phase | Sprint Planning | Bugs Management & Deferring | Strict Bug SLA's | Dependency management | Missing SLA's for Bugs, Trackers on Jira | Less than 5% | We need to enforce a strict code freeze. | YES | Current Challenge: During deployments to IAQA and Staging, we are noticing multiple issues such as missed tags, incorrect tags being deployed, and in some cases FB branches still residing on IAQA and Staging while release testing is in progress. This creates repeated back-and-forth between Code Freeze → IAQA deployment → Staging deployment, leading to frequent misses and extensive follow-ups to bring things back on track. Need: To avoid these challenges, we require a more robust artifact management mechanism and a streamlined deployment process that ensures accuracy, consistency, and minimal manual intervention. Also, we need to have ownership to make sure the right tags are deployed on all environments that are used for release validation. | There are many fields in JIRA not in use. We should clean them up and make JIRA as source truth for all task, bugs ..etc |  | Yes | Exploring / understanding existing codebase, Review PRs, Creating test cases or test scripts, Understanding QA bugs and CS bugs from JIRA | 20% to 50% | Whenever there is a service alert, or escalation or regression bug, I will use the Cursor prompt (created a prompt) and get the complete history like Code analyis through PRs, pattern of the bug, how many times it appeared earlier, why it got missed..etc | NA | Yes
2025-09-18 17:10 | Mujtaba Ahmad | Raman Soni | Dev & Scrum Master | Apollo | 4 | Yes | Issue was on spiking burndown graphs, due to story points being added in sprint progress, we asked team to add estimates as much as possibe before sprint start, so that sudden spikes can be avoided. | Yes | Balanced | 4 | 5 | 4 | 4 | Yes | 4 | 4 | Scrum Team | 5 | 4 | Yes | YES | Multiple | 20% to 30% | No | Multiple | Balanced (80% - 90%) | Some Information but still need further details | Yes | Well Managed | Continuous Epic Grooming | Sprint Closure/review | Intra Team Collaboration - Dependency linking on Jira by Individual owners | Blocking Scope change | Release Planning, Strategy & Schedule (Proper Checkpoint and dates on jira tickets) | Ad-hoc Tasks & improper prioritisation | Less than 5% |  | YES | NA |  |  | Yes | Dev Prototype, Exploring / understanding existing codebase, Writing code for new features, Review PRs, Debugging and Fixing Bugs, Writing Unit tests, Creating test cases or test scripts, Discussion over multiple approaches while writing code | 20% to 50% | Helped me write EFS component changes, with good comparion of various Algorithms in discussion. | Cursor is good for Coding companion, it helps to understand code and suggest good code fixes along with corner case identiication. | Yes
2025-09-18 17:17 | Jegadeesh Santhana Krishnan | Ankur Sachdeva | Dev | Echo | 4 | No |  | Yes | Chaotic | 2 | 4 | 3 | 5 | Partially/Incomplete | 2 | 4 | Scrum Team | 5 | 5 | Yes | YES | None | Less than 10% | Yes | Moderate | Over Utilised (90% and Above) | Some Information but still need further details | Yes | Not Well | Monitoring and Controlling Progress | Sprint Planning | Intra Team Collaboration - Dependency linking on Jira by Individual owners | Risk call out during Weekly SoS | None | PR Merges | More Than 5% but less than 10% |  | YES | Stop overcommit. Manage dependencies better |  |  | Yes | Exploring / understanding existing codebase, Writing code for new features, Writing Unit tests, Creating test cases or test scripts | Less than 10% | Generating test-cases | cursorrules in all repos and using spec driven development | Yes
2025-09-18 17:19 | Diksha Khatri | SWATANTRA ROUT | Dev | Astra | 5 | Yes | The action items were regarding better documenting before automation warroom and it was resolved before the warroom II | Yes | Balanced | 5 | 4 | 5 | 4 | Yes | 5 | 4 | SME/Epic Owner/EM/QM (Pre Defined Efforts Estimates) | 5 | 3 | No | YES | Moderate | Less than 10% | No | None |  | Some Information but still need further details | Yes | Average | Continuous Epic Grooming | Sprint Closure/review | Jira Details - Epic breakdown, DoD, Exit criteria, CS Bugs | Risk call out during Weekly SoS | None | Intra team collaboration | More than 10% but Less than 20% |  | YES | NA |  |  | Yes | Writing code for new features, Review PRs, Debugging and Fixing Bugs, Writing Unit tests | 20% to 50% | It helped me in axios migration, and checking of few of the corrupt integrations tasks, where I was unable to find out some things about the update code and it helped me in doing those tasks | NA | Yes getting good support
2025-09-18 17:23 | Jegadeesh Santhana Krishnan | Rajesh Subramani | Dev | Hercules | 5 | Yes | Yes | Yes | Balanced | 4 | 4 | 4 | 4 | Yes | 5 | 4 | Scrum Team | 5 | 4 | No | YES | Moderate | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Some Information but still need further details | Yes | Average | Continuous Epic Grooming | Sprint Planning | Tech Design | Blocking Scope change | Release Planning, Strategy & Schedule (Proper Checkpoint and dates on jira tickets) | Ad-hoc Tasks & improper prioritisation | More Than 5% but less than 10% |  | YES | NA |  |  | Yes | Writing code for new features, Review PRs, Writing Unit tests, Creating test cases or test scripts | 20% to 50% | Unit test cases and mock data creating with different cases. | Great for boosting the productivity | Yes
2025-09-18 17:24 | Jegadeesh Santhana Krishnan | Jegadeesh Santhana Krishnan | Architect/Individual Contributors |  |  |  |  | No | [32 empty] | Ai in Engineering & Tech Debts Strategy | Yes | Writing code for new features, Review PRs, create jira descriptions | 20% to 50% | Jira creation: Tech debt item which required code traversal for creating details jira description | Its better on new projects and not accurate on existing projects | Yes
2025-09-18 17:24 | Jegadeesh Santhana Krishnan | Ankur Sachdeva | Dev | Echo | 4 | No Action items | NA | Yes | Balanced | 4 | 3 | 5 | 4 | Yes | 4 | 4 | Scrum Team | 4 | 3 | No | YES | Moderate | Less than 10% | No | Multiple | Balanced (80% - 90%) | Some Information but still need further details | Yes | Average | Committed Epic Prioritisation | Sprint Planning | Ad-hoc requests prioritisation and acceptance | Blocking Scope change | Efficient Jira Usage (New Fields such as - Due date, QA Lead, QA Involvement, QA Signoff date) | Ad-hoc Tasks & improper prioritisation | Less than 5% |  | YES | NA |  |  | Yes | Exploring / understanding existing codebase, Writing code for new features, Debugging and Fixing Bugs, Writing Unit tests, Creating test cases or test scripts | 20% to 50% | Helped in creating efficient test cases without mocking | Should give more info on which model to use for different tasks | Yes
2025-09-18 17:27 | Jegadeesh Santhana Krishnan | Chandra Sekhar Kusupati | Dev | Eirene | 3 | Yes | Implement proper tracking mechanism for dark mode migration and implementation | Yes | Balanced | 5 | 5 | 5 | 5 | Yes | 5 | 5 | Scrum Team | 4 | 4 | Yes | YES | Multiple | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Some Information but still need further details | Yes | Average | Code Freeze Milestones and hardening phase | Sprint Retrospective | Jira Details - Epic breakdown, DoD, Exit criteria, CS Bugs | Change in Due date and QA Sign off Date restrictions | Release Planning, Strategy & Schedule (Proper Checkpoint and dates on jira tickets) | Delayed Response on open Queries, need multiple followups | Less than 5% |  | YES | Reduce turn around time for queries |  |  | Yes | Dev Prototype, Exploring / understanding existing codebase, Writing code for new features, Review PRs, Debugging and Fixing Bugs, Writing Unit tests, Creating test cases or test scripts | Greater than 50% | Unit tests, fixing corner cases | Nil | Yes
2025-09-18 17:29 | Diksha Khatri | SWATANTRA ROUT | Dev & Scrum Master | Nexus | 5 | Yes | CReating smaller stories to easily close them before the closure of sprint, Getting unblocked in automating TCs by meeting with IOAUT | Yes | Balanced | 4 | 4 | 4 | 4 | Yes | 4 | 5 | Scrum Team | 5 | 4 | Yes | Moderately | Moderate | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Continuous Epic Grooming | Sprint Planning | Backlog & CS bugs prioritisation | Risk call out during Weekly SoS | Work allocation with sufficient capacity reserve | Ad-hoc Tasks & improper prioritisation | My role involves process improvement and enablement (EM's, SM's & Other folks responsible for process streamlining) |  | YES | NA | unable to track the SP that are getting spilled to next sprint but efforts kept in the current sprint, which is sometimes leads to scope change and unable to calculate the velocity per resource correctly |  | Yes | Exploring / understanding existing codebase, Writing code for new features, Review PRs, Debugging and Fixing Bugs, Writing Unit tests, Creating test cases or test scripts | 20% to 50% | Writing bug free code w.r.t automation | It should save prompts in the memory, which can be re-used | getting enough support through slack
2025-09-18 17:29 | Diksha Khatri | SWATANTRA ROUT | Dev & Scrum Master | Iota | 4 | Yes | Splunk monitoring, fb testing tag issues | Yes | Balanced | 4 | 4 | 4 | 3 | Yes | 4 | 4 | SME/Epic Owner/EM/QM (Pre Defined Efforts Estimates) | 4 | 4 | Yes | YES | Moderate | 10% to 20% | Yes | None | Balanced (80% - 90%) | Some Information but still need further details | No | Well Managed | Continuous Epic Grooming | Sprint Planning | Non Release Activity Identification & capacity reserve | Blocking Scope change | Better & transparent commitments | Modifications on Approved Tech designs | My role involves process improvement and enablement (EM's, SM's & Other folks responsible for process streamlining) |  | YES | NA |  |  | Yes | Writing code for new features, Debugging and Fixing Bugs, Writing Unit tests, | 20% to 50% | For writing better POCs | NA | Yes
2025-09-18 17:31 | Jegadeesh Santhana Krishnan | Chandra Sekhar Kusupati | Dev | Ganges | 5 | No Action items | Na | Yes | Balanced | 4 | 4 | 4 | 4 | Yes | 4 | 3 | Scrum Team | 4 | 4 | Yes | Moderately | Moderate | Less than 10% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Release Kick Off | Sprint Closure/review | Tech Design | Strict Bug SLA's | Better Estimations & Epic Breakdown | Intra team collaboration | My role involves process improvement and enablement (EM's, SM's & Other folks responsible for process streamlining) |  | YES | Na | Na |  | Yes | Dev Prototype, Writing Unit tests | 20% to 50% | Na | Na | Na
2025-09-18 17:34 | Diksha Khatri | Diksha Khatri | Dev & Scrum Master | Astra | 5 | Yes | Dedicated time for feature training and efficient SLA for review resolved the missing retro action item | Yes | Balanced | 4 | 4 | 5 | 5 | Yes |  | 4 | Scrum Team | 4 | 5 | Yes | YES | Moderate | 10% to 20% | Yes | Moderate | Over Utilised (90% and Above) | Some Information but still need further details | No | Average | Epic Breakdown | Sprint Closure/review | Ad-hoc requests prioritisation and acceptance | Strict Bug SLA's | Work allocation with sufficient capacity reserve | Partial or missing details on Jira Trackers Description | More Than 5% but less than 10% |  | YES | Need to reduce meeting frequencies |  |  | Yes | Exploring / understanding existing codebase, Writing code for new features, Review PRs, Debugging and Fixing Bugs | 20% to 50% | Fixing vulnerabilities across IAs and Analysis for Tech design to upgrade to Node 24 got done in a day rather than weeks manually. | Context and training are not retained , we need to use rules. | Yes
2025-09-18 17:36 | Jegadeesh Santhana Krishnan | Jegadeesh Santhana Krishnan | EM |  |  |  |  | Yes | Well Managed | 5 | 5 | 5 | 5 | Yes | 5 | 5 | Scrum Team | 4 | 5 | Yes | YES | Moderate | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Some Information but still need further details | Yes | Average | Code Freeze Milestones and hardening phase | Sprint DSU's | Intra Team Collaboration - Dependency linking on Jira by Individual owners | Change in Due date and QA Sign off Date restrictions | Better & transparent commitments | Delay in commitments from dependant team | My role involves process improvement and enablement (EM's, SM's & Other folks responsible for process streamlining) |  | YES | We need to ask the teams to follow strict timelines on deliverables |  |  | Yes | Review PRs | 20% to 50% | Helped me to analyse the code base | Not much | slack channel is really active and helpful
2025-09-18 17:36 | Mujtaba Ahmad | Hemant Agrawal | Dev | Enigma | 5 | Yes | Dividing bigger stories into Dev and QA separately to improve the sprint timely closure of tasks | Yes | Well Managed | 5 | 5 | 5 | 5 | Yes | 5 | 5 | Scrum Team | 5 | 5 | Yes | YES | Moderate | Less than 10% | Yes | None | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Code Freeze Milestones and hardening phase | Sprint Planning | Test Design | Change in Due date and QA Sign off Date restrictions | Release Planning, Strategy & Schedule (Proper Checkpoint and dates on jira tickets) | Non Release Activities | Less than 5% |  | YES |  |  |  | Yes | Dev Prototype, Exploring / understanding existing codebase, Writing code for new features, Review PRs, Debugging and Fixing Bugs, Writing Unit tests | 20% to 50% |  |  | Yes
2025-09-18 17:39 | Jegadeesh Santhana Krishnan | Rajesh Subramani | Dev | Hercules | 5 | Yes | We discussed about sprint grooming in time. We progressing on that. | No | [32 empty] | Development | Yes | Dev Prototype, Exploring / understanding existing codebase, Writing code for new features, Review PRs, Debugging and Fixing Bugs, Writing Unit tests, Creating test cases or test scripts | 20% to 50% | It help me identify potential bugs in PR. | It is helpful. Pls keep it. | Yes
2025-09-18 17:54 | Jegadeesh Santhana Krishnan | Selvakumar Thiyagarajan | Dev & Scrum Master | Pheonix | 4 | No Action items | NA | Yes | Balanced | 4 | 5 | 5 | 5 | Yes | 5 | 5 | Individual | 5 | 4 | Yes | YES | Moderate | Less than 10% | Yes | None | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Continuous Epic Grooming | Sprint Planning | Intra Team Collaboration - Dependency linking on Jira by Individual owners | Strict Bug SLA's | Efficient Jira Usage (New Fields such as - Due date, QA Lead, QA Involvement, QA Signoff date) | Delay in commitments from dependant team | My role involves process improvement and enablement (EM's, SM's & Other folks responsible for process streamlining) |  | YES | NA |  |  | Yes | Dev Prototype, Exploring / understanding existing codebase, Writing code for new features, Debugging and Fixing Bugs, Writing Unit tests, Creating test cases or test scripts | 20% to 50% | NA | NA | Yes
2025-09-18 18:17 | Diksha Khatri | Diksha Khatri | EM |  |  |  |  | No | [32 empty] | Delivery management, Backlog management, Reviewing FRD's | Yes | Exploring / understanding existing codebase, Debugging and Fixing Bugs, Creating Functionality doc by reviewing the code base | 20% to 50% | 1) It provided a TD for existing Shopify NS IA code, without the need to refer the KB acticle. 2) Identifying the API's 3) Basic configuration of setting up GIT branches. 4) Understanding a function | NA | Yes
2025-09-18 18:25 | Jegadeesh Santhana Krishnan | Anusha Badveeti | Dev | Tranformers | 5 | Yes | Long PR merging timelines were slightly addressed during this release | Yes | Well Managed | 5 | 5 | 4 | 5 | Yes | 5 | 5 | Scrum Team | 5 | 5 | Yes | YES | Moderate | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Not aware of any such initiative. Though the release coordination among teams was better than previous releases among teams | Well Managed | Continuous Epic Grooming | Sprint Planning | KT and recording repository | Risk call out during Weekly SoS | Sprint Planning Structure | Delayed Response on open Queries, need multiple followups | Less than 5% |  | YES | Enhanced buffer time for committed items to mitigate adhoc risks due to blockers |  |  | Yes | Dev Prototype, Exploring / understanding existing codebase, Writing code for new features, Debugging and Fixing Bugs, Writing Unit tests | 20% to 50% | Finding the logic that you might be looking for in the complex codebase. | NA | NA
2025-09-18 18:26 | Jegadeesh Santhana Krishnan | Rajesh Subramani | Dev | Hercules | 5 | No Action items | nil | Yes | Balanced | 5 | 5 | 4 | 5 | Yes | 5 | 5 | Scrum Team | 5 | 5 | Yes | YES | Moderate | Less than 10% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Continuous Epic Grooming | Sprint Planning | Jira Details - Epic breakdown, DoD, Exit criteria, CS Bugs | Blocking Scope change | Better & transparent commitments | Delayed Response on open Queries, need multiple followups | Less than 5% |  | YES | nil |  |  | Yes | Dev Prototype, Exploring / understanding existing codebase, Debugging and Fixing Bugs | 20% to 50% | - | - | -
2025-09-18 18:29 | Diksha Khatri | SWATANTRA ROUT | Dev | Iota | 4 | No Action items | NA | Yes | Balanced |  | 5 | 5 | 5 | Yes | 4 | 4 | Scrum Team | 5 | 4 | Yes | YES | Moderate | Less than 10% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Release Kick Off | Sprint Planning | Ad-hoc requests prioritisation and acceptance | Change in Due date and QA Sign off Date restrictions | Release Planning, Strategy & Schedule (Proper Checkpoint and dates on jira tickets) | Non Release Activities | Less than 5% |  | YES | NA |  |  | Yes | Dev Prototype, Exploring / understanding existing codebase, Writing code for new features, Review PRs, Debugging and Fixing Bugs, Writing Unit tests, Creating test cases or test scripts | 20% to 50% | for doing POCs | NA | Yes
2025-09-18 18:35 | Diksha Khatri | SWATANTRA ROUT | Dev | Iota | 5 | Yes | Limiting scope changes by having PMs in loop during the design and development phase | Yes | Balanced | 4 | 5 | 3 | 5 | Partially/Incomplete | 5 | 5 | Scrum Team | 5 | 5 | Yes | YES | Moderate | 10% to 20% | Yes | None | Balanced (80% - 90%) | Some Information but still need further details | Yes | Well Managed | Epic Breakdown | Sprint Planning | Jira Details - Epic breakdown, DoD, Exit criteria, CS Bugs | Blocking Scope change | Release Planning, Strategy & Schedule (Proper Checkpoint and dates on jira tickets) | Improper Epic Breakdown & Estimations - Missing Sprint Backlog | Less than 5% |  | YES | NA |  |  | Yes | Exploring / understanding existing codebase, Writing code for new features, Review PRs, Debugging and Fixing Bugs, Writing Unit tests, Creating test cases or test scripts | 20% to 50% | Based on the given context it was able to debug one issue related exponential retry and provided detailed analysis on the issue. | For certain issues we need to provide a lot of context multiple times to get the right analysis | Yes
2025-09-18 19:09 | Jegadeesh Santhana Krishnan | Ankur Sachdeva | Dev | Chipmuks | 5 | Yes | We focussed on resolving webhook plaintext support and resolving as many bugs as possible | Yes | Well Managed | 5 | 4 | 4 | 5 | Yes | 4 | 5 | Scrum Team | 5 | 5 | Yes | YES | Multiple | More than 30% | Yes | Multiple | Balanced (80% - 90%) | Optimal information available | Not aware of any such initiative. Though the release coordination among teams was better than previous releases among teams | Well Managed | Epic Breakdown | Sprint Closure/review | CI/CD, Testing & Continuous planning | Blocking Scope change | Release Planning, Strategy & Schedule (Proper Checkpoint and dates on jira tickets) | Ad-hoc Tasks & improper prioritisation | More than 10% but Less than 20% |  | YES | Maybe retro and planning becomes clearer |  |  | Yes | Dev Prototype, Exploring / understanding existing codebase, Writing code for new features, Review PRs, Debugging and Fixing Bugs, Writing Unit tests, Creating test cases or test scripts | Greater than 50% | I wanted to make a Microsoft Webhook Request to celigo webhook, had no idea how to do things. Asked cursor to help me setup things | No | Yes
2025-09-18 19:15 | Jegadeesh Santhana Krishnan | Ramakrishna Grandhi | Dev | Tintin | 5 | Yes | na | Yes | Well Managed | 5 | 4 | 4 | 4 | Yes | 4 | 4 | Individual | 4 | 4 | No | YES | Moderate | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Some Information but still need further details | Yes | Well Managed | Continuous Epic Grooming | Sprint Planning | Test Design | Risk call out during Weekly SoS | Effective communication | Intra team collaboration | More Than 5% but less than 10% | na | YES | na | na |  | Yes | Dev Prototype, Exploring / understanding existing codebase, Writing code for new features, Debugging and Fixing Bugs, Writing Unit tests, Creating test cases or test scripts | 20% to 50% | for non complex task it is good and can do repetitive task in minutes which takes for devloper whole day | always review the code written by cursor , some time it add lot of grabage code and unit test which is not effective | yes
2025-09-18 19:17 | Jegadeesh Santhana Krishnan | Subhan Ansari | Dev | Aliens | 4 | No Action items | NA | Yes | Balanced |  |  |  |  | Yes |  |  | Scrum Team |  |  | No | YES | Moderate | 10% to 20% | No |  |  | Optimal information available | Yes |  | Epic Breakdown | Sprint Planning | KT and recording repository | Risk call out during Weekly SoS | Release Planning, Strategy & Schedule (Proper Checkpoint and dates on jira tickets) | Ad-hoc Tasks & improper prioritisation | Less than 5% |  | YES | NA |  |  | Yes | Exploring / understanding existing codebase, Writing code for new features, Review PRs, Debugging and Fixing Bugs, Writing Unit tests | 20% to 50% | it Wrote a UT for me | NA | NA
2025-09-18 21:17 | Mohammed Fayaz | Prasad Deverakonda | QA & Scrum Master | Astra | 4 | Yes | NA | Yes | Balanced | 4 | 5 | 5 | 5 | Partially/Incomplete | 5 | 4 | Scrum Team | 4 | 4 | Yes | YES | Multiple | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Some Information but still need further details | Yes | Well Managed | Continuous Epic Grooming | Sprint Planning | Jira Details - Epic breakdown, DoD, Exit criteria, CS Bugs | Change in Due date and QA Sign off Date restrictions | Release Planning, Strategy & Schedule (Proper Checkpoint and dates on jira tickets) | Intra team collaboration | Less than 5% | NA | YES | NA | NA |  | Yes | Exploring / understanding existing codebase, Creating test cases or test scripts | No Productivity Improvement | Using Cursor, generate a test scope for the upcoming release epic and create a test script by referencing similar existing cases easily | NA | NA
2025-09-18 21:19 | Jegadeesh Santhana Krishnan | Rajesh Subramani | Dev | Hercules | 4 | No |  | Yes | Well Managed | 4 | 4 | 4 | 4 | Yes | 4 | 4 | Scrum Team | 4 | 4 | Yes | Moderately | Moderate | 10% to 20% | Yes | Moderate | Over Utilised (90% and Above) | Some Information but still need further details | Yes | Well Managed | Release Kick Off | Sprint Closure/review | Bugs Management & Deferring | Risk call out during Weekly SoS | Better Estimations & Epic Breakdown | Improper Epic Breakdown & Estimations - Missing Sprint Backlog | More Than 5% but less than 10% |  | YES | nil | nil |  | Yes | Exploring / understanding existing codebase, Writing code for new features, Writing Unit tests, Creating test cases or test scripts | 20% to 50% | nii | nil | yes
2025-09-18 21:45 | Jegadeesh Santhana Krishnan | Selvakumar Thiyagarajan | Dev | Pheonix | 5 | No Action items | NA | Yes | Balanced | 4 | 5 | 4 | 5 | Yes | 5 | 5 | Scrum Team | 5 | 4 | Yes | YES | Moderate | 10% to 20% | Yes | None | Balanced (80% - 90%) | Optimal information available | Yes | Average | Code Freeze Milestones and hardening phase | Sprint Closure/review | CI/CD, Testing & Continuous planning | Change in Due date and QA Sign off Date restrictions | Efficient Jira Usage (New Fields such as - Due date, QA Lead, QA Involvement, QA Signoff date) | Reviews | Less than 5% | NA | YES | NA | NA |  | Yes | Exploring / understanding existing codebase, Writing code for new features, Debugging and Fixing Bugs, Writing Unit tests, Improve code quality for optimization | 20% to 50% | It quickly wrote a utility to install python project as a dependency in a node project | NA | Yes
2025-09-18 21:50 | Jegadeesh Santhana Krishnan | Ankur Sachdeva | Dev | Chipmuks | 5 | Yes | better planning | Yes | Balanced | 5 | 5 | 5 | 5 | Yes | 5 | 5 | Scrum Team | 5 | 5 | Yes | YES | Moderate | 10% to 20% | Yes | None | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Committed Epic Prioritisation | Sprint Planning | Non Release Activity Identification & capacity reserve | Blocking Scope change | Sprint Planning Structure | Delayed Response on open Queries, need multiple followups | Less than 5% |  | YES | no |  |  | Yes | Dev Prototype, Exploring / understanding existing codebase | 20% to 50% | Its helpful in analysing the existing code which can be very useful during design | new code generation can be faulty. Also test cases are also having too much mocking. | Slack
2025-09-18 23:41 | Jegadeesh Santhana Krishnan | Ankur Sachdeva | Dev & Scrum Master | Chipmuks | 5 | No Action items | No action items | Yes | Well Managed | 5 | 5 | 5 | 5 | Yes | 5 | 5 | Scrum Team | 5 | 5 | Yes | YES | Moderate | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Monitoring and Controlling Progress | Sprint Planning | Tech Design | Change in Due date and QA Sign off Date restrictions | Better & transparent commitments | Ad-hoc Tasks & improper prioritisation | More than 10% but Less than 20% |  | YES | nope |  |  | Yes | Dev Prototype, Exploring / understanding existing codebase, Writing code for new features, Review PRs, Debugging and Fixing Bugs, Writing Unit tests, Creating test cases or test scripts | 20% to 50% | It helped me discover edge cases | despite great prompts, it's not helpful for complex code | yes
2025-09-19 00:02 | Mujtaba Ahmad | Priya Vanteru | Dev | Falcon | 4 | No |  | Yes | Balanced | 4 | 4 | 4 | 4 | Yes | 4 | 4 | Scrum Team | 4 | 4 | Yes | YES | Moderate | Less than 10% | No | Moderate | Over Utilised (90% and Above) | Some Information but still need further details | No | Not Well | Code Freeze Milestones and hardening phase | Sprint Planning | Ad-hoc requests prioritisation and acceptance | Blocking Scope change | Better Estimations & Epic Breakdown | Communication gap b/w dependent teams | More than 20% | na | YES | na | na |  | Yes | Dev Prototype, Exploring / understanding existing codebase, Review PRs, Debugging and Fixing Bugs, Writing Unit tests | Less than 10% | na | na | na
2025-09-19 07:02 | Mohammed Fayaz | Tharuni Sai Idupulapati | QA | Apollo | 4 | No Action items | NA | Yes | Balanced | 4 | 5 | 4 | 5 | Yes | 4 | 5 | Scrum Team | 4 | 4 | Yes | Moderately | Multiple | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Average | Epic Breakdown | Sprint Planning | Ad-hoc requests prioritisation and acceptance | Change in Due date and QA Sign off Date restrictions | Reduced over commit | Ad-hoc Tasks & improper prioritisation | Less than 5% |  | YES | NA |  |  | Yes | Exploring / understanding existing codebase, Debugging and Fixing Bugs, Creating test cases or test scripts | 20% to 50% | Cursor helped us in sharing negative and positive test cases for a bug | NA | YES
2025-09-19 09:33 | Jegadeesh Santhana Krishnan | Chandra Sekhar Kusupati | Dev | Eirene | 5 | No |  | Yes | Balanced | 4 | 5 | 4 | 5 | Yes | 5 | 5 | Individual | 5 | 5 | Yes | YES | Moderate | 10% to 20% | Yes | Multiple | Over Utilised (90% and Above) | Some Information but still need further details | Yes | Average | Continuous Epic Grooming | Sprint Planning | Ad-hoc requests prioritisation and acceptance | Blocking Scope change | Better & transparent commitments | Ad-hoc Tasks & improper prioritisation | Less than 5% |  | YES | NA |  |  | Yes | Dev Prototype, Exploring / understanding existing codebase, Writing code for new features, Review PRs, Debugging and Fixing Bugs, Writing Unit tests | 20% to 50% | Cursor was able to understand the existing huge codebase and provide optimal solution for the problem. It is helpful in creating the isolated components and its business logic given the clear instructions about what needs to be done. | Especially in huge codebases, most of the times it writes unnecessary code to fix simple issues and complicate things | Yes
2025-09-19 10:07 | Diksha Khatri | SWATANTRA ROUT | Dev | Iota | 4 | Yes | . | Yes | Well Managed | 4 | 4 | 4 | 4 | Yes | 4 | 4 | Scrum Team | 4 | 3 | Yes | Moderately | Moderate | Less than 10% | No | Moderate | Over Utilised (90% and Above) | Optimal information available | Not aware of any such initiative. Though the release coordination among teams was better than previous releases among teams | Average | Committed Epic Prioritisation | Sprint Closure/review | Tech Design | Change in Due date and QA Sign off Date restrictions | Release Planning, Strategy & Schedule (Proper Checkpoint and dates on jira tickets) | Partial or missing details on Jira Trackers Description | Less than 5% |  | YES | . |  |  | Yes | Dev Prototype, Exploring / understanding existing codebase, Writing code for new features, Writing Unit tests | 20% to 50% | if you ever want to know how a use case would be handled accross a repo, you can ask its journey and what all things impact this with input and output data. For the data, It takes refference from the unit/integration test's data to provide you with the examples. | NA | NA
2025-09-19 10:30 | Diksha Khatri | Diksha Khatri | Dev | Astra | 5 | Yes | updation of status was not happening earlier but it's happening now | Yes | Balanced | 4 | 4 | 3 | 5 | Yes | 4 | 5 | Scrum Team | 5 | 5 | Yes | YES | Moderate | Less than 10% | Yes | None | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Committed Epic Prioritisation | Sprint Closure/review | Backlog & CS bugs prioritisation | Risk call out during Weekly SoS | Better Estimations & Epic Breakdown | Partial or missing details on Jira Trackers Description | More Than 5% but less than 10% |  | YES | no |  |  | Yes | Exploring / understanding existing codebase, Debugging and Fixing Bugs, Writing Unit tests | 20% to 50% | In automating testcases and also helped in finding out issue with the testcase | It's very useful sometimes and sometimes it gives you the result that you want like if you say this is incorrect it will yes you are perfectly right | Yes
2025-09-19 10:41 | Jegadeesh Santhana Krishnan | Ashok Kumar Dantham | Dev | Aurora | 4 | Yes | Communication with UX was a bit delayed, and this time it was quicker and more frequent | No | [32 empty] | I was working on a tech debt to upgrade the redux and react-redux package and also dealing backlog in DI | Yes | Dev Prototype, Exploring / understanding existing codebase, Writing code for new features, Debugging and Fixing Bugs, Writing Unit tests, I use a mix of browser UI screenshots and browser console screenshots with the code IDE to fix and debug issues. Even though it doesn't fix the issues completely, it certainly does save alot of time | 20% to 50% | There was 2 critical issues which were introduced with the package uprade, that I was working on, one I fixed with the help of a package change log description given by gemini. In another one I was not able to accurately point out the rootcause for the issue, it would have taken days. I asked cursor to add logs at certain areas that I have narrowed out where I felt the issue might be occuring, and I gave it 2 screenshots of the browser console, which contains the store action calls printed. One screenshot with my package upgrade changes and another without it where the issue was not occuring. It compared the screenshots analysed them and gave a critical breakthrough which helped alot to pinpoint the rootcause. | It might not be an issue at all for majority, but I felt typing in the entire lengthy descriptive instructions to the cursor chat window feels tedious , if we can have a speech to text tool it would be better atleast in my case i felt that way because I often give larger instruction texts to make sure the model doesn't halucinate and does exactly what I ask it to do | Yes
2025-09-19 10:53 | Mohammed Fayaz | Tharuni Sai Idupulapati | QA | Apollo | 5 | Yes | NA | Yes | Well Managed | 5 | 4 | 5 | 5 | Partially/Incomplete | 4 | 5 | Individual | 5 | 4 | Yes | YES | Moderate | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Code Freeze Milestones and hardening phase | Sprint Closure/review | KT and recording repository | Change in Due date and QA Sign off Date restrictions | Better & transparent commitments | Delayed Response on open Queries, need multiple followups | More Than 5% but less than 10% | NA | YES | NA | NA |  | Yes | Exploring / understanding existing codebase, Creating test cases or test scripts | 20% to 50% | For point fix bugs, manually we won't get much test cases, where as while using cursor, we are getting good number of test cases which are valid | NA | Yes
2025-09-19 11:31 | Mujtaba Ahmad | Priya Vanteru | Dev | Indus | 5 | Yes | Planning for dev review bandwidth explicitly | Yes | Chaotic | 2 | 4 | 2 | 4 | Yes | 2 | 3 | Scrum Team | 3 | 4 | Yes | NO | Moderate | 20% to 30% | No | Multiple | Over Utilised (90% and Above) | Optimal information available | Yes | Not Well | Epic Breakdown | Sprint Planning | Intra Team Collaboration - Dependency linking on Jira by Individual owners | Risk call out during Weekly SoS | None | Improper Epic Breakdown & Estimations - Missing Sprint Backlog | More than 10% but Less than 20% |  | Not Efficiently | NA |  |  | Yes | Dev Prototype, Exploring / understanding existing codebase, Writing code for new features, Review PRs, Debugging and Fixing Bugs, Writing Unit tests, Creating test cases or test scripts | 20% to 50% | Very good with repetitive tasks like adding env vars/config for all env vars in cd | Cursor sometimes goes for the unnecessarily complex solutions | Yes
2025-09-19 11:43 | Mohammed Fayaz | Mohammed Fayaz | QA | Optimus | 4 | Yes | Not Involved in Release work | No | [32 empty] | Automation Framework Development | Yes | Writing code for new features, Debugging and Fixing Bugs | Greater than 50% | I was able to fix all the issues in the Jenkins Pipeline and Automation Framework Issues | Need thorough review | Getting the proper support
2025-09-19 12:07 | Mohammed Fayaz | SathishKumar D | QA | Optimus | 5 | No Action items | NA | No | [33 empty] | Yes | Writing code for new features, Review PRs, Debugging and Fixing Bugs, Writing Unit tests | 20% to 50% | To fix a Docker cloudflare storage issue | NA | Yes
2025-09-19 12:12 | Jegadeesh Santhana Krishnan | Selvakumar Thiyagarajan | Dev | Pheonix | 4 | Yes | how we can improve process for new automation thing for epics | Yes | Balanced | 4 | 4 | 3 | 4 | Yes | 3 | 4 | Individual | 4 | 4 | Yes | YES | Moderate | Less than 10% | Yes | None | Balanced (80% - 90%) | Some Information but still need further details | Not aware of any such initiative. Though the release coordination among teams was better than previous releases among teams | Average | Continuous Epic Grooming | Sprint Planning | Intra Team Collaboration - Dependency linking on Jira by Individual owners | Blocking Scope change | Work allocation with sufficient capacity reserve | Partial or missing details on Jira Trackers Description | More Than 5% but less than 10% |  | YES | N/A |  |  | Yes | Exploring / understanding existing codebase, Writing code for new features, Review PRs, Debugging and Fixing Bugs, Writing Unit tests | 20% to 50% | In fixing bugs and writing test cases and identifying bugs that can occur with our code and finding the files which may impact due to changes we did. | N/A | yes
2025-09-19 12:14 | Mohammed Fayaz | SathishKumar D | QA | Optimus | 5 | Yes | SSO account related latest updates were moved to all environments and test cases were fixed | Yes | Balanced | 5 | 4 | 4 | 5 | Yes | 5 | 5 | Scrum Team | 5 | 4 | Yes | Moderately | Moderate | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Some Information but still need further details | Yes | Well Managed | Monitoring and Controlling Progress | Sprint Planning | KT and recording repository | Change in Due date and QA Sign off Date restrictions | Reduced over commit | Modifications on Approved Tech designs | More Than 5% but less than 10% | nothing in prior right now | YES | it is going good | better story points and details for step creation required |  | Yes | Writing code for new features, Review PRs, Debugging and Fixing Bugs, Creating test cases or test scripts | 20% to 50% | it helped me do local setup of io | good to use | Pankaj.Chauhan@celigo.com
2025-09-19 13:12 | Krishna Kishore Mothukuri | Ajitkumar kaller | Dev | Velocity | 5 | Yes | Epic breakdown | Yes | Balanced | 4 | 4 | 4 | 4 | Yes | 4 | 4 | Individual | 4 | 4 | Yes | YES | Moderate | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Average | Epic Breakdown | Sprint Planning | Tech Design | Blocking Scope change | Release Planning, Strategy & Schedule (Proper Checkpoint and dates on jira tickets) | Improper Epic Breakdown & Estimations - Missing Sprint Backlog | More Than 5% but less than 10% |  | YES | NA |  |  | Yes | Dev Prototype, Writing code for new features | 20% to 50% | Finding patterns in IA testcases | NA | yes
2025-09-19 13:15 | Diksha Khatri | Prasad Deverakonda | QA | Phi | 3 | No |  | Yes | Balanced | 3 | 3 | 3 | 3 | Yes | 3 | 3 | Scrum Team | 4 | 3 | Yes | YES | None | 10% to 20% | No | Moderate | Under Utilisation (80% Below) | Optimal information available | Yes | Average | Code Freeze Milestones and hardening phase | Sprint Planning | Ad-hoc requests prioritisation and acceptance | Blocking Scope change | None | Delay in commitments from dependant team | More than 10% but Less than 20% |  | Not Efficiently | Need focus more sprint planing |  |  | Yes | Debugging and Fixing Bugs, Creating test cases or test scripts | 20% to 50% | Executing test cases for connector by verfying metdata | no | Yes
2025-09-19 13:15 | Krishna Kishore Mothukuri | Ajitkumar kaller | Dev | Velocity | 5 | Yes | Sprint planing should be proper and all the trackers needed should be created before planing starts | Yes | Balanced | 5 | 5 | 5 | 5 | Yes | 5 | 5 | Scrum Team | 5 | 5 | Yes | YES | Moderate | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Some Information but still need further details | Yes | Well Managed | Continuous Epic Grooming | Sprint Planning | Non Release Activity Identification & capacity reserve | Blocking Scope change | None | Non Release Activities | Less than 5% | NA | YES | NA | NA |  | Yes | Dev Prototype, Exploring / understanding existing codebase, Writing code for new features, Debugging and Fixing Bugs, Writing Unit tests, Creating test cases or test scripts | 20% to 50% | NA | NA | Yes
2025-09-19 13:35 | Diksha Khatri | Diksha Khatri | Dev | Individual Capacity, Not Associated with any particular team | 4 | Yes | Timely updates to Jira trackers. | Yes | Balanced | 3 | 4 | 4 | 4 | Yes | 2 | 3 | SME/Epic Owner/EM/QM (Pre Defined Efforts Estimates) | 4 | 4 | Yes | YES | Moderate | 10% to 20% | Yes | Multiple | Over Utilised (90% and Above) | Some Information but still need further details | Yes | Average | Continuous Epic Grooming | Sprint Closure/review | Ad-hoc requests prioritisation and acceptance | Change in Due date and QA Sign off Date restrictions | Better & transparent commitments | Ad-hoc Tasks & improper prioritisation | Less than 5% | NA | YES | NA | NA |  | Yes | Dev Prototype, Exploring / understanding existing codebase, Writing code for new features, Review PRs, Debugging and Fixing Bugs, Writing Unit tests, Creating test cases or test scripts | 20% to 50% | Cursor helped me to generate a fully functional SuiteApp from the existing SuiteBundle. | Needs some more context while writing automation test cases. | yes
2025-09-19 13:36 | Krishna Kishore Mothukuri | Krishna Kishore Mothukuri | Architect/Individual Contributors |  |  |  |  | Yes | Balanced | 5 | 5 | 5 | 5 | Yes | 5 | 5 | Individual | 5 | 5 | Yes | YES | Multiple | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Code Freeze Milestones and hardening phase | Sprint Closure/review | Tech Design | Change in Due date and QA Sign off Date restrictions | None | Modifications on Approved Tech designs | More Than 5% but less than 10% |  | YES | None |  |  | Yes | Dev Prototype, Writing code for new features, Debugging and Fixing Bugs, Brainstorming for ideas for research | 20% to 50% | I can develop POCs very quickly using web technologies that I am not familiar with | None | Yes
2025-09-19 13:39 | Diksha Khatri | SWATANTRA ROUT | Dev | Astra | 5 | Yes | The jira updation was not happening on regular basis. But by adding a placeholder in calendar, everyone started to follow it. | Yes | Well Managed | 5 | 5 | 5 | 5 | Yes | 5 | 5 | Scrum Team | 5 | 5 | Yes | YES | Moderate | 20% to 30% | Yes | None | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Continuous Epic Grooming | Sprint DSU's | Tech Design | Blocking Scope change | Better Estimations & Epic Breakdown | Reviews | More Than 5% but less than 10% |  | YES | - |  |  | Yes | Dev Prototype, Exploring / understanding existing codebase, Writing code for new features, Review PRs, Debugging and Fixing Bugs, Writing Unit tests, Creating test cases or test scripts | 20% to 50% | We can get multiplle automation skeleton within few minutes. | Cursor has definately helped in reducing manual effort and focus our attention to necessary things. | Yes
2025-09-19 13:49 | Krishna Kishore Mothukuri | Ajitkumar kaller | Dev | Velocity | 4 | Yes | We are adding trackers mid-sprint because most of our work is exploratory, and the next steps depend on the completion of the current tracker. To address this, we now create placeholder trackers at the start of the sprint with descriptions stating that the next steps for a particular tracker will be captured there. Once we pick them up, we update the placeholders with the correct descriptions. | Yes | Balanced | 5 | 5 | 5 | 5 | Yes | 5 | 5 | Scrum Team | 5 | 5 | Yes | YES | Multiple | Less than 10% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Continuous Epic Grooming | Sprint Closure/review | Ad-hoc requests prioritisation and acceptance | Risk call out during Weekly SoS | Efficient Jira Usage (New Fields such as - Due date, QA Lead, QA Involvement, QA Signoff date) | Ad-hoc Tasks & improper prioritisation | Less than 5% |  | YES | no | no |  | Yes | Dev Prototype, Exploring / understanding existing codebase, Writing code for new features, Debugging and Fixing Bugs | 20% to 50% | To address the bug, I first provided the error scenario along with detailed information to help reproduce the issue. Using this context, Cursor automatically identified all the impacted areas in the codebase. Based on its suggestions, I applied the necessary changes to ensure that the bug was resolved consistently across all affected sections of the code. In this way, the time usually spent on root cause analysis was significantly reduced, and my focus was limited to validating the changes through manual testing. | none | yes
2025-09-19 13:52 | Mujtaba Ahmad | Mujtaba Ahmad | EM |  |  |  |  | Yes | Balanced | 5 | 5 | 5 | 5 | Yes | 5 | 5 | Scrum Team | 5 | 5 | Yes | YES | Moderate | 10% to 20% | No | Multiple | Balanced (80% - 90%) | Optimal information available | Yes | Average | Epic Breakdown | Sprint Planning | Jira Details - Epic breakdown, DoD, Exit criteria, CS Bugs | Blocking Scope change | Sprint Planning Structure | Ad-hoc Tasks & improper prioritisation | My role involves process improvement and enablement (EM's, SM's & Other folks responsible for process streamlining) | NA | YES | not much | New automation to move engineering EPIC to approve state is really troublesome |  | Yes | Exploring / understanding existing codebase, Review PRs, Debugging and Fixing Bugs, Writing Unit tests | Greater than 50% | V8 test case generation was 100% automated with cursor. New handlebar epic more then 50% work was done by cursor GPT was a great help in Enterprise logging tech designs | All good | Yes
2025-09-19 14:01 | Mohammed Fayaz | Tharuni Sai Idupulapati | QA | Ganges | 4 | No Action items | NA | Yes | Balanced | 4 | 4 | 4 | 4 | Partially/Incomplete | 4 | 4 | Scrum Team | 4 | 4 | Yes | YES | Moderate | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Some Information but still need further details | Yes | Average | Epic Breakdown | Sprint Planning | Jira Details - Epic breakdown, DoD, Exit criteria, CS Bugs | Blocking Scope change | Efficient Jira Usage (New Fields such as - Due date, QA Lead, QA Involvement, QA Signoff date) | Improper Epic Breakdown & Estimations - Missing Sprint Backlog | More Than 5% but less than 10% |  | YES | NA | NA |  | Yes | Dev Prototype, Exploring / understanding existing codebase, Creating test cases or test scripts | 20% to 50% | Helped me in creating an agent that helps analyse UI automation reports | NA | NA
2025-09-19 14:05 | Mohammed Fayaz | Komal Varma | QA | Aurora | 4 | No |  | Yes | Balanced | 4 | 4 | 4 | 4 | Yes | 4 | 4 | Scrum Team | 4 | 4 | Yes | YES | Moderate | Less than 10% | No | Moderate | Balanced (80% - 90%) | Some Information but still need further details | Not aware of any such initiative. Though the release coordination among teams was better than previous releases among teams | Average | Code Freeze Milestones and hardening phase | Sprint Planning | Non Release Activity Identification & capacity reserve | Change in Due date and QA Sign off Date restrictions | Better Estimations & Epic Breakdown | Delay in commitments from dependant team | Less than 5% |  | YES | No |  |  | Yes | Exploring / understanding existing codebase, Creating test cases or test scripts | 20% to 50% | It helps in understanding the impacted areas in the codebase | NA | Yes
2025-09-19 14:14 | Mohammed Fayaz | Varun Batra | QA | Minions | 4 | Yes | JIRA updation | Yes | Balanced | 3 | 4 | 5 | 5 | Partially/Incomplete | 4 | 3 | Scrum Team | 4 | 4 | Yes | YES | Moderate | 10% to 20% | Yes | Moderate | Over Utilised (90% and Above) | Optimal information available | Yes | Average | Committed Epic Prioritisation | Sprint Planning | Jira Details - Epic breakdown, DoD, Exit criteria, CS Bugs | Blocking Scope change | Better & transparent commitments | Improper Epic Breakdown & Estimations - Missing Sprint Backlog | Less than 5% | - | YES | - |  |  | Yes | Exploring / understanding existing codebase, Review PRs, Debugging and Fixing Bugs, Creating test cases or test scripts | 20% to 50% | - | - | -
2025-09-19 14:16 | Mujtaba Ahmad | Raman Soni | Dev | Ganges | 4 | Yes | Write all the feasible tests from the test design in the unit tests itself rather covering in cmp tests/rest api automation | Yes | Well Managed | 4 | 4 | 4 | 4 | Yes | 4 | 4 | Individual | 4 | 4 | Yes | YES | Moderate | Less than 10% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Committed Epic Prioritisation | Sprint Closure/review | KT and recording repository | Blocking Scope change | None | Non Release Activities | Less than 5% |  | YES | na |  |  | Yes | Exploring / understanding existing codebase, Writing code for new features, Review PRs, Debugging and Fixing Bugs, Writing Unit tests, Creating test cases or test scripts, Reproduce bugs | 20% to 50% | It helped me reproduce a CPU block which we were struggling to reproduce in QA env/local | NA | yes
2025-09-19 14:16 | Mujtaba Ahmad | Raman Soni | Dev & Scrum Master | Stark | 4 | No Action items | No action items | Yes | Chaotic | 3 | 4 | 4 | 4 | Yes | 4 | 4 | Individual | 4 | 3 | Yes | YES | Moderate | Less than 10% | No | Multiple | Balanced (80% - 90%) | Some Information but still need further details | Yes | Average | Monitoring and Controlling Progress | Sprint Planning | Bugs Management & Deferring | Strict Bug SLA's | None | Ad-hoc Tasks & improper prioritisation | More Than 5% but less than 10% |  | YES | na |  |  | Yes | Exploring / understanding existing codebase, Debugging and Fixing Bugs, Writing Unit tests | 20% to 50% | used cursor to modify code in js-runtime , which needed to check google v8 documentation. with cursor help time to implement code changes was reduced drastically | it still gives flaky results manytimes , its very important to validate the changes it added | proper support is there
2025-09-19 14:37 | Mujtaba Ahmad | Raman Soni | Dev | Stark | 5 | Yes | Effective Jira usage | Yes | Balanced | 4 | 5 | 5 | 5 | Yes | 5 | 5 | Scrum Team | 5 | 5 | Yes | YES | Multiple | Less than 10% | Yes | Multiple | Balanced (80% - 90%) | Optimal information available | Not aware of any such initiative. Though the release coordination among teams was better than previous releases among teams | Average | Committed Epic Prioritisation | Sprint Closure/review | Non Release Activity Identification & capacity reserve | Strict Bug SLA's | None | Ad-hoc Tasks & improper prioritisation | More Than 5% but less than 10% |  | YES | NA |  |  | Yes | Dev Prototype, Exploring / understanding existing codebase, Debugging and Fixing Bugs, Writing Unit tests, Creating test cases or test scripts | 20% to 50% | upgrading v8 | As we are already have workflow automation that connects to many apps. So we can include Chatgpt as one of the apps as an intermediate, create a connection with it and use it for various use cases. Just like various n8n does combines AI capabilities with business process automation | Yes
2025-09-19 14:40 | Mohammed Fayaz | Prasad Deverakonda | QA | Iota | 5 | Yes | Discussed on the environment setup for holiday season | Yes | Balanced | 5 | 5 | 5 | 5 | Yes | 5 | 4 | Individual | 4 | 4 | Yes | YES | Moderate | 10% to 20% | Yes | Moderate | Over Utilised (90% and Above) | Optimal information available | Yes | Well Managed | Continuous Epic Grooming | Sprint Planning | Ad-hoc requests prioritisation and acceptance | Risk call out during Weekly SoS | Better Estimations & Epic Breakdown | Ad-hoc Tasks & improper prioritisation | Less than 5% |  | YES | no |  |  | Yes | Exploring / understanding existing codebase, Writing code for new features, Debugging and Fixing Bugs, Creating test cases or test scripts | 20% to 50% | It helped in debugging automation errors, Also helped alot in creating the test data generation for load testing | Saving lot of manual effort while automating the test scripts | yes
2025-09-19 14:54 | Mujtaba Ahmad | Ranjith Kumar M | Dev & Scrum Master | Gryffindor | 4 | Yes | Team need to prioritise items on release deliverables. Priority should be clear in planning meet. if other teams are merging PR on our repos and PR needs review, we should be inform beforehand while planning. mainly EDI team requests were Before start of the release, we should be clear of priorities of each epic/bug. like we are doing for this rel If we add any tracker in between the sprint, we need to inform QA. related to agent issue etc. | Yes | Chaotic | 4 | 4 | 4 | 5 | Yes | 3 | 4 | Scrum Team | 4 | 4 | Yes | YES | Moderate | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Some Information but still need further details | Yes | Not Well | Committed Epic Prioritisation | Sprint Planning | Jira Details - Epic breakdown, DoD, Exit criteria, CS Bugs | Blocking Scope change | Efficient Jira Usage (New Fields such as - Due date, QA Lead, QA Involvement, QA Signoff date) | Improper Epic Breakdown & Estimations - Missing Sprint Backlog | More Than 5% but less than 10% | story Estimation of items from the team can be improved | YES | We should stop dev changes 2-3 days prior to release code freeze | NA |  | Yes | Exploring / understanding existing codebase, Writing code for new features, Review PRs, Debugging and Fixing Bugs, Writing Unit tests, Creating test cases or test scripts | 20% to 50% | It helped me in doing POC's on sdk v3 migration for file-service and exploring c++ code used within that and giving a correction there | Getting a lot of AI loops in some recent taks | yes
2025-09-19 15:01 | Mohammed Fayaz | Tharuni Sai Idupulapati | QA | Gryffindor | 5 | Yes | Having PR reviews post DSU and leaving some bandwidth for adhoc tasks | Yes | Chaotic | 5 | 4 | 5 | 5 | Yes | 4 | 5 | Individual | 4 | 3 | Yes | YES | Moderate | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Average | Monitoring and Controlling Progress | Sprint Closure/review | Ad-hoc requests prioritisation and acceptance | Change in Due date and QA Sign off Date restrictions | Sprint Planning Structure | Ad-hoc Tasks & improper prioritisation | More than 20% | NA | YES | No | No |  | Yes | Creating test cases or test scripts | 20% to 50% | Cursor provided me the whole Azure postman collection, where it helped a lot to create refresh tokens, even it helped me in providing correct client details in postman collection | NO | YES
2025-09-19 15:06 | Mohammed Fayaz | SathishKumar D | QA | Optimus | 5 | Yes | Action Item: As part of the Automation team, my responsibility during the release was to route the Automation IO suites with the latest canary tags, ensuring proper worker enable/disable configurations. This helped provide framework-level support so the QA team could perform their testing smoothly. Resolution: I coordinated with multiple teams regarding the canary release version and ensured the suites were aligned correctly for smooth execution. In addition, I personally took part in After Deployment tasks in IAQA, validating stability and confirming that the automation framework was functioning as expected post-release. This ensured that any post-deployment checks were handled effectively and the system was ready for QA usage. | No | [32 empty] | Although I was not directly associated with the release deliverables, I contributed in several support areas. I closely monitored the automation framework to ensure stability, assisted QA teams in resolving environment or execution-related blockers, and helped with routing IO suites when needed. I also collaborated with cross-functional teams to clarify queries related to canary tags, coordinated with stakeholders for smooth execution, and participated in after-deployment validation tasks in IAQA. These activities ensured that the overall release process remained seamless and that testing could be carried out without interruptions. | Yes | Dev Prototype, Writing code for new features, Debugging and Fixing Bugs | Greater than 50% | While running automation with the canary tag in IAQA, we encountered multiple rate-limit and server errors (429, 500, and 503) across 4–5 services. On investigation, we found that the /audit/signedURL API endpoint was being hit more than 3,000+ times, which caused these issues. With the help of Cursor, we were able to quickly implement a retry logic for the v1/audit/signedURL endpoint. This stabilized the execution, resolved the errors, and allowed our automation reports to be generated successfully. I also collaborated with Khaiser and Anita to validate and finalize the fix. This solution not only resolved the immediate problem but also ensured smoother automation runs in subsequent executions. | One key suggestion for Cursor would be to improve error handling visibility during execution. At times, when we encounter rate-limit or server errors, it takes effort to trace back the exact cause. If Cursor could provide clearer, real-time insights (like highlighting repeated failing API calls or retry attempts), it would help teams identify bottlenecks faster and apply fixes more efficiently. | gautam.rana@celigo.com
2025-09-19 15:12 | Mujtaba Ahmad | Ranjith Kumar M | Dev & Scrum Master | Zeta | 5 | Yes | way to better handle unplanned items causing spillovers and timeline deliveries - left some utilization -> tradeoff with low priority items (in planning we're trying to have some low priority items which can be trade-off) | Yes | Well Managed | 5 | 5 | 5 | 5 | Yes | 5 | 4 | Scrum Team | 4 | 4 | Yes | YES | Multiple | 10% to 20% | Yes | Multiple | Over Utilised (90% and Above) | Optimal information available | Yes | Well Managed | Monitoring and Controlling Progress | Sprint Planning | Ad-hoc requests prioritisation and acceptance | Blocking Scope change | Reduced over commit | Ad-hoc Tasks & improper prioritisation | More Than 5% but less than 10% |  | YES | N/A | N/A |  | Yes | Dev Prototype, Exploring / understanding existing codebase, Writing code for new features, Review PRs, Debugging and Fixing Bugs, Writing Unit tests, Creating test cases or test scripts | 20% to 50% | N/A | N/A | yes
2025-09-19 15:18 | Mohammed Fayaz | Komal Varma | Architect/Individual Contributors |  |  |  |  | Yes | Balanced | 3 | 5 | 1 | 5 | Yes | 3 | 3 | Individual | 4 | 4 | Yes | YES | Moderate | 10% to 20% | Yes | Moderate | Over Utilised (90% and Above) | Some Information but still need further details | Not aware of any such initiative. Though the release coordination among teams was better than previous releases among teams | Average | Committed Epic Prioritisation | Sprint Planning | Jira Details - Epic breakdown, DoD, Exit criteria, CS Bugs | Change in Due date and QA Sign off Date restrictions | Effective communication | Intra team collaboration | More than 10% but Less than 20% | - | YES | Figmas/FRDs should be updated in parallel in case of any updates. | Jira should have more details |  | Yes | Exploring / understanding existing codebase, Writing code for new features, Automation skeletons | 20% to 50% | Analysis of UI automation report | The tool is good for new implementation but creating or modifying the existing one it deviates. Also for little test steps, it gives non-needed steps. | yes
2025-09-19 15:49 | Mohammed Fayaz | Mohammed Fayaz | EM |  |  |  |  | Yes | Chaotic | 3 | 5 | 4 | 5 | Yes | 5 | 4 | Scrum Team | 4 | 4 | Yes | YES | Multiple | 10% to 20% | Yes | Moderate | Over Utilised (90% and Above) | Some Information but still need further details | Yes | Average | Committed Epic Prioritisation | Sprint Planning | Intra Team Collaboration - Dependency linking on Jira by Individual owners | Change in Due date and QA Sign off Date restrictions | Effective communication | Intra team collaboration | My role involves process improvement and enablement (EM's, SM's & Other folks responsible for process streamlining) |  | YES | Proper branching strategy when multiple teams are involved. | Change in QA ReadDate and QA Sign off Date - There should be some restrictions to update the dates during implementation phase atleast for the committed Epics. |  | Yes | Exploring / understanding existing codebase, JIRA MCP - for tracking release activities | 20% to 50% | JIRA MCP — using Cursor for Slack + JIRA integration to send notifications related to milestone slippages and release status with some customised formats. | NA | NA
2025-09-19 16:55 | Diksha Khatri | Diksha Khatri | Dev | Astra | 5 | Yes | Call out early to avoid spill overs | Yes | Well Managed | 5 | 5 | 5 | 5 | Yes | 5 | 5 | Scrum Team | 5 | 5 | Yes | YES | Moderate | Less than 10% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes |  | Code Freeze Milestones and hardening phase | Sprint DSU's | Ad-hoc requests prioritisation and acceptance | Risk call out during Weekly SoS | Effective communication | Delayed Response on open Queries, need multiple followups | More than 10% but Less than 20% |  | YES | Remove questions from this form which have been getting similar responses in the past 4-5 surveys. |  |  | Yes | Dev Prototype, Exploring / understanding existing codebase, Writing code for new features, Review PRs, Debugging and Fixing Bugs, Writing Unit tests, Creating test cases or test scripts, | 20% to 50%
2025-09-19 17:16 | Mohammed Fayaz | SathishKumar D | QA | optimus | 5 | Yes | new changes are merged | No | [32 empty] | fixing automation | Yes | Exploring / understanding existing codebase | 20% to 50% | NA | NA | All good
2025-09-19 17:47 | Mohammed Fayaz | SathishKumar D | QA | Optimus | 4 | Yes | Dividing the work based on resources bandwidth | No | [32 empty] | Enhancements to the automation framework | Yes | Exploring / understanding existing codebase, Writing code for new features, Debugging and Fixing Bugs | 20% to 50% | I need to create a few similar type of jira tasks. For this I took the help of cursor to create a similar type of tasks, this saved my time | Sometimes this is hallucinating and providing the unnecessary changes to the files | Yes
2025-09-19 23:56 | Jegadeesh Santhana Krishnan | Selvakumar Thiyagarajan | Dev | Iris | 5 | Yes | - | Yes | Balanced | 5 | 4 | 5 | 4 | Yes | 4 | 4 | Individual | 5 | 4 | Yes | YES | Moderate | 20% to 30% | Yes | Moderate | Balanced (80% - 90%) | Some Information but still need further details | Yes | Average | Monitoring and Controlling Progress | Sprint Closure/review | Jira Details - Epic breakdown, DoD, Exit criteria, CS Bugs | Blocking Scope change | Better Estimations & Epic Breakdown | Missing SLA's for Bugs, Trackers on Jira | More than 10% but Less than 20% |  | YES | - |  |  | Yes | Dev Prototype, Exploring / understanding existing codebase, Writing code for new features, Review PRs, Debugging and Fixing Bugs, Writing Unit tests, Creating test cases or test scripts | Greater than 50% | - | - | Yes
2025-09-20 00:09 | Mujtaba Ahmad | Ranjith Kumar M | Dev | Gryffindor | 4 | No |  | Yes | Chaotic | 2 | 3 | 3 | 3 | Partially/Incomplete | 3 | 4 | Scrum Team | 4 | 4 | Yes | Moderately | Moderate | 20% to 30% | Yes | Moderate | Over Utilised (90% and Above) | Optimal information available | Yes |  | Committed Epic Prioritisation | Sprint Planning | Ad-hoc requests prioritisation and acceptance | Risk call out during Weekly SoS | None | Improper Epic Breakdown & Estimations - Missing Sprint Backlog | Less than 5% |  | YES | No |  |  | Yes | Dev Prototype, Exploring / understanding existing codebase, Review PRs, Debugging and Fixing Bugs, Writing Unit tests, Creating test cases or test scripts | 20% to 50% | Created and used multiple scripts during npm vulnerability issue to clean up automatically. | No | Yes
2025-09-20 20:39 | Mohammed Fayaz | Anusha Jharupula | QA | Indus | 5 | Yes | We should give other teams a heads-up if their review is needed for an epic | Yes | Well Managed | 5 | 5 | 5 | 5 | Yes | 5 | 5 | Scrum Team | 5 | 5 | Yes | YES | Moderate | Less than 10% | Yes | None | Over Utilised (90% and Above) | Optimal information available | Yes | Well Managed | Committed Epic Prioritisation | Sprint Planning | Intra Team Collaboration - Dependency linking on Jira by Individual owners | Risk call out during Weekly SoS | Work allocation with sufficient capacity reserve | Delayed Response on open Queries, need multiple followups | Less than 5% |  | YES | No |  |  | Yes | Exploring / understanding existing codebase, Review PRs, Debugging and Fixing Bugs, Creating test cases or test scripts | 20% to 50% | Issues with starting the local setup, was able to resolve them using Cursor | No | Yes
2025-09-20 22:06 | Jegadeesh Santhana Krishnan | Jegadeesh Santhana Krishnan | Dev | Aliens | 4 | No Action items | no | No | [33 empty] | Yes | Dev Prototype, Exploring / understanding existing codebase, Writing code for new features, Review PRs, Debugging and Fixing Bugs | 20% to 50% | finding bugs | good | yes
2025-09-21 19:58 | Mohammed Fayaz | Tharuni Sai Idupulapati | EM |  |  |  |  | Yes | Balanced | 4 | 5 | 5 | 5 | Partially/Incomplete | 5 | 5 | Scrum Team | 5 | 4 | Yes | YES | Moderate | 10% to 20% | No | Moderate | Balanced (80% - 90%) | Some Information but still need further details | Yes | Average | Epic Breakdown | Sprint Closure/review | Jira Details - Epic breakdown, DoD, Exit criteria, CS Bugs | Strict Bug SLA's | None | Ad-hoc Tasks & improper prioritisation | My role involves process improvement and enablement (EM's, SM's & Other folks responsible for process streamlining) |  | YES | More focus on the third party libraries and their deprecation timelines and plan ahead of time, ex: AWS SDK in the current release was not planned properly. | NA |  | Yes | Creating test cases or test scripts | 20% to 50% | NA | NA | Yes
2025-09-22 10:05 | Mujtaba Ahmad | Raman Soni | Dev | Ganges | 4 | No Action items | -- | Yes | Balanced | 4 | 4 | 4 | 4 | Yes | 4 | 4 | Scrum Team | 4 | 4 | Yes | YES | Moderate | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Some Information but still need further details | Yes | Well Managed | Continuous Epic Grooming | Sprint Planning | KT and recording repository | Blocking Scope change | Better Estimations & Epic Breakdown | Reviews | Less than 5% |  | YES | - |  |  | Yes | Exploring / understanding existing codebase, Writing code for new features, Review PRs, Writing Unit tests | 20% to 50% | I was able to generate the UML diagrams with the help of cursor, which help better understand the code base | - | -
2025-09-22 10:12 | Krishna Kishore Mothukuri | Ajitkumar kaller | Dev | Velocity | 5 | Yes | NA | Yes | Balanced | 4 | 4 | 5 | 5 | Yes | 3 | 5 | Scrum Team | 4 | 4 | Yes | YES | Moderate | Less than 10% | No | Moderate | Balanced (80% - 90%) | Some Information but still need further details | Yes | Average | Epic Breakdown | Sprint Planning | Jira Details - Epic breakdown, DoD, Exit criteria, CS Bugs | Blocking Scope change | Work allocation with sufficient capacity reserve | Ad-hoc Tasks & improper prioritisation | More Than 5% but less than 10% |  | YES | NA |  |  | Yes | Dev Prototype, Exploring / understanding existing codebase, Debugging and Fixing Bugs, Pseudo code and getting design suggestions | Less than 10% | NA | NA | https://celigo-internal.slack.com/archives/C092NBURBEF
2025-09-22 10:38 | Jegadeesh Santhana Krishnan | Selvakumar Thiyagarajan | Dev | Chloris | 5 | No Action items | NA | Yes | Balanced | 5 | 4 | 5 | 4 | Yes | 5 | 5 | Individual | 5 | 5 | Yes | YES | Moderate | Less than 10% | Yes | Multiple | Over Utilised (90% and Above) | Optimal information available | Yes | Well Managed | Code Freeze Milestones and hardening phase | Sprint Planning | Bugs Management & Deferring | Blocking Scope change | Dependency management | Ad-hoc Tasks & improper prioritisation | Less than 5% |  | YES | None |  |  | Yes | Writing code for new features, Debugging and Fixing Bugs, Writing Unit tests, Creating test cases or test scripts | Less than 10% | It helped in generating the test cases for old file and trying to understand the dependencied of old code. | None | yes
2025-09-22 10:41 | Mujtaba Ahmad | Mujtaba Ahmad | EM |  |  |  |  | No | [32 empty] | Working as a SEM | Yes | Exploring / understanding existing codebase, Review PRs, Writing Unit tests, Fix uncaught execption, remove deadcode | Greater than 50% | Fix uncaught execption | Workshop on every Friday | Yes
2025-09-22 11:08 | Krishna Kishore Mothukuri | Krishna Kishore Mothukuri | EM |  |  |  |  | Yes | Balanced | 4 | 5 | 5 | 5 | Yes | 5 | 5 | Scrum Team | 5 | 5 | Yes | YES | Multiple | Less than 10% | Yes | None | Balanced (80% - 90%) | Some Information but still need further details | Yes | Well Managed | Continuous Epic Grooming | Sprint Planning | Jira Details - Epic breakdown, DoD, Exit criteria, CS Bugs | Blocking Scope change | Work allocation with sufficient capacity reserve | Modifications on Approved Tech designs | My role involves process improvement and enablement (EM's, SM's & Other folks responsible for process streamlining) |  | YES | We are discussing those in the Engineering Process Improvement meetings. |  |  | Yes | Dev Prototype, | 20% to 50% | Not much into dev currently. The release has gone in strengthening the team by hiring right candidates, workshops on the work that we are going to start on, some of the plan for next year etc. | Not currently. | Getting full support
2025-09-22 11:08 | Mohammed Fayaz | Anusha Jharupula | QA | Enigma | 5 | No Action items | No action item | Yes | Balanced | 5 | 5 | 5 | 5 | Yes | 5 | 5 | Scrum Team | 5 | 5 | Yes | YES | Moderate | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Code Freeze Milestones and hardening phase | Sprint Planning | Ad-hoc requests prioritisation and acceptance | Change in Due date and QA Sign off Date restrictions | Work allocation with sufficient capacity reserve | Reviews | More Than 5% but less than 10% | NA | YES | NA | NA |  | Yes | Writing code for new features, Review PRs, Debugging and Fixing Bugs, Creating test cases or test scripts | 20% to 50% | NA | NA | Yes
2025-09-22 11:26 | Mujtaba Ahmad | Anurag Goyal | Dev & Scrum Master | Titans | 5 | Yes | Making integrator-adaptor easy to manage, we had two main branches which was very difficult to manage. Now, we have only one main branch and restricted merge access which made things much easier. | Yes | Balanced | 3 | 5 | 5 | 5 | Yes | 5 | 5 | Scrum Team | 5 | 5 | Yes | YES | Moderate | 10% to 20% | Yes | Multiple | Over Utilised (90% and Above) | Optimal information available | Yes | Average | Monitoring and Controlling Progress | Sprint Closure/review | Ad-hoc requests prioritisation and acceptance | Blocking Scope change | Sprint Planning Structure | Ad-hoc Tasks & improper prioritisation | Less than 5% |  | YES | NA |  |  | Yes | Exploring / understanding existing codebase, Writing code for new features, Review PRs, Debugging and Fixing Bugs, Writing Unit tests | 20% to 50% | Cursor helped in finalizing infra related changes we were planning to do on our MS pods with perfect reasoning. | NA | Yes, getting sufficient support
2025-09-22 11:55 | Mujtaba Ahmad | Mujtaba Ahmad | EM |  |  |  |  | Yes | Chaotic | 3 | 3 | 5 | 5 | Yes | 4 | 5 | SME/Epic Owner/EM/QM (Pre Defined Efforts Estimates) | 5 | 5 | Yes | YES | Multiple | Less than 10% | Yes | Multiple | Balanced (80% - 90%) | Some Information but still need further details | Yes | Not Well | Continuous Epic Grooming | Sprint Retrospective | Non Release Activity Identification & capacity reserve | Change in Due date and QA Sign off Date restrictions | None | Delay in commitments from dependant team | My role involves process improvement and enablement (EM's, SM's & Other folks responsible for process streamlining) |  | YES | NA |  |  | Yes | Exploring / understanding existing codebase | 20% to 50% | Analysing critical bugs | NA | NA
2025-09-22 11:58 | Krishna Kishore Mothukuri | Ajitkumar kaller | Dev | Velocity | 5 | Yes | Major was regarding project allocation and was going well | Yes | Balanced | 4 | 3 | 4 | 4 | Partially/Incomplete | 4 | 5 | Individual | 5 | 4 | Yes | YES | Moderate | 20% to 30% | Yes | Moderate | Balanced (80% - 90%) | Some Information but still need further details | Yes | Average | Epic Breakdown | Sprint Planning | KT and recording repository | Change in Due date and QA Sign off Date restrictions | Release Planning, Strategy & Schedule (Proper Checkpoint and dates on jira tickets) | Improper Epic Breakdown & Estimations - Missing Sprint Backlog | More than 20% |  | YES | Epic breakdown and KT should be done in very depth , 60% TIME should be spent on this |  |  | Yes | Dev Prototype, Writing code for new features, Debugging and Fixing Bugs, Writing Unit tests, Creating test cases or test scripts | 20% to 50% | It helped in Improving and optimisation | We should show the user how much he is consuming the cusor , so that he has a responsibility to use it only for productive things . | yes
2025-09-22 12:06 | Mohammed Fayaz | Prasad Deverakonda | QA | Astra | 5 | Yes | . | Yes | Balanced | 5 | 5 | 5 | 5 | Yes | 5 | 5 | Individual | 4 | 4 | Yes | YES | Moderate | Less than 10% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Average | Continuous Epic Grooming | Sprint Planning | Test Design | Strict Bug SLA's | Better & transparent commitments | Communication gap b/w dependent teams | Less than 5% | . | YES | . | . |  | Yes | Exploring / understanding existing codebase, Writing code for new features, Creating test cases or test scripts | 20% to 50% | It helped a lot during automating the rest api test cases | . | .
2025-09-22 12:17 | Jegadeesh Santhana Krishnan | Subhan Ansari | Dev | Skywalker | 3 | Yes | NA | Yes | Chaotic | 3 | 4 | 5 | 4 | Yes | 4 | 4 | Individual | 4 | 4 | Yes | YES | None | More than 30% | No | Multiple | Over Utilised (90% and Above) | Optimal information available | Yes | Well Managed | Committed Epic Prioritisation | Sprint Closure/review | Ad-hoc requests prioritisation and acceptance | Strict Bug SLA's | None | Ad-hoc Tasks & improper prioritisation | More Than 5% but less than 10% |  | YES | Please account for adhoc and release activities |  |  | Yes | Dev Prototype, Exploring / understanding existing codebase, Writing code for new features, Review PRs, Debugging and Fixing Bugs, Writing Unit tests, Creating test cases or test scripts | Greater than 50% | It helped me debug critical P1 bugs and updating agent automation pipeline in just few seconds. | NA | NA
2025-09-22 13:17 | Mujtaba Ahmad | Hemant Agrawal | Dev | Titans | 5 | Yes | Effective jira usage | Yes | Chaotic | 3 | 5 | 5 | 5 | Partially/Incomplete | 5 | 5 | Scrum Team | 5 | 5 | Yes | YES | Moderate | 10% to 20% | Yes | Moderate | Over Utilised (90% and Above) | Some Information but still need further details | Yes | Not Well | Committed Epic Prioritisation | Sprint Planning | Intra Team Collaboration - Dependency linking on Jira by Individual owners | Blocking Scope change | None | Delay in commitments from dependant team | Less than 5% |  | YES | Epic prioritisation could be improved so we don’t wait until the last minute to prioritise an epic. |  |  | Yes | Dev Prototype, Exploring / understanding existing codebase, Writing code for new features, Review PRs, Debugging and Fixing Bugs, Writing Unit tests, Creating test cases or test scripts | 20% to 50% | Increasing code coverage | NA | Yes
2025-09-22 14:22 | Jegadeesh Santhana Krishnan | Subhan Ansari | Dev | Skywalker | 5 | Yes | spillovers and ad hoc items were reduced | Yes | Balanced |  |  |  |  | Yes |  |  | Individual |  |  | Yes | YES | Moderate | 10% to 20% | Yes |  |  | Some Information but still need further details | Yes | Average | Code Freeze Milestones and hardening phase | Sprint Planning | Ad-hoc requests prioritisation and acceptance | Change in Due date and QA Sign off Date restrictions | Reduced over commit | Ad-hoc Tasks & improper prioritisation | Less than 5% |  | YES | hardening and code freeze |  |  | Yes | Exploring / understanding existing codebase, Writing code for new features, Debugging and Fixing Bugs, Writing Unit tests | Less than 10% | Bug finding, UTs | None | -
2025-09-22 16:12 | Mohammed Fayaz | Anusha Jharupula | QA | Falcon | 4 | Yes | Issues call out in DSU's | Yes | Balanced | 4 | 4 | 4 | 4 | Yes | 4 | 4 | Scrum Team | 4 | 4 | Yes | YES | Multiple | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Committed Epic Prioritisation | Sprint Closure/review | Non Release Activity Identification & capacity reserve | Change in Due date and QA Sign off Date restrictions | Better & transparent commitments | PR Merges | More than 10% but Less than 20% |  | YES | Adding more buffer considering any unplanned leaves |  |  | Yes | Exploring / understanding existing codebase, Creating test cases or test scripts | 20% to 50% | Identifying the pattern of handlebars in production and fields in which the handlebars are used | cross validation and analysis is little difficult | yes
2025-09-22 16:28 | Mohammed Fayaz | Anusha Jharupula | QA | Falcon | 3 | No Action items | None | Yes | Balanced | 4 | 4 | 4 | 4 | Yes | 4 | 4 | Scrum Team | 4 | 4 | Yes | Moderately | Moderate | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Some Information but still need further details | Yes | Well Managed | Continuous Epic Grooming | Sprint Planning | CI/CD, Testing & Continuous planning | Change in Due date and QA Sign off Date restrictions | None | Communication gap b/w dependent teams | More Than 5% but less than 10% |  | YES | None |  |  | Yes | Exploring / understanding existing codebase, Creating test cases or test scripts | 20% to 50% | None | None | None
2025-09-22 16:49 | Jegadeesh Santhana Krishnan | Chandra Sekhar Kusupati | Dev | Eirene | 5 | No Action items | NA | Yes | Balanced | 5 | 5 | 5 | 5 | Yes | 5 | 5 | Scrum Team | 5 | 5 | Yes | YES | Moderate | Less than 10% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Epic Breakdown | Sprint Closure/review | Non Release Activity Identification & capacity reserve | Blocking Scope change | Release Planning, Strategy & Schedule (Proper Checkpoint and dates on jira tickets) | Delayed Response on open Queries, need multiple followups | More than 10% but Less than 20% |  | YES | No |  |  | Yes | Dev Prototype, Exploring / understanding existing codebase, Writing code for new features, Review PRs, Debugging and Fixing Bugs, Writing Unit tests, Creating test cases or test scripts | 20% to 50% | For understanding existing code and to find the relevant component/code easliy and to fix/modify the code at a faster rate. | No | Yes
2025-09-22 16:52 | Mujtaba Ahmad | Raman Soni | Dev & Scrum Master | Ganges | 4 | Yes | we took an action item to prioritise the test coverage in order of unit test>component test>rest api tests, and we are following it. | Yes | Chaotic | 3 | 5 | 5 | 5 | Yes | 4 | 4 | Scrum Team | 4 | 4 | Yes | YES | Moderate | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Some Information but still need further details | Yes | Average | Code Freeze Milestones and hardening phase | Sprint Planning | Ad-hoc requests prioritisation and acceptance | Risk call out during Weekly SoS | Efficient Jira Usage (New Fields such as - Due date, QA Lead, QA Involvement, QA Signoff date) | Ad-hoc Tasks & improper prioritisation | More than 10% but Less than 20% |  | YES | no |  |  | Yes | Exploring / understanding existing codebase, Writing code for new features, Review PRs, Writing Unit tests | Greater than 50% | it helped me understand the workflow of a code which was completely new to me | it needs to improve on writing the unit tests. Even on priding enough context and detailed prompt, it is not able to write correct and crisp tests | yes
2025-09-22 18:47 | Jegadeesh Santhana Krishnan | Jegadeesh Santhana Krishnan | Architect/Individual Contributors |  |  |  |  | No | [32 empty] | Design approvals | Yes | Dev Prototype, Exploring / understanding existing codebase, Review PRs, analysis of data | 20% to 50% | Had to do analysis of data from jira and able to develop scripts to pull data and analyse it using AI models | Expect folks to share via cursor adoption channel on thier expiriments | yes
2025-09-22 19:32 | Mujtaba Ahmad | Hemant Agrawal | Dev | Enigma | 5 | Yes | Try to get the trackers delivered incrementally | Yes | Well Managed | 5 | 5 | 5 | 5 | Yes | 5 | 5 | Scrum Team | 5 | 5 | Yes | YES | Moderate | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Continuous Epic Grooming | Sprint Planning | CI/CD, Testing & Continuous planning | Blocking Scope change | Release Planning, Strategy & Schedule (Proper Checkpoint and dates on jira tickets) | Ad-hoc Tasks & improper prioritisation | More Than 5% but less than 10% |  | YES | n/a |  |  | Yes | Dev Prototype, Exploring / understanding existing codebase, Writing code for new features, Review PRs, Debugging and Fixing Bugs, Writing Unit tests | 20% to 50% | Able to develop POC using cursor quickly and make changes, Got good help while doing local setup | n/a | yes, getting the suppport
2025-09-22 19:37 | Mohammed Fayaz | Tharuni Sai Idupulapati | QA | Stark | 4 | Yes | Actively monitoring alerts | Yes | Chaotic | 2 | 3 | 3 | 3 | Partially/Incomplete | 4 | 4 | Scrum Team | 4 | 4 | Yes | YES | Moderate | Less than 10% | No | Multiple | Over Utilised (90% and Above) | Optimal information available | Yes | Average | Continuous Epic Grooming | Sprint Planning | Ad-hoc requests prioritisation and acceptance | Risk call out during Weekly SoS | None | Ad-hoc Tasks & improper prioritisation | Less than 5% |  | YES | - |  |  | Yes | Exploring / understanding existing codebase, Debugging and Fixing Bugs, Creating test cases or test scripts | 20% to 50% | Helped me to test 13k prod scripts easily | - | Yes
2025-09-22 19:47 | Mujtaba Ahmad | Hemant Agrawal | EM |  |  |  |  | No | [32 empty] | Team Management and Resource Planning | Yes | Exploring / understanding existing codebase, Review PRs | 20% to 50% | NA | NA | Yes
2025-09-22 19:57 | Mohammed Fayaz | Tharuni Sai Idupulapati | QA | Ganges | 5 | Yes | Coming up with the automation strategy for a new epic, like unit - component - rest | Yes | Balanced | 5 | 5 | 5 | 5 | Yes | 5 | 5 | Scrum Team | 5 | 5 | Yes | YES | Moderate | 10% to 20% | Yes | None | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Committed Epic Prioritisation | Sprint Planning | CI/CD, Testing & Continuous planning | Blocking Scope change | Risk call out (Release Confluence Page) | Modifications on Approved Tech designs | More Than 5% but less than 10% | Nothing | YES | Nothing | Nothing |  | Yes | Exploring / understanding existing codebase, Debugging and Fixing Bugs, Creating test cases or test scripts | 20% to 50% | There was an epic related to handle bar helpers in this sept release, cursor gave me lot of possible input-output combinations | Nothing | yes getting good support
2025-09-22 19:57 | Mohammed Fayaz | Tharuni Sai Idupulapati | Architect/Individual Contributors |  |  |  |  | Yes | Balanced | 4 | 4 | 2 | 4 | Yes | 3 | 4 | Individual | 3 | 3 | Yes | YES | Moderate | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Some Information but still need further details | Yes | Average | Monitoring and Controlling Progress | Sprint Closure/review | Ad-hoc requests prioritisation and acceptance | Change in Due date and QA Sign off Date restrictions | Better Estimations & Epic Breakdown | Reviews | More Than 5% but less than 10% |  | Not Efficiently | NA |  |  | Yes | Exploring / understanding existing codebase, Writing code for new features, Creating test cases or test scripts | 20% to 50% | NA | NA | NA
2025-09-22 20:15 | Mohammed Fayaz | Varun Batra | QA | Tintin | 5 | No |  | Yes | Balanced | 4 | 4 | 4 | 4 | Yes | 4 | 4 | Scrum Team | 4 | 4 | Yes | Moderately | Moderate | Less than 10% | Yes | Moderate | Balanced (80% - 90%) | Some Information but still need further details | Yes | Average | Code Freeze Milestones and hardening phase | Sprint Planning | Ad-hoc requests prioritisation and acceptance | Blocking Scope change | Risk call out (Release Confluence Page) | Ad-hoc Tasks & improper prioritisation | More Than 5% but less than 10% |  | YES | NA | NA |  | Yes | Exploring / understanding existing codebase, Writing code for new features, Review PRs, Debugging and Fixing Bugs, Creating test cases or test scripts, Impact analysis, validating the report failures, fixing the failed automation test cases | 20% to 50% | Solving the hacker one scenario. | NA | NA
2025-09-22 20:19 | Mohammed Fayaz | Varun Batra | QA | Avengers | 5 | No Action items | NA | Yes | Balanced | 4 | 4 | 4 | 4 | Yes | 4 | 4 | Scrum Team | 4 | 4 | Yes | YES | Moderate | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Average | Monitoring and Controlling Progress | Sprint Planning | Ad-hoc requests prioritisation and acceptance | Blocking Scope change | Release Planning, Strategy & Schedule (Proper Checkpoint and dates on jira tickets) | Ad-hoc Tasks & improper prioritisation | More Than 5% but less than 10% |  | YES | NA |  |  | Yes | Exploring / understanding existing codebase, Review PRs, Debugging and Fixing Bugs, Creating test cases or test scripts, impact analysis and test case designs | 20% to 50% | Fixed multiple cases in a suite a found the root cause of failing cases. | Help in understanding and debugging issues | yes
2025-09-22 20:42 | Jegadeesh Santhana Krishnan | Ashok Kumar Dantham | Dev | Iris | 5 | No Action items | NA | Yes | Well Managed | 5 | 4 | 5 | 5 | Yes | 4 | 5 | Scrum Team | 5 | 5 | Yes | YES | Moderate | 10% to 20% | Yes | None | Balanced (80% - 90%) | Optimal information available | Yes | Average | Committed Epic Prioritisation | Sprint Planning | Intra Team Collaboration - Dependency linking on Jira by Individual owners | Risk call out during Weekly SoS | Better & transparent commitments | Improper Epic Breakdown & Estimations - Missing Sprint Backlog | Less than 5% |  | YES | Na |  |  | Yes | Dev Prototype, Writing code for new features, Review PRs, Debugging and Fixing Bugs, Writing Unit tests, Creating test cases or test scripts | 20% to 50% | . | . | Yeah
2025-09-22 20:51 | Mohammed Fayaz | Varun Batra | QA | Aliens | 4 | No |  | Yes | Chaotic | 3 | 4 | 4 | 4 | Partially/Incomplete | 4 | 4 | Scrum Team | 4 | 4 | Yes | YES | Moderate | Less than 10% | No | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Code Freeze Milestones and hardening phase | Sprint Planning | Jira Details - Epic breakdown, DoD, Exit criteria, CS Bugs | Risk call out during Weekly SoS | Better Estimations & Epic Breakdown | Ad-hoc Tasks & improper prioritisation | Less than 5% |  | YES | Checking the priority of the epic committed and stick to it |  |  | Yes | Exploring / understanding existing codebase, Review PRs, Creating test cases or test scripts | 20% to 50% | NA | NA | Yes
2025-09-22 20:57 | Jegadeesh Santhana Krishnan | Selvakumar Thiyagarajan | EM |  |  |  |  | Yes | Well Managed | 5 | 5 | 5 | 5 | Yes | 5 | 5 | Scrum Team | 5 | 5 | Yes | YES | Multiple | 10% to 20% | Yes | None | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Code Freeze Milestones and hardening phase | Sprint Retrospective | Bugs Management & Deferring | Change in Due date and QA Sign off Date restrictions | None | Communication gap b/w dependent teams | My role involves process improvement and enablement (EM's, SM's & Other folks responsible for process streamlining) |  | YES | No |  |  | Yes | Dev Prototype | Less than 10% | Easy to work on POC | No | Yes
2025-09-22 21:05 | Jegadeesh Santhana Krishnan | Rajesh Subramani | Dev | Helios | 5 | No Action items | No action item | No | [32 empty] | Automation and bugs | Yes | Exploring / understanding existing codebase, Writing code for new features, Debugging and Fixing Bugs, Writing Unit tests | 20% to 50% | no such case | no | yes
2025-09-22 21:06 | Jegadeesh Santhana Krishnan | Ashok Kumar Dantham | Dev | Iris | 5 | Yes | 1. Dev need to submit automation report and Figma report(if required) as part of PR. 2. PR should be reviewed by 2 person (1 team and 1 other team member) 3. Skeleton need to be provided by QA for each story and bug and as part of code tracker dev will validate it. 4. Manual task to be added only in Epic level. | Yes | Balanced | 4 | 5 | 5 | 5 | Yes | 5 | 5 | Individual | 5 | 5 | Yes | YES | None | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Some Information but still need further details | Yes | Well Managed | Continuous Epic Grooming | Sprint Planning | Intra Team Collaboration - Dependency linking on Jira by Individual owners | Blocking Scope change | Better & transparent commitments | Intra team collaboration | More Than 5% but less than 10% |  | YES | - |  |  | Yes | Dev Prototype, Exploring / understanding existing codebase, Writing code for new features, Review PRs, Debugging and Fixing Bugs, Writing Unit tests, Creating test cases or test scripts | 20% to 50% | Writing Unit tests. Implement figma designs | - | Yes
2025-09-22 21:37 | Mujtaba Ahmad | Hemant Agrawal | Dev & Scrum Master | Enigma | 5 | Yes | Splitting the stories into much shorter, that improved the burndown chart much better than previous stats. | Yes | Well Managed | 5 | 5 | 5 | 5 | Yes | 5 | 5 | Scrum Team | 5 | 5 | Yes | YES | Moderate | Less than 10% | Yes | None | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Continuous Epic Grooming | Sprint Planning | Ad-hoc requests prioritisation and acceptance | Strict Bug SLA's | Better Estimations & Epic Breakdown | Communication gap b/w dependent teams | More Than 5% but less than 10% |  | YES | No |  |  | Yes | Dev Prototype, Writing code for new features, Review PRs, Debugging and Fixing Bugs, Writing Unit tests | Greater than 50% | Working on new features by providing design specifications as text files to Cursor for development kickoff. | No | Receiving sufficient support across all forums.
2025-09-22 21:38 | Jegadeesh Santhana Krishnan | Selvakumar Thiyagarajan | Dev | Chloris | 4 | No Action items | - | Yes | Balanced | 4 | 4 | 4 | 4 | Yes | 4 | 4 | Scrum Team | 4 | 4 | Yes | YES | Moderate | 10% to 20% | Yes | Moderate | Over Utilised (90% and Above) | Optimal information available | Yes | Average | Release Kick Off | Sprint Closure/review | Test Design | Risk call out during Weekly SoS | Dependency management | Ad-hoc Tasks & improper prioritisation | More Than 5% but less than 10% |  | YES | - | - |  | Yes | Exploring / understanding existing codebase, Writing code for new features, Debugging and Fixing Bugs, Writing Unit tests | 20% to 50% | - | - | -
2025-09-22 22:02 | Jegadeesh Santhana Krishnan | Chandra Sekhar Kusupati | Dev & Scrum Master | Helios | 4 | No |  | Yes | Balanced | 3 | 4 | 4 | 4 | Yes | 4 | 4 | Scrum Team | 5 | 4 | Yes | YES | Moderate | 20% to 30% | Yes | Moderate | Balanced (80% - 90%) | Some Information but still need further details | Yes | Average | Code Freeze Milestones and hardening phase | Sprint Retrospective | Intra Team Collaboration - Dependency linking on Jira by Individual owners | Change in Due date and QA Sign off Date restrictions | None | Intra team collaboration | More Than 5% but less than 10% |  | YES | NA | NA |  | Yes | Dev Prototype, Exploring / understanding existing codebase, Writing code for new features, Review PRs, Debugging and Fixing Bugs, Writing Unit tests, Creating test cases or test scripts | 20% to 50% | Analysis critical bugs and gives solutions, At same time debugging issues in this code beccomes problem since we dont know entire code which it wrote for completion of a feature | NA | NA
2025-09-22 22:04 | Krishna Kishore Mothukuri | Ajitkumar kaller | Dev | Velocity | 4 | Yes | N/a | Yes | Balanced | 4 | 4 | 4 | 4 | Yes | 5 | 4 | Scrum Team | 4 | 4 | Yes | YES | Moderate | Less than 10% | Yes | Multiple | Over Utilised (90% and Above) | Optimal information available | Yes | Well Managed | Continuous Epic Grooming | Sprint Planning | Non Release Activity Identification & capacity reserve | Change in Due date and QA Sign off Date restrictions | Dependency management | Non Release Activities | Less than 5% | N/a | YES | n/a | Subtasks of the story are not accounted until we close the story, Ideal sprint doesn't work in this way. |  | Yes | Dev Prototype, Exploring / understanding existing codebase, Writing code for new features, Debugging and Fixing Bugs, Creating test cases or test scripts | 20% to 50% | I am able to construct complete langgraph in a single prompt. | Individual metrics is based on number of hits, ideally a good prompt doesn't require much hits, Is this right way to calculate usage? | yes
2025-09-22 22:27 | Jegadeesh Santhana Krishnan | Chandra Sekhar Kusupati | Dev | Eirene | 4 | Yes | adhering to deadlines | Yes | Balanced | 3 | 3 |  | 3 | Yes | 3 | 3 | Scrum Team | 3 | 3 | Yes | YES | Moderate | 10% to 20% | Yes | None | Balanced (80% - 90%) | Some Information but still need further details | Yes | Average | Monitoring and Controlling Progress | Sprint Planning | Intra Team Collaboration - Dependency linking on Jira by Individual owners | Risk call out during Weekly SoS | Better Estimations & Epic Breakdown | Communication gap b/w dependent teams | More than 10% but Less than 20% |  | YES | . |  |  | Yes | Dev Prototype, Exploring / understanding existing codebase, Writing code for new features, Review PRs, Debugging and Fixing Bugs, Writing Unit tests, Creating test cases or test scripts | 20% to 50% | Cursor helped me really well in epic breakdown, which took me 2 hours with the help of cursor, if I had to do the same manually it would have taken me 1 complete day. | helpful as a pair programmer and helping boost productivity | yes
2025-09-22 22:28 | Mujtaba Ahmad | Mujtaba Ahmad | EM |  |  |  |  | No | [33 empty] | Yes | Dev Prototype, Writing code for new features | 20% to 50% | Building documentation | It's going at the apt pace | Yes
2025-09-22 22:33 | Jegadeesh Santhana Krishnan | Ashok Kumar Dantham | Dev | Aurora | 4 | Yes | better UX support | Yes | Balanced | 4 | 5 | 5 | 5 | Yes | 5 | 5 | Scrum Team | 5 | 5 | Yes | YES | Moderate | 10% to 20% | Yes | None | Balanced (80% - 90%) | Optimal information available | Yes | Average | Committed Epic Prioritisation | Sprint Planning | Intra Team Collaboration - Dependency linking on Jira by Individual owners | Blocking Scope change | Effective communication | Delay in commitments from dependant team | Less than 5% |  | YES | better dependency management |  |  | Yes | Dev Prototype, Exploring / understanding existing codebase, Writing code for new features, Debugging and Fixing Bugs, Writing Unit tests, Creating test cases or test scripts | 20% to 50% | making styling changes based on figma MCP worked well | more open source models | yes
2025-09-22 22:34 | Jegadeesh Santhana Krishnan | Anusha Badveeti | Dev | Tranformers | 5 | Yes | - | Yes | Well Managed | 5 | 5 | 5 | 5 | Yes | 5 | 5 | Scrum Team | 5 | 5 | Yes | YES | Moderate | 10% to 20% | Yes | Moderate | Over Utilised (90% and Above) | Optimal information available | Yes | Well Managed | Epic Breakdown | Sprint Planning | Tech Design | Blocking Scope change | Release Planning, Strategy & Schedule (Proper Checkpoint and dates on jira tickets) | Ad-hoc Tasks & improper prioritisation | More Than 5% but less than 10% |  | YES | - |  |  | Yes | Dev Prototype, Exploring / understanding existing codebase, Writing code for new features, Debugging and Fixing Bugs, Writing Unit tests | Less than 10% | - | - | -
2025-09-22 22:37 | Jegadeesh Santhana Krishnan | Selvakumar Thiyagarajan | Dev | Pheonix | 5 | Yes | Supporting typeAhead on Static maps and export select | Yes | Well Managed | 5 | 5 | 5 | 5 | Yes | 5 | 5 | Scrum Team | 5 | 5 | Yes | YES | Multiple | Less than 10% | Yes | None | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Epic Breakdown | Sprint Closure/review | Jira Details - Epic breakdown, DoD, Exit criteria, CS Bugs | Risk call out during Weekly SoS | Efficient Jira Usage (New Fields such as - Due date, QA Lead, QA Involvement, QA Signoff date) | Improper Epic Breakdown & Estimations - Missing Sprint Backlog | Less than 5% |  | YES | NA |  |  | Yes | Dev Prototype, Exploring / understanding existing codebase, Writing code for new features, Review PRs, Debugging and Fixing Bugs, Writing Unit tests | Greater than 50% | Helped me come up with interesting approaches to problems. | NA | Yes.
2025-09-23 07:50 | Mujtaba Ahmad | Raman Soni | Dev | Stark | 5 | No Action items | NA | Yes | Well Managed | 5 | 5 | 5 | 5 | Yes | 5 | 5 | Scrum Team | 5 | 5 | Yes | YES | Multiple | Less than 10% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Epic Breakdown | Sprint Planning | Ad-hoc requests prioritisation and acceptance | Change in Due date and QA Sign off Date restrictions | Effective communication | Ad-hoc Tasks & improper prioritisation | Less than 5% |  | YES | NA |  |  | Yes | Exploring / understanding existing codebase, Writing code for new features, Review PRs, Debugging and Fixing Bugs, Writing Unit tests | 20% to 50% | It Helped me for research kind of tasks | NA | Yes
2025-09-23 08:54 | Mohammed Fayaz | Tharuni Sai Idupulapati | QA | Zeta | 5 | Yes | NA | Yes | Balanced | 5 | 5 | 5 | 5 | Yes | 5 | 5 | Scrum Team | 5 | 5 | Yes | YES | Multiple | 10% to 20% | Yes | Moderate | Over Utilised (90% and Above) | Optimal information available | Yes | Well Managed | Epic Breakdown | Sprint Planning | Jira Details - Epic breakdown, DoD, Exit criteria, CS Bugs | Change in Due date and QA Sign off Date restrictions | Better Estimations & Epic Breakdown | Ad-hoc Tasks & improper prioritisation | Less than 5% |  | YES | NA | NA |  | Yes | Creating test cases or test scripts | 20% to 50% | writing testcases and debugging | No | yes
2025-09-23 09:14 | Jegadeesh Santhana Krishnan | Ashok Kumar Dantham | Dev & Scrum Master | Iris | 5 | Yes | Don't accept Figma changes post scoping sprint. | Yes | Well Managed | 5 | 5 | 5 | 5 | Yes | 5 | 5 | Individual | 5 | 5 | Yes | YES | Multiple | Less than 10% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Code Freeze Milestones and hardening phase | Sprint Closure/review | Intra Team Collaboration - Dependency linking on Jira by Individual owners | Strict Bug SLA's | Effective communication | Delay in commitments from dependant team | My role involves process improvement and enablement (EM's, SM's & Other folks responsible for process streamlining) |  | YES |  |  |  | Yes | Dev Prototype, Exploring / understanding existing codebase, Writing code for new features, Review PRs, Debugging and Fixing Bugs, Writing Unit tests, Creating test cases or test scripts | 20% to 50% | It helped me with React 18-19 upgradation, specially the unit testcase fixes. |  | Yes
2025-09-23 09:31 | Mujtaba Ahmad | Ranjith Kumar M | Dev | Zeta | 4 | Yes | Have reserve bandwidth with each dev to accommodate adhoc and still get everything closed by end of sprint | No | [33 empty] | Yes | Dev Prototype, Exploring / understanding existing codebase, Writing code for new features, Review PRs, Debugging and Fixing Bugs, Writing Unit tests, Creating test cases or test scripts | Greater than 50% | It let me fix the bug in an open source library on its own | Use rules and evolve them ove time to make it more personal to your need | Yes
2025-09-23 09:45 | Mujtaba Ahmad | Priya Vanteru | Dev | Falcon | 4 | No |  | Yes | Chaotic | 1 | 4 | 3 | 3 | Partially/Incomplete | 2 | 4 | Scrum Team | 4 | 4 | Yes | NO | Moderate | 20% to 30% | Yes | Moderate | Over Utilised (90% and Above) | Some Information but still need further details | Not aware and did not find any significant change in the release coordination among teams | Not Well | Epic Breakdown | Sprint Closure/review | Backlog & CS bugs prioritisation | Blocking Scope change | None | Communication gap b/w dependent teams | More Than 5% but less than 10% | aws-sdk changes were chaotic due to bad planning | Not Efficiently | Better planning and ownership | NA |  | Yes | Exploring / understanding existing codebase, Writing code for new features, Review PRs, Debugging and Fixing Bugs, Writing Unit tests, Creating test cases or test scripts | 20% to 50% | NA | NA | Yes
2025-09-23 09:52 | Mujtaba Ahmad | Priya Vanteru | Dev | Falcon | 3 | Yes | Worked on the aws-sdk upgrade. | Yes | Chaotic | 3 | 2 | 1 | 3 | Partially/Incomplete | 4 | 5 | Scrum Team | 5 | 5 | Yes | Moderately | Moderate | 10% to 20% | Yes | None | Over Utilised (90% and Above) | Some Information but still need further details | Yes | Well Managed | Continuous Epic Grooming | Sprint Retrospective | KT and recording repository | Risk call out during Weekly SoS | Risk call out (Release Confluence Page) | Communication gap b/w dependent teams | More than 10% but Less than 20% |  | YES | No |  |  | Yes | Exploring / understanding existing codebase, Debugging and Fixing Bugs, Writing Unit tests | 20% to 50% | Cursor helped me to understand the code flow for a complicated bug. | no | yes
2025-09-23 09:52 | Mujtaba Ahmad | Priya Vanteru | Dev & Scrum Master | Indus | 4 | No Action items | N/A | Yes | Balanced | 3 | 4 | 4 | 4 | Yes | 3 | 4 | Scrum Team | 4 | 3 | Yes | YES | Multiple | 10% to 20% | Yes | Multiple | Over Utilised (90% and Above) | Optimal information available | Yes | Average | Epic Breakdown | Sprint Closure/review | Intra Team Collaboration - Dependency linking on Jira by Individual owners | Blocking Scope change | Better Estimations & Epic Breakdown | Communication gap b/w dependent teams | Less than 5% |  | YES | No |  |  | Yes | Dev Prototype, Exploring / understanding existing codebase, Writing code for new features, Review PRs, Debugging and Fixing Bugs, Writing Unit tests | 20% to 50% | It has helped me a lot in designing the new java-bridge-on-prem functionality. | No | Yes
2025-09-23 09:56 | Mujtaba Ahmad | Priya Vanteru | Dev | Falcon | 4 | Yes | NA | Yes | Balanced | 4 | 4 | 4 | 3 | Yes | 4 | 4 | Scrum Team | 4 | 4 | No | Moderately | Moderate | 20% to 30% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Code Freeze Milestones and hardening phase | Sprint Planning | Backlog & CS bugs prioritisation | Strict Bug SLA's | Better Estimations & Epic Breakdown | Missing SLA's for Bugs, Trackers on Jira | More than 20% |  | YES | Nothing |  |  | Yes | Exploring / understanding existing codebase | Greater than 50% | It’s really helpful in understanding code base | nothing | Yes
2025-09-23 10:01 | Mujtaba Ahmad | Priya Vanteru | Dev | Indus | 5 | Yes | NA | Yes | Balanced | 5 | 5 | 5 | 4 | Yes | 4 | 4 | Scrum Team | 4 | 4 | Yes | YES | Multiple | 20% to 30% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Continuous Epic Grooming | Sprint Planning | Tech Design | Strict Bug SLA's | Effective communication | Improper Epic Breakdown & Estimations - Missing Sprint Backlog | More Than 5% but less than 10% |  | YES | NA |  |  | Yes | Exploring / understanding existing codebase, Writing code for new features, Review PRs, Debugging and Fixing Bugs, Writing Unit tests | 20% to 50% | NA | NA | NA
2025-09-23 10:03 | Mujtaba Ahmad | Priya Vanteru | Dev & Scrum Master | Falcon | 4 | Yes | working on how to improve the cross team collaboration, basically for this sprint it was exception for aws-sdk | Yes | Chaotic | 3 | 5 | 5 | 5 | Yes | 4 | 4 | Scrum Team | 4 | 4 | Yes | YES | Multiple | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Not aware of any such initiative. Though the release coordination among teams was better than previous releases among teams | Average | Committed Epic Prioritisation | Sprint Closure/review | Ad-hoc requests prioritisation and acceptance | Blocking Scope change | Effective communication | PR Merges | More Than 5% but less than 10% |  | YES | NA |  |  | Yes | Dev Prototype, Exploring / understanding existing codebase, Writing code for new features, Review PRs, Writing Unit tests | 20% to 50% | In recent development, there was a case with working on data stream, where we need to copy the stream & consume it in other place there was also a retry mechanism, so cursor highlighted the issue that the retry mechanism would break if the main stream closes & there can be a chance of data loss too. | NA | Yes
2025-09-23 10:05 | Mujtaba Ahmad | Priya Vanteru | Dev | Indus | 5 | Yes | discussing with team, manager | Yes | Balanced | 4 | 4 | 5 | 5 | Yes | 4 | 4 | Scrum Team | 5 | 5 | Yes | YES | Multiple | 20% to 30% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Continuous Epic Grooming | Sprint Closure/review | Ad-hoc requests prioritisation and acceptance | Risk call out during Weekly SoS | Effective communication | Intra team collaboration | More Than 5% but less than 10% | NA | YES | NA | NA |  | Yes | Dev Prototype, Exploring / understanding existing codebase, Writing code for new features, Review PRs, Debugging and Fixing Bugs | Greater than 50% | helped in enhancing routing feature for ms services, built a mini project to run enhanced routing algo in isto | NA | Yes
2025-09-23 10:08 | Mujtaba Ahmad | Priya Vanteru | Dev | Indus | 5 | Yes | continous grooming | Yes | Balanced | 5 | 5 | 4 | 5 | Yes | 4 | 4 | Scrum Team | 5 | 4 | Yes | YES | Moderate | 10% to 20% | Yes | Multiple | Balanced (80% - 90%) | Optimal information available | Not aware of any such initiative. Though the release coordination among teams was better than previous releases among teams | Average | Continuous Epic Grooming | Sprint Planning | Bugs Management & Deferring | Risk call out during Weekly SoS | Efficient Jira Usage (New Fields such as - Due date, QA Lead, QA Involvement, QA Signoff date) | Reviews | Less than 5% |  | YES | no |  |  | Yes | Dev Prototype, Exploring / understanding existing codebase, Writing code for new features, Review PRs, Debugging and Fixing Bugs, Writing Unit tests, Creating test cases or test scripts | 20% to 50% | Recently httpmockserver's token got updated which resulted in failure of many automation tests. Cursor was able to fix that with a single prompt with little manual intervention. | no | yes via slack
2025-09-23 10:20 | Mujtaba Ahmad | Ranjith Kumar M | Dev | Zeta | 3 | No Action items | NA | Yes | Balanced | 3 | 3 | 3 | 3 | Yes | 3 | 3 | SME/Epic Owner/EM/QM (Pre Defined Efforts Estimates) | 3 | 3 | Yes | YES | Moderate | Less than 10% | No | Moderate | Over Utilised (90% and Above) | Optimal information available | Yes | Average | Committed Epic Prioritisation | Sprint Planning | Jira Details - Epic breakdown, DoD, Exit criteria, CS Bugs | Strict Bug SLA's | Efficient Jira Usage (New Fields such as - Due date, QA Lead, QA Involvement, QA Signoff date) | Ad-hoc Tasks & improper prioritisation | More than 10% but Less than 20% |  | YES | Reduce JIRA fields and processes |  |  | Yes | Dev Prototype, Exploring / understanding existing codebase, Writing code for new features, Review PRs, Debugging and Fixing Bugs, Writing Unit tests, Creating test cases or test scripts | 20% to 50% | Gave reference to multiple PRs of an EPIC for different repo and it generated TCs with mocking those repo code | NA | Yes
2025-09-23 10:37 | Mujtaba Ahmad | Anurag Goyal | Dev | Titans | 5 | Yes | Better planning to close tasks in the same sprint and leave some buffer for adhocs | Yes | Well Managed | 5 | 5 | 5 | 5 | Yes | 4 | 4 | Scrum Team | 5 | 5 | Yes | YES | Moderate | Less than 10% | No | Multiple | Over Utilised (90% and Above) | Optimal information available | Not aware of any such initiative. Though the release coordination among teams was better than previous releases among teams | Average | Committed Epic Prioritisation | Sprint Planning | CI/CD, Testing & Continuous planning | Blocking Scope change | None | Ad-hoc Tasks & improper prioritisation | Less than 5% |  | YES | N/A |  |  | Yes | Dev Prototype, Exploring / understanding existing codebase, Review PRs, Debugging and Fixing Bugs, Writing Unit tests, Creating test cases or test scripts | 20% to 50% | Preparing api documentation by reducing significant time | N/A | N/A
2025-09-23 11:01 | Mujtaba Ahmad | Ranjith Kumar M | Dev | Gryffindor | 5 | Yes | Change in priorities were strictly restricted and team followed the same in the sprint. | Yes | Chaotic | 2 | 2 | 2 | 2 | Partially/Incomplete | 3 | 4 | Scrum Team | 5 | 5 | Yes | Moderately | Moderate | Less than 10% | No | Multiple | Over Utilised (90% and Above) | Some Information but still need further details | Yes | Average | Committed Epic Prioritisation | Sprint Closure/review | Intra Team Collaboration - Dependency linking on Jira by Individual owners | Blocking Scope change | None | Delay in commitments from dependant team | More Than 5% but less than 10% |  | YES | NA | NA |  | Yes | Exploring / understanding existing codebase, Review PRs, Writing Unit tests | 20% to 50% | Identified an issue where with xml parser intermittent records were getting dropped and we were not able to replicate it in local due to local constraints. After exploring through splunk logs and cursor was able to find the root-cause of the issue. | Overall I find it very useful in complex situations and usecases | NA
2025-09-23 11:03 | Mujtaba Ahmad | Ranjith Kumar M | Dev | Zeta | 3 | No |  | Yes | Balanced | 3 | 3 | 4 | 3 | Yes | 3 | 3 | Individual | 3 | 4 | Yes | Moderately | None | Less than 10% | No | Moderate | Over Utilised (90% and Above) | Optimal information available | Yes | Average | Committed Epic Prioritisation | Sprint Planning | Ad-hoc requests prioritisation and acceptance | Blocking Scope change | None | Ad-hoc Tasks & improper prioritisation | More Than 5% but less than 10% |  | YES | No |  |  | Yes | Dev Prototype, Exploring / understanding existing codebase, Writing code for new features, Debugging and Fixing Bugs, Writing Unit tests, Creating test cases or test scripts | 20% to 50% | Local testing script for high priority bugs | High memory usage leading to system crash | Yes
2025-09-23 11:09 | Mujtaba Ahmad | Hemant Agrawal | Dev | Enigma | 4 | Yes | - | Yes | Balanced | 4 | 4 | 4 | 4 | Yes | 4 | 4 | Scrum Team | 4 | 4 | Yes | YES | Moderate | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Average | Monitoring and Controlling Progress | Sprint Retrospective | Bugs Management & Deferring | Risk call out during Weekly SoS | None | Non Release Activities | More than 10% but Less than 20% |  | YES | - |  |  | Yes | Writing code for new features, Review PRs, Debugging and Fixing Bugs, Writing Unit tests, Creating test cases or test scripts | Less than 10% | - | Good | yes
2025-09-23 11:18 | Mohammed Fayaz | Prasad Deverakonda | QA | Tetris(E2E) | 5 | Yes | We had a action item to increase bugs in September release, we have worked on | Yes | Well Managed | 5 | 5 | 5 | 5 | Yes | 5 | 5 | Scrum Team | 5 | 5 | Yes | YES | Multiple | Less than 10% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Code Freeze Milestones and hardening phase | Sprint Closure/review | Test Design | Strict Bug SLA's | Work allocation with sufficient capacity reserve | Delay in commitments from dependant team | Less than 5% | Nil | YES | No | No |  | Yes | Exploring / understanding existing codebase, Writing code for new features, Creating test cases or test scripts | 20% to 50% | To optimise the k6 tool utility, cursor was helpfull | No | Yes
2025-09-23 11:24 | Jegadeesh Santhana Krishnan | Selvakumar Thiyagarajan | Dev | Sharks | 4 | No Action items | NA | Yes | Balanced | 4 | 4 |  | 4 | Yes | 4 | 4 | Individual | 4 | 4 | Yes | YES | Moderate | Less than 10% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Average | Continuous Epic Grooming | Sprint Closure/review | Bugs Management & Deferring | Blocking Scope change | Better Estimations & Epic Breakdown | Ad-hoc Tasks & improper prioritisation | More Than 5% but less than 10% |  | YES | NA |  |  | Yes | Dev Prototype, Exploring / understanding existing codebase, Writing code for new features, Review PRs, Writing Unit tests | 20% to 50% | Used it to get a dev prototype when provided the reference of the FRD and TD | NA | yes
2025-09-23 11:30 | Mohammed Fayaz | Varun Batra | QA | Echo | 5 | Yes | Devops issue | Yes | Balanced | 4 | 5 | 5 | 5 | Yes | 5 | 5 | Individual | 5 | 5 | No | YES | Multiple | 20% to 30% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Monitoring and Controlling Progress | Sprint Planning | Non Release Activity Identification & capacity reserve | Blocking Scope change | Work allocation with sufficient capacity reserve | Non Release Activities | More than 20% |  | YES | na |  |  | Yes | Exploring / understanding existing codebase, Review PRs, Creating test cases or test scripts | 20% to 50% | identifying critical area, suggesting usecases where we might miss | Helpful to find to edge cases | yes
2025-09-23 11:32 | Mujtaba Ahmad | Ranjith Kumar M | Dev | Gryffindor | 4 | Yes | AWS-SDK | Yes | Chaotic | 2 | 4 | 2 | 5 | Yes | 2 | 2 | Scrum Team | 4 | 3 | Yes | Moderately | Moderate | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Not aware of any such initiative. Though the release coordination among teams was better than previous releases among teams | Average | Committed Epic Prioritisation | Sprint Planning | Ad-hoc requests prioritisation and acceptance | Change in Due date and QA Sign off Date restrictions | Better & transparent commitments | Reviews | Less than 5% | NA | YES | Improved Reviews | NA |  | Yes | Exploring / understanding existing codebase, Review PRs, Debugging and Fixing Bugs, Writing Unit tests | 20% to 50% | AWS-SDK, POC and unit tests | NA | Yes
2025-09-23 11:34 | Mohammed Fayaz | Prasad Deverakonda | QA & Scrum Master | Tetris(E2E) | 5 | Yes | 1. Collation common folder/env file for E2E team 2. Allocating more time for release activity for E2E | Yes | Chaotic | 5 | 5 | 5 | 5 | Yes | 5 | 5 | Scrum Team | 5 | 4 | Yes | YES | Moderate | Less than 10% | Yes | Moderate | Over Utilised (90% and Above) | Optimal information available | Yes | Average | Code Freeze Milestones and hardening phase | Sprint Closure/review | Backlog & CS bugs prioritisation | Blocking Scope change | Dependency management | Delay in commitments from dependant team | Less than 5% |  | YES |  |  |  | Yes | Exploring / understanding existing codebase, Debugging and Fixing Bugs | 20% to 50% | -Developing utilities/scripts to avoid repetitive tasks - Understanding the existing testcases and optimizing it/ writing a new set of cases by cursor by making existing cases as baseline.
2025-09-23 11:40 | Mohammed Fayaz | Varun Batra | QA | Tranformers | 2 | Yes | NA | Yes | Chaotic | 2 | 2 | 2 | 2 | Partially/Incomplete | 2 | 2 | Scrum Team | 2 | 2 | Yes | YES | Moderate | Less than 10% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Not aware of any such initiative. Though the release coordination among teams was better than previous releases among teams | Average | Committed Epic Prioritisation | Sprint Planning | Jira Details - Epic breakdown, DoD, Exit criteria, CS Bugs | Change in Due date and QA Sign off Date restrictions | Better & transparent commitments | Ad-hoc Tasks & improper prioritisation | Less than 5% |  | Not Efficiently | NA |  |  | Yes | Creating test cases or test scripts | 20% to 50% | Building testcases | Good | Slack
2025-09-23 11:43 | Jegadeesh Santhana Krishnan | Chandra Sekhar Kusupati | EM |  |  |  |  | Yes | Well Managed | 5 | 5 | 5 | 5 | Yes | 5 | 5 | Individual | 5 | 5 | Yes | YES | Moderate | Less than 10% | Yes | None | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Code Freeze Milestones and hardening phase | Sprint Planning | Jira Automation | Blocking Scope change | None | Delay in commitments from dependant team | My role involves process improvement and enablement (EM's, SM's & Other folks responsible for process streamlining) |  | YES | - |  |  | Yes | Exploring / understanding existing codebase | Greater than 50% | - | - | -
2025-09-23 11:46 | Mohammed Fayaz | Varun Batra | QA | Skywalker | 4 | Yes | Plan the trackers effectively | Yes | Chaotic | 4 | 4 | 4 | 4 | Yes | 4 | 4 | Individual | 4 | 4 | Yes | YES | Moderate | 10% to 20% | No | Moderate | Balanced (80% - 90%) | Some Information but still need further details | Yes | Average | Epic Breakdown | Sprint Planning | Tech Design | Change in Due date and QA Sign off Date restrictions | Effective communication | PR Merges | Less than 5% |  | YES | Have to be strict on QA ready Date |  |  | Yes | Exploring / understanding existing codebase, Review PRs, Creating test cases or test scripts | 20% to 50% | Understanding the PR and regression test cases | sometimes observing slowness | yes
2025-09-23 11:53 | Diksha Khatri | Diksha Khatri | Dev | Phi | 4 | Yes | There are some constant field names of FDRs, so added them in the validation script, so we won't miss them while publishing the FDRs | Yes | Balanced | 5 | 4 | 5 | 5 | Yes | 5 | 4 | Scrum Team | 5 | 4 | Yes | YES | Moderate | Less than 10% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Code Freeze Milestones and hardening phase | Sprint Closure/review | Ad-hoc requests prioritisation and acceptance | Change in Due date and QA Sign off Date restrictions | Better & transparent commitments | Ad-hoc Tasks & improper prioritisation | Less than 5% |  | YES | We need to plan the staging release prior to sprint end so it can be tested and released in the production on the release date. |  |  | Yes | Writing code for new features, Review PRs, Debugging and Fixing Bugs | 20% to 50% | Cursor is helping us for creating FDRs if automation utility is not working. It is also helpful in the http connector building. | Cursor is very powerful tool which is helping in the productivity for almost every task. | Yes, we are getting the enough support.
2025-09-23 11:56 | Mohammed Fayaz | SathishKumar D | QA | Optimus | 5 | Yes | NA | No | [32 empty] | Report portal tasks and IA | Yes | Exploring / understanding existing codebase, Writing code for new features, Review PRs, Debugging and Fixing Bugs, Creating test cases or test scripts, Pipeline changes | Greater than 50% | Rest pipeline understanding | NA | Yes
2025-09-23 12:12 | Mujtaba Ahmad | Mujtaba Ahmad | Dev | Stark | 5 | No Action items | NA | Yes | Well Managed | 4 | 4 | 4 | 4 | Yes | 4 | 4 | Individual | 4 | 4 | Yes | YES | Moderate | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Epic Breakdown | Sprint Planning | Tech Design | Blocking Scope change | Release Planning, Strategy & Schedule (Proper Checkpoint and dates on jira tickets) | Communication gap b/w dependent teams | More than 10% but Less than 20% |  | YES | NA |  |  | Yes | Dev Prototype, Exploring / understanding existing codebase, Writing code for new features, Review PRs, Debugging and Fixing Bugs, Writing Unit tests, Creating test cases or test scripts | 20% to 50% | NA | NA | NA
2025-09-23 12:27 | Jegadeesh Santhana Krishnan | Chandra Sekhar Kusupati | Dev | Helios | 5 | No Action items | NA | Yes | Balanced | 4 | 4 | 5 | 5 | Yes | 5 | 5 | Scrum Team | 5 | 5 | Yes | YES | Moderate | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Not aware of any such initiative. Though the release coordination among teams was better than previous releases among teams | Average | Continuous Epic Grooming | Sprint Planning | Intra Team Collaboration - Dependency linking on Jira by Individual owners | Change in Due date and QA Sign off Date restrictions | Sprint Planning Structure | Ad-hoc Tasks & improper prioritisation | More than 10% but Less than 20% |  | YES | NA |  |  | Yes | Dev Prototype, Exploring / understanding existing codebase, Writing code for new features, Review PRs, Debugging and Fixing Bugs, Writing Unit tests | 20% to 50% | Researching in general. | NA | Weekly meetings
2025-09-23 13:06 | Mohammed Fayaz | Varun Batra | QA | Helios | 5 | No |  | Yes | Chaotic | 3 | 3 | 4 | 4 | Partially/Incomplete | 3 | 3 | Scrum Team | 3 | 3 | Yes | YES | Moderate | Less than 10% | Yes | Multiple | Over Utilised (90% and Above) | Some Information but still need further details | Yes | Not Well | Epic Breakdown | Sprint Closure/review | Jira Details - Epic breakdown, DoD, Exit criteria, CS Bugs | Risk call out during Weekly SoS | Release Planning, Strategy & Schedule (Proper Checkpoint and dates on jira tickets) | Communication gap b/w dependent teams | More Than 5% but less than 10% |  | YES | no |  |  | Yes | Exploring / understanding existing codebase, Writing code for new features, Review PRs, Debugging and Fixing Bugs, Creating test cases or test scripts | Greater than 50% | Automation impact annalysis | No | Yes
2025-09-23 13:13 | Mohammed Fayaz | Komal Varma | QA | Iris | 4 | Yes | Backlog grooming should be done internally and BE teams. | Yes | Balanced | 3 | 4 | 5 | 5 | Yes | 4 | 4 | Individual | 4 | 4 | Yes | YES | Moderate | Less than 10% | Yes | Moderate | Over Utilised (90% and Above) | Some Information but still need further details | Yes | Well Managed | Continuous Epic Grooming | Sprint Planning | Bugs Management & Deferring | Blocking Scope change | Efficient Jira Usage (New Fields such as - Due date, QA Lead, QA Involvement, QA Signoff date) | Delay in commitments from dependant team | More than 10% but Less than 20% |  | YES | Epic should be in epic breakdown by Mid of hardening sprint and Team should have the comitted list of epic from BE team |  |  | Yes | Exploring / understanding existing codebase, Review PRs, Debugging and Fixing Bugs, Creating test cases or test scripts | 20% to 50% | Able to resolve the GIt error issue quickly now and able to analyse the impacted areas quickly | Feedback is halucinating sometimes even for small fix its giving more line of code and that is taking time to debug.In some cases its working fine and able to give 70 % correct output | Lunch n Learn series
2025-09-23 13:19 | Mujtaba Ahmad | Ranjith Kumar M | Dev | Zeta | 4 | Yes | clear communication and proper planning for adhoc meetings and work | Yes | Balanced | 3 | 4 | 3 | 4 | Yes | 4 | 4 | Scrum Team | 3 | 4 | Yes | YES | Moderate | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Some Information but still need further details | Yes | Well Managed | Committed Epic Prioritisation | Sprint Closure/review | Ad-hoc requests prioritisation and acceptance | Blocking Scope change | Effective communication | Ad-hoc Tasks & improper prioritisation | More Than 5% but less than 10% |  | YES |  |  |  | Yes | Dev Prototype, Exploring / understanding existing codebase, Writing code for new features, Review PRs, Writing Unit tests, Creating test cases or test scripts, For spikes and documentation | 20% to 50% | helped with one ws issue. | It's really great nfor learning new things, I have been using it for learning a new language and working on it. | yes
2025-09-23 14:17 | Mohammed Fayaz | Varun Batra | QA | Chipmuks | 3 | Yes | NA | Yes | Balanced | 3 | 4 | 4 | 4 | Partially/Incomplete | 4 | 4 | Scrum Team | 4 | 4 | Yes | Moderately | Moderate | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Average | Committed Epic Prioritisation | Sprint Planning | Tech Design | Risk call out during Weekly SoS | None | Ad-hoc Tasks & improper prioritisation | More Than 5% but less than 10% | NA | YES | NA | NA |  | Yes | Exploring / understanding existing codebase, Debugging and Fixing Bugs, Creating test cases or test scripts | 20% to 50% | Debugging Customer faced errors | NA | NA
2025-09-23 14:32 | Mujtaba Ahmad | Raman Soni | Dev | Apollo | 4 | Yes | NA | Yes | Balanced | 4 | 4 | 4 | 4 | Yes | 4 | 4 | SME/Epic Owner/EM/QM (Pre Defined Efforts Estimates) | 5 | 4 | Yes | YES | Moderate | More than 30% | Yes | Moderate | Balanced (80% - 90%) | Some Information but still need further details | Not aware of any such initiative. Though the release coordination among teams was better than previous releases among teams | Average | Release Kick Off | Sprint Planning | KT and recording repository | Blocking Scope change | Sprint Planning Structure | Intra team collaboration | More Than 5% but less than 10% |  | YES | NA |  |  | Yes | Dev Prototype, Exploring / understanding existing codebase, Writing code for new features, Debugging and Fixing Bugs, Writing Unit tests | Greater than 50% | helped me debug configuration file, which could have taken days | NA | If people could also share , where else the AI could be utilised
2025-09-23 14:36 | Mohammed Fayaz | Komal Varma | QA | Velocity | 5 | Yes | there were multiple items, which were mentioned in the Retro sheet | Yes | Well Managed | 5 | 4 | 5 | 5 | Partially/Incomplete | 5 | 4 | Scrum Team | 4 | 4 | Yes | YES | Moderate | 10% to 20% | Yes | None | Balanced (80% - 90%) | Some Information but still need further details | Yes | Well Managed | Continuous Epic Grooming | Sprint Planning | Backlog & CS bugs prioritisation | Blocking Scope change | Release Planning, Strategy & Schedule (Proper Checkpoint and dates on jira tickets) | Communication gap b/w dependent teams | Less than 5% |  | YES | No improvements needed, as of now it is going smooth. We will share the suggestions if there are any. | NA |  | Yes | Writing code for new features, Creating test cases or test scripts | 20% to 50% | Performed load testing using script shared by cursor | good | yes
2025-09-23 14:39 | Jegadeesh Santhana Krishnan | Jegadeesh Santhana Krishnan | EM |  |  |  |  | No | [32 empty] | Working with all product stakeholders and dev and QA teams to get all epics delivered. | Yes | Exploring / understanding existing codebase, Review PRs | Greater than 50% | There was a bug on lastexportdatetime and team was struggling on that - I used cursor to understand FLET ecosystem and was able to give some directions to the team etc....... | Continue to use for understanding codebase and even fixing uncaughts/flow stucks etc | Yes
2025-09-23 14:46 | Mohammed Fayaz | Mohammed Fayaz | QA | Dynamos | 5 | Yes | Code review and stream line the QA handoff date | Yes | Balanced | 5 | 5 | 4 | 4 | Yes | 4 | 5 | Scrum Team | 5 | 5 | Yes | YES | Moderate | Less than 10% | Yes | Moderate | Balanced (80% - 90%) | Some Information but still need further details | Yes | Well Managed | Monitoring and Controlling Progress | Sprint DSU's | Jira Details - Epic breakdown, DoD, Exit criteria, CS Bugs | Change in Due date and QA Sign off Date restrictions | None | Delayed Response on open Queries, need multiple followups | Less than 5% |  | YES | No | No |  | Yes | Dev Prototype, Exploring / understanding existing codebase, Creating test cases or test scripts | 20% to 50% | Build a customize mocker api, json compare , salesforce data simulator for testing | right now no. | Getting enough support
2025-09-23 14:47 | Mohammed Fayaz | Mohammed Fayaz | Architect/Individual Contributors |  |  |  |  | No | [32 empty] | Predictive Bug Analysis Engine | Yes | Exploring / understanding existing codebase, Writing code for new features, Review PRs, Debugging and Fixing Bugs, Writing Unit tests | 20% to 50% | Each Analyser in Predictive Bug Analysis Engine does few OpenAI APi calls, Git and JIRA calls. I wanted to have single class which tracks the API calls, TOkens used and also custom logger for easy debugging. With a single prompt, Cursor generated entire modularised code with out any errors using singleton design pattern | While tryygin to generate testcases for each endpoint on the given repo, It stucks in the middle and when we prompt to contiue, it strats from the beginning. Also while cross referencing repo, it loses context in the middle | Getting enough support
2025-09-23 14:49 | Mohammed Fayaz | Mohammed Fayaz | EM |  |  |  |  | Yes | Chaotic | 2 | 5 | 4 | 4 | Partially/Incomplete | 3 | 3 | Scrum Team | 4 | 3 | Yes | YES | Moderate | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Some Information but still need further details | Not aware of any such initiative. Though the release coordination among teams was better than previous releases among teams | Average | Continuous Epic Grooming | Sprint Planning | Ad-hoc requests prioritisation and acceptance | Strict Bug SLA's | Reduced over commit | Communication gap b/w dependent teams | My role involves process improvement and enablement (EM's, SM's & Other folks responsible for process streamlining) |  | YES | No |  |  | Yes | Exploring / understanding existing codebase, Creating test cases or test scripts | Less than 10% | Understanding existing code, Impact analysis using commit PR | No | Yes
2025-09-23 14:53 | Mohammed Fayaz | Tharuni Sai Idupulapati | Architect/Individual Contributors |  |  |  |  | No | [32 empty] | I was working on these initiatives 1. Automation first approach planning, 2. Keda based autoscaling to include open connection threshold for http-adaptor pod autoscaling 3. Static code scanning and validation to identify possible CPU spikes and memory leaks using cursor for HTTP-Adaptor and js-runtime microservice | Yes | Exploring / understanding existing codebase, Debugging and Fixing Bugs, - Built k6 performance test framework to test websocket paginated messages, static code analysis to find CPU spikes and memory leak with real time testing framework | 20% to 50% | 1. I was able to build k6 based performance test automation framework quickly to meet the need of web-socket messaging testing, along with updated html and console report 2. Working alongside with cursor as companion helped me understand how can I use q&a from cursor or any other AI to provide it more direct and focused context. I also discovered cursor or any other AI can effectively teach us how to effectively use it. We need to just ask it in right way. AI can also help us know the wight way to ask also. This goes deep and there are lot of learnings. Instead of using AI as slave or a smart worker (by trusting everything), we can use it as mentor, guide, friend and colleague as per the need. | We should promote cursor to ask us questions for the task we are performing so that it can help us understand what points are we missing. And also I would recommend regular use of .cursorignore and .cursorrules. Cursor will help us generate the .cursorrules | Yes, I am getting the required help. But as per my interaction with cursor so far , I learned a way to self teach myself for any issues related to AI or cursor. any AI can teach us how to effectively use it.
2025-09-23 15:00 | Mohammed Fayaz | Mohammed Fayaz | Architect/Individual Contributors |  |  |  |  | Yes | Well Managed | 5 | 5 | 4 | 5 | Yes | 5 | 5 | Scrum Team | 5 | 4 | Yes | YES | Multiple | 10% to 20% | Yes | None | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Continuous Epic Grooming | Sprint Closure/review | KT and recording repository | Change in Due date and QA Sign off Date restrictions | Release Planning, Strategy & Schedule (Proper Checkpoint and dates on jira tickets) | Ad-hoc Tasks & improper prioritisation | Less than 5% | NA | YES | NA | NA |  | Yes | Writing code for new features, Creating test cases or test scripts | 20% to 50% | NA | NA | More hands on sessions
2025-09-23 15:05 | Mohammed Fayaz | Komal Varma | QA | Chloris | 5 | No Action items | no action items as part of last release | Yes | Chaotic | 4 | 5 | 5 | 5 | Yes | 4 | 5 | Scrum Team | 5 | 5 | Yes | YES | Multiple | 10% to 20% | Yes | Multiple | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Code Freeze Milestones and hardening phase | Sprint Planning | Ad-hoc requests prioritisation and acceptance | Risk call out during Weekly SoS | None | Ad-hoc Tasks & improper prioritisation | More Than 5% but less than 10% |  | YES | no |  |  | Yes | Creating test cases or test scripts | 20% to 50% | helped me in generating all the detailed scenarios to be covered and impacted areas for epics | No | yes
2025-09-23 15:24 | Mujtaba Ahmad | Hemant Agrawal | Dev | Enigma | 3 | Yes | N/A | No | [33 empty] | Yes | Dev Prototype, Exploring / understanding existing codebase, Writing code for new features, Debugging and Fixing Bugs, Writing Unit tests, Creating test cases or test scripts | Greater than 50% | I created a complete MCP server project with Cursor | N/A | Yes
2025-09-23 15:36 | Mohammed Fayaz | Komal Varma | QA | Hercules | 5 | Yes | To reduce ad-hoc tasks and planned accordingly | Yes | Balanced | 4 | 4 | 5 | 5 | Yes | 5 | 5 | Scrum Team | 5 | 4 | Yes | YES | Moderate | Less than 10% | Yes | None | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Code Freeze Milestones and hardening phase | Sprint Planning | Backlog & CS bugs prioritisation | Risk call out during Weekly SoS | Sprint Planning Structure | Ad-hoc Tasks & improper prioritisation | More than 10% but Less than 20% | No comments | YES | No comments | No comments |  | No | Writing code for new features | 20% to 50% | Didn't used cursor as such mostly used chatgpt. | Nothing as of now | Yes
2025-09-23 15:49 | Mujtaba Ahmad | Raman Soni | Dev | Apollo | 5 | Yes | Action items are taken up by team like maintaining burnup chart and burndown chart, adaoption of AI/cursors and individuals take ownership on these action items to get them done. | Yes | Balanced | 4 | 5 | 5 | 5 | Yes | 4 | 5 | Scrum Team | 5 | 5 | Yes | YES | Moderate | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Committed Epic Prioritisation | Sprint Planning | Ad-hoc requests prioritisation and acceptance | Blocking Scope change | Reduced over commit | Ad-hoc Tasks & improper prioritisation | More Than 5% but less than 10% |  | YES | NA |  |  | Yes | Exploring / understanding existing codebase, Review PRs, Debugging and Fixing Bugs | 20% to 50% | Cursor helps to identify probable causes for test failures, intermittent issues and refactoring or writing code. | NA | Yes, getting all the support.
2025-09-23 15:49 | Mujtaba Ahmad | Raman Soni | Dev | Apollo | 4 | Yes | Review trackers should be assign before sprint start In this sprint, team has assigned before sprint start | Yes | Balanced | 4 | 4 | 4 | 4 | Yes | 4 | 3 | Scrum Team | 3 | 3 | Yes | YES | Moderate | Less than 10% | No | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Average | Epic Breakdown | Sprint Planning | Intra Team Collaboration - Dependency linking on Jira by Individual owners | Risk call out during Weekly SoS | Reduced over commit | Intra team collaboration | More Than 5% but less than 10% |  | YES | no |  |  | Yes | Exploring / understanding existing codebase, Writing Unit tests | 20% to 50% | it helps in writing the testcases | Sometime for small tasks we have to give prompt multiple time so that it give correct response and also we can't relay on cursor in even understanding the code as sometime it understand it incorrectly. | yes, Lunch n Learn series
2025-09-23 15:51 | Mohammed Fayaz | Komal Varma | QA | Pheonix | 5 | No Action items | NA | Yes | Balanced | 5 | 5 | 5 | 5 | Yes | 5 | 5 | Scrum Team | 5 | 5 | Yes | YES | Moderate | 10% to 20% | Yes | None | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Committed Epic Prioritisation | Sprint Planning | CI/CD, Testing & Continuous planning | Blocking Scope change | Efficient Jira Usage (New Fields such as - Due date, QA Lead, QA Involvement, QA Signoff date) | Communication gap b/w dependent teams | More Than 5% but less than 10% | NA | YES | NA | NA |  | Yes | Review PRs, Creating test cases or test scripts | Greater than 50% | Was able to write playwright automation cases quickly | NA | Yes getting good support
2025-09-23 15:52 | Jegadeesh Santhana Krishnan | Jegadeesh Santhana Krishnan | Architect/Individual Contributors |  |  |  |  | No | [32 empty] | ERP logging reviews & worker resource optimisation | Yes | Exploring / understanding existing codebase, Writing code for new features, Review PRs, Writing Unit tests | 20% to 50% | Able to find the bug very quickly | NA | Yes
2025-09-23 16:07 | Mohammed Fayaz | Komal Varma | QA | Eirene | 4 | No |  | Yes | Balanced | 3 | 5 | 5 | 5 | Yes | 4 | 4 | Individual | 4 | 4 | Yes | YES | Moderate | Less than 10% | Yes | Moderate | Balanced (80% - 90%) | Some Information but still need further details | Yes | Average | Epic Breakdown | Sprint Retrospective | Non Release Activity Identification & capacity reserve | Change in Due date and QA Sign off Date restrictions | Release Planning, Strategy & Schedule (Proper Checkpoint and dates on jira tickets) | Communication gap b/w dependent teams | Less than 5% |  | YES | No |  |  | Yes | Exploring / understanding existing codebase, Review PRs, Creating test cases or test scripts | 20% to 50% | While fixing some failing test cases, I noticed multiple cases had the same root cause. When I opened a similar file again, Cursor automatically suggested exactly which line to change based on previous edits. It saved time and made the fix consistent across files. | Cursor is great at picking up patterns across similar files and suggesting consistent changes, especially when fixing repeated issues. | Mostly yes
2025-09-23 16:11 | Mohammed Fayaz | Komal Varma | QA | Helios | 5 | Yes | need to resolve dependency faster | Yes | Balanced | 4 | 4 | 5 | 5 | Yes | 5 | 5 | Scrum Team | 4 | 5 | Yes | YES | Multiple | 10% to 20% | Yes | Multiple | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Monitoring and Controlling Progress | Sprint DSU's | Intra Team Collaboration - Dependency linking on Jira by Individual owners | Blocking Scope change | Sprint Planning Structure | Communication gap b/w dependent teams | More than 10% but Less than 20% |  | YES | no |  |  | Yes | Exploring / understanding existing codebase, Review PRs, Creating test cases or test scripts | 20% to 50% | we can automate bugs by connecting to jira directly using mcp | good but seems slow at times | yes
2025-09-23 16:17 | Jegadeesh Santhana Krishnan | Subhan Ansari | Dev | Nebulancer | 5 | No Action items | NA | No | [32 empty] | Spikes/Design research on AI initiatives related to MCP server. | Yes | Dev Prototype, Exploring / understanding existing codebase, Review PRs, Debugging and Fixing Bugs | 20% to 50% | I have been using Cursor to complete tasks that I do not have a prior experience on. I have completed docker related tasks via Cursor's help. | NA | Yes
2025-09-23 16:43 | Jegadeesh Santhana Krishnan | Anusha Badveeti | Dev | Aliens | 5 | Yes | planned that qa should get enough time for testing the stories. we should plan accordingly | Yes | Well Managed | 5 | 5 | 5 | 5 | Yes | 5 | 5 | Individual | 5 | 5 | Yes | YES | Moderate | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Monitoring and Controlling Progress | Sprint DSU's | Jira Details - Epic breakdown, DoD, Exit criteria, CS Bugs | Change in Due date and QA Sign off Date restrictions | Better & transparent commitments | Reviews | Less than 5% |  | YES | no |  |  | Yes | Dev Prototype, Exploring / understanding existing codebase, Writing code for new features, Review PRs, Debugging and Fixing Bugs, Writing Unit tests | 20% to 50% | helped me to understand code. as a new developer i can play with cursor and ask my doubts regarding code like how this works and what are the advantage to use this kind of approach etc. | should define cursorRules files in all the repos and define the rules so overall response generation would be better | yes
2025-09-23 17:05 | Mujtaba Ahmad | Hemant Agrawal | Dev | Enigma | 5 | Yes | Keeping stories shorter | Yes | Well Managed | 5 | 5 | 5 | 5 | Yes | 5 | 5 | Scrum Team | 5 | 5 | Yes | YES | Moderate | Less than 10% | No | None | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Monitoring and Controlling Progress | Sprint Planning | CI/CD, Testing & Continuous planning | Change in Due date and QA Sign off Date restrictions | Better Estimations & Epic Breakdown | Communication gap b/w dependent teams | Less than 5% |  | YES | No |  |  | Yes | Writing code for new features, Debugging and Fixing Bugs | 20% to 50% | Automating repeated tasks | No | Yes
2025-09-23 17:15 | Mohammed Fayaz | Varun Batra | QA | Dynamos | 5 | Yes | Expedite PR reviews | Yes | Balanced | 5 | 5 | 5 | 5 | Yes | 5 | 5 | Individual | 5 | 5 | Yes | YES | Moderate | 10% to 20% | No | Moderate | Balanced (80% - 90%) | Some Information but still need further details | Yes | Well Managed | Continuous Epic Grooming | Sprint Planning | Jira Details - Epic breakdown, DoD, Exit criteria, CS Bugs | Blocking Scope change | Release Planning, Strategy & Schedule (Proper Checkpoint and dates on jira tickets) | Improper Epic Breakdown & Estimations - Missing Sprint Backlog | More than 10% but Less than 20% |  | YES | Local setup, we should implement a process around it. This can help the team to seamlessly set it up and run. Currently, everyone is facing different issues and fixing their local issues. If we have a defined process to have this tracked in a central place, and have all the local setup issues and changes in respective services merged to the main on time, it can help the team move forward. |  |  | Yes | Dev Prototype, Exploring / understanding existing codebase, Writing code for new features, Review PRs, Debugging and Fixing Bugs, Writing Unit tests, Creating test cases or test scripts | 20% to 50% | Developed utilities to create test data at scale to test NFRs. Identify potential bugs in code base and fix it. but it needs to be carefully reviwed before going with the Cursor suggestions . Fix the outdated OpenAPI specs | It is good code assistant but cant completely rely on it. | Yes
2025-09-23 17:53 | Jegadeesh Santhana Krishnan | Subhan Ansari | Dev | nebulancer | 5 | No Action items | No action items | Yes | Balanced | 5 | 5 | 4 | 5 | Yes | 5 | 5 | Scrum Team | 4 | 5 | Yes | YES | Multiple | 10% to 20% | No | Multiple | Over Utilised (90% and Above) | Optimal information available | Yes | Well Managed | Continuous Epic Grooming | Sprint Planning | Jira Automation | Blocking Scope change | Release Planning, Strategy & Schedule (Proper Checkpoint and dates on jira tickets) | Improper Epic Breakdown & Estimations - Missing Sprint Backlog | More Than 5% but less than 10% |  | YES | None |  |  | Yes | Dev Prototype, Review PRs, Debugging and Fixing Bugs | 20% to 50% | understanding new codebase | Need to work smartly with Cursor as it has its issues. | yes
2025-09-23 17:53 | Jegadeesh Santhana Krishnan | Subhan Ansari | Dev | Skywalker | 5 | Yes | Better sprint planning | Yes | Balanced | 4 | 5 | 5 | 5 | Yes | 4 | 4 | Scrum Team | 5 | 5 | Yes | YES | Moderate | Less than 10% | Yes | Moderate | Over Utilised (90% and Above) | Optimal information available | Yes | Average | Continuous Epic Grooming | Sprint Planning | Jira Details - Epic breakdown, DoD, Exit criteria, CS Bugs | Risk call out during Weekly SoS | Sprint Planning Structure | PR Merges | Less than 5% |  | YES | NA |  |  | Yes | Dev Prototype, Writing code for new features, Review PRs, Debugging and Fixing Bugs, Writing Unit tests | 20% to 50% | NA | NA | NA
2025-09-23 17:56 | Jegadeesh Santhana Krishnan | Subhan Ansari | Dev | Aliens | 4 | Yes | Have Proper Descriptive trackers | Yes | Well Managed | 4 | 5 | 4 | 4 | Yes | 5 | 4 | Scrum Team | 4 | 4 | Yes | YES | Multiple | Less than 10% | Yes | None | Balanced (80% - 90%) | Some Information but still need further details | Yes | Well Managed | Epic Breakdown | Sprint Planning | Jira Details - Epic breakdown, DoD, Exit criteria, CS Bugs | Strict Bug SLA's | Better & transparent commitments | Communication gap b/w dependent teams | Less than 5% |  | YES | No |  |  | Yes | Exploring / understanding existing codebase, Writing code for new features, Review PRs, Debugging and Fixing Bugs, Writing Unit tests, Creating test cases or test scripts | Greater than 50% | For Writing Unit-testcases | None | Yes
2025-09-23 18:06 | Jegadeesh Santhana Krishnan | Subhan Ansari | Dev | Skywalker | 5 | Yes | n | Yes | Well Managed | 5 | 5 | 5 | 5 | Yes | 4 | 5 | Scrum Team | 4 | 5 | Yes | YES | Multiple | 20% to 30% | Yes | Moderate | Balanced (80% - 90%) | Some Information but still need further details | Yes | Well Managed | Continuous Epic Grooming | Sprint Planning | Intra Team Collaboration - Dependency linking on Jira by Individual owners | Change in Due date and QA Sign off Date restrictions | Efficient Jira Usage (New Fields such as - Due date, QA Lead, QA Involvement, QA Signoff date) | PR Merges | Less than 5% |  | YES | no |  |  | Yes | Exploring / understanding existing codebase, Debugging and Fixing Bugs, Writing Unit tests, Creating test cases or test scripts | 20% to 50% | writing the testcases to impove thje vocerage | sometime it makes things difficult by taking a wrong approach when easy ones are present | yes
2025-09-23 18:12 | Jegadeesh Santhana Krishnan | Ramakrishna Grandhi | Dev | Aliens | 5 | Yes | There were few bugs and some epic items . | Yes | Well Managed | 4 | 5 | 5 | 5 | Yes | 5 | 5 | Individual | 4 | 4 | Yes | Moderately | Multiple | 20% to 30% | Yes | Moderate | Balanced (80% - 90%) | Some Information but still need further details | Not aware of any such initiative. Though the release coordination among teams was better than previous releases among teams | Well Managed | Epic Breakdown | Sprint Closure/review | Bugs Management & Deferring | Risk call out during Weekly SoS | Risk call out (Release Confluence Page) | Communication gap b/w dependent teams | More than 10% but Less than 20% |  | YES | Lets try to find uncaught exceptions little before so that we get time to fix it. |  |  | Yes | Writing code for new features | 20% to 50% | For finding the usage of particular pattern in the entire code base. | We need to verify all the changes with detail .. Most of the time it uses variables which are not in scope of that block. | Yes
2025-09-23 18:21 | Jegadeesh Santhana Krishnan | Jegadeesh Santhana Krishnan | Dev | Aliens | 5 | Yes | NA | Yes | Well Managed | 5 | 5 | 5 | 5 | Yes | 5 | 5 | Scrum Team | 5 | 5 | Yes | YES | Multiple | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Continuous Epic Grooming | Sprint Planning | CI/CD, Testing & Continuous planning | Change in Due date and QA Sign off Date restrictions | None | Delay in commitments from dependant team | Less than 5% | NA | YES | NA | NA |  | Yes | Dev Prototype, Exploring / understanding existing codebase, Writing code for new features, Review PRs, Debugging and Fixing Bugs, Writing Unit tests | Greater than 50% | NA | NA | NA
2025-09-23 18:28 | Jegadeesh Santhana Krishnan | Subhan Ansari | Dev & Scrum Master | Skywalker | 4 | No Action items | NA | Yes | Balanced | 4 | 4 | 4 | 4 | Yes | 4 | 4 | SME/Epic Owner/EM/QM (Pre Defined Efforts Estimates) | 4 | 4 | Yes | YES | Multiple | 20% to 30% | Yes | Multiple | Balanced (80% - 90%) | Some Information but still need further details | Yes | Average | Continuous Epic Grooming | Sprint Planning | KT and recording repository | Change in Due date and QA Sign off Date restrictions | Better Estimations & Epic Breakdown | Delayed Test Designs | More than 10% but Less than 20% | No | YES | No | No |  | Yes | Review PRs | 20% to 50% | Apply git changes directly from a commit instead of merging. | No | Yes
2025-09-23 18:33 | Jegadeesh Santhana Krishnan | Subhan Ansari | Dev & Scrum Master | Aliens | 5 | Yes | Jira board hygiene Action item: Stories were stuck in “In Progress” with unclear ownership. Resolution: Simplified statuses, added assignee + due date fields, and did a 5-minute daily “stuck items” review in standup. Outcome: Fewer carryovers; better visibility on blockers. Follow-up: Keep the daily “stuck” call-out and enforce story owners. | Yes | Well Managed | 5 | 5 | 4 | 5 | Yes | 5 | 5 | SME/Epic Owner/EM/QM (Pre Defined Efforts Estimates) | 5 | 5 | Yes | YES | Multiple | 20% to 30% | Yes | None | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Committed Epic Prioritisation | Sprint Closure/review | Ad-hoc requests prioritisation and acceptance | Change in Due date and QA Sign off Date restrictions | Release Planning, Strategy & Schedule (Proper Checkpoint and dates on jira tickets) | PR Merges | More than 10% but Less than 20% |  | YES | Carryover review in retro (owner: Team) — For each carryover: cause, fix, single next action. Target: ≤10% story points carried over. | QA skip should not have QA ready/signoff dates |  | Yes | Dev Prototype, Exploring / understanding existing codebase, Writing code for new features, Review PRs, Debugging and Fixing Bugs, Writing Unit tests, Creating test cases or test scripts | Greater than 50% | For sprint demo prep, I fed Cursor the feature brief and recent commits and asked for a 2-minute demo script. It gave me a crisp narrative (problem → change → outcome) and a quick rollback note. The demo stayed on time and landed approvals faster. | Use Cursor as a structured pair-programmer, not just autocomplete: standardize prompt templates per repo, use “chat with selection” for targeted changes, require Cursor to draft tests and PR descriptions, and keep AI diffs small and reviewable. Measure success by reduced review churn and faster UAT sign-off. | Customizing AI adoption support by role (e.g., engineers, QA, PMs, support) so each group sees direct value in their day-to-day work. This could also be short 10-minute demo clips per role.
2025-09-23 22:17 | Jegadeesh Santhana Krishnan | Subhan Ansari | Dev | nebulancer | 4 | No Action items | no action items | Yes | Well Managed | 4 | 5 | 4 | 4 | Yes | 4 | 5 | Scrum Team | 4 | 5 | Yes | YES | Multiple | 10% to 20% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Continuous Epic Grooming | Sprint Planning | Jira Automation | Change in Due date and QA Sign off Date restrictions | None | Intra team collaboration | Less than 5% |  | YES | na |  |  | Yes | Dev Prototype, Creating test cases or test scripts | Less than 10% | na | na | na
2025-09-24 06:18 | Jegadeesh Santhana Krishnan | Ankur Sachdeva | Dev | Echo | 5 | No Action items | NA | Yes | Chaotic | 3 | 5 | 3 | 4 | Yes | 4 | 5 | Scrum Team | 5 | 5 | Yes | YES | Moderate | 20% to 30% | Yes | Multiple | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Committed Epic Prioritisation | Sprint Closure/review | CI/CD, Testing & Continuous planning | Change in Due date and QA Sign off Date restrictions | Efficient Jira Usage (New Fields such as - Due date, QA Lead, QA Involvement, QA Signoff date) | Delayed Test Designs | More Than 5% but less than 10% |  | YES | NA | NA |  | Yes | Dev Prototype, Exploring / understanding existing codebase, Writing code for new features, Debugging and Fixing Bugs, Writing Unit tests | 20% to 50% | NA | NA | NA
2025-09-24 10:28 | Jegadeesh Santhana Krishnan | Ankur Sachdeva | Dev | Chipmuks | 4 | Yes | task prioritizations | Yes | Chaotic | 4 | 3 | 3 | 4 | Partially/Incomplete | 4 | 4 | Scrum Team | 4 | 4 | Yes | YES | Multiple | Less than 10% | No | Moderate | Balanced (80% - 90%) | Some Information but still need further details | Yes | Well Managed | Committed Epic Prioritisation | Sprint Planning | Tech Design | Blocking Scope change | Reduced over commit | Modifications on Approved Tech designs | Less than 5% |  | YES | - |  |  | Yes | Exploring / understanding existing codebase, Writing code for new features, Review PRs, Debugging and Fixing Bugs, Writing Unit tests | 20% to 50% | test cases and simplifying complex logic | - | yes
2025-09-24 11:26 | Jegadeesh Santhana Krishnan | Anusha Badveeti | Dev & Scrum Master | Dynamos | 4 | Yes | PR review process wa very slow in the team. So we come up with daily mandatory call wherever pr reviews are being done and we are able to close prs faster | Yes | Balanced | 4 | 5 | 5 | 5 | Yes | 4 | 4 | Scrum Team | 5 | 4 | Yes | YES | Moderate | Less than 10% | Yes | Moderate | Balanced (80% - 90%) | Optimal information available | Yes | Well Managed | Continuous Epic Grooming | Sprint Closure/review | KT and recording repository | Blocking Scope change | Release Planning, Strategy & Schedule (Proper Checkpoint and dates on jira tickets) | Improper Epic Breakdown & Estimations - Missing Sprint Backlog | My role involves process improvement and enablement (EM's, SM's & Other folks responsible for process streamlining) |  | YES | NA |  |  | Yes | Dev Prototype, Exploring / understanding existing codebase, Writing code for new features, Debugging and Fixing Bugs, Writing Unit tests | 20% to 50% | I had to write a TD for a feature which involves touching a existing core functionality which i have never worked on. Cursor helped me a lot in understanding the code quickly and play with it | NA | YES